## ALL PROJECTS MONTHLY REPORT
A | B | C | D | E | F | G | H | I | J | K | L=J+K | M | N | O | P=N+O | Q=O/N | R=DATE-T | S=R/P | T | U=T+N-1 | V=T+P-1 | W | X | Y | Z | AA | AB | AC | AD=AB+AC | AE=AC/AB | AF | AG | AH=AF+AG | AI=AH/AD | AJ=(W-T)/I | AK | AL | AM | AN
RQ | Municipality | Name of the Project | PHAPR Monitor | Management Agent | Construction Manager/PM | Designer (A/E) | Contractor | Units |  |  |  |  | Times | [5 empty] | Dates | [5 empty] | Funds | [9 empty] | Certified Days/Unit | % Progress | Monthly Employment | Executive Summary | Status
[8 empty] | Total Dwelling Units | Previous Completed Dwelling Units | Completed Dwelling Units for this Period | Total Completed Dwelling Units | Dwelling Units Forecast for next Month | Contruction Period (Cal. Days) | Time Extension (Cal. Days) | Revised Construction Period (Cal. Days) | % Extended Time | Elapsed Time (Cal. Days) | Elapsed Time (%) | Construction Start Date | Original Completion Date | Revised Construction Completion Date | Substantial Completion Date | Final Acceptance Date | Registered at Controller Contract Termination Date | Funds Proceeds | Funds Obligation Date | Original Construction Contract Amount | Approved Change Orders Amount ($) | Revised Construction Contract Amount | % Of Change Orders | Previous Certified Amount | Certified this Period | Total Certified Amount | Certified Amount (%)
3025 | Carolina | Felipe Sánchez Osorio (Demolition) | Luis Rodríguez | N/A | Municipio de Carolina | State Engineering | Municipio de Carolina | 32 | 26 | 0 | 26 | 0 | 120 | 0 | 120 | 0% | 259 | 215.8% | 2013-08-14 | 2013-12-11 | 2013-12-11 | [5 empty] | 336510 | 0 | 336510 | 0% | 27516.72 | 122054.24 | 149570.96 | 44.45% |  |  |  | ♦ Project Situation according to the CPM Uptaded: Phase I was completed on November 27, 2013. ♦ Reasons of the Delay (if applies) N/A ♦ Change Order in PRPHA pending for approval: N/A ♦ Extraordinary Situations with Relocation (if applies)- N/A ♦ Situations with Governmental Agencies (if applies): N/A ♦ Others situations that are affecting the project (if Applies): N/A | Active
5127 | Arecibo | La Meseta | Pedro Vega | Housing Promoters, Inc. | AVP | ERA | Maglez Engineering & Contractors, Corp. | 0 | 0 | 0 | 0 | 0 | 365 | 0 | 365 | 0% | 394 | 107.9% | 2013-04-01 | 2014-03-31 | 2014-03-31 |  |  | 2014-03-31 | CFP |  | 1602797 | 0 | 1602797 | 0% | 979943.16 | 71165.27 | 1051108.43 | 65.58% |  |  |  | • Project Situation: Some submmittal requirement from designer are delaying the Contractor's time to make purchase orders or solve construction problems as design error for primary system upgrade. • Project Status: Last CPM Updated february 28,2014, refected a reduction of project delay from 49 days behind schedule. There is a CO #1 with 14 calendars days pending for PRPHA approval. New letter of intents are in negotiation that can reflect additional extension claim. • Change Orders: CO #1 $41,193.88 where send to PRPHA. • Last Certification: #11 february 28, 2014 • Relocation issues: There is not Relocation issues. • Goverment Agencies issues: AEE are requiring change to approved design that represent additional cost to project. • Other Situation issues: There is not AAA endorsement. this month the designer submmit the endorsement amedment. | Active
4011 | Mayaguez | Rafael Hernandez (El Kennedy) | Noefebdo Ramírez | JA Machuca | Klassik Builders | Hernán Jr. Machado Ingenieros Consultores | F & R Construction | 190 | 26 | 0 | 26 | 24 | 1094 | 153 | 1247 | 13.99% | 926 | 74.26% | 2011-10-17 | 2014-10-14 | 2015-03-16 |  |  | 2016-02-07 | CFP |  | 21797000 | 446287.81 | 22243287.81 | 2.047% | 13868385.06 | 204312.21 | 14072697.27 | 63.27% |  |  |  | • Project situation according to the CPM updated: According to the last CPM updated, the project finish date is September 3, 2015. The contract revisedconstruction completion date is March 16,2015. That represent 171 days of delay. When thechange order # 9 be approvedthe completion date move to May 30, 2015. the Change Order # 10 included 10 aditional days for weather conditions. Then represent 58 days of delay. • Reasons of the Delay: One reasons is the delay for termination and delivery of modernized units by the Contractors. The lead and asbestos abatement started on February 3,2014 to enclosure the building # 4. The buildingcome to be ready to start the works on March 21,2014, No contruction works can't do it into the buildings. Those impact the crithical path which is total responsability of the contractor. In special the building # 18, which in the next building in the modernization sequence and are stopped for 108 days. • Change Order in PRPHA pending for approval:. The CO # 9 (193,914.32 and include 75 calendar days extension) and change order # 10 (of $562,564.73 and include 10 calendar days extension) • Payments Certifications Status: The Contractor has pending to submit to PRPHA the Certifications for partial payment of # 30 (February 2014 period) and # 31 (March 2014 period) • Extraordinary Situations with Relocation - N/A • Situations with Governmental Agencies: The tapping conection for the potable water services, under the PR #2 state road was not do it in this period. This tapping is a change order in a process of negotiation. The AAA final endosement depend of finish this connection works. The Puerto Rico Power Authority present a new request to install other facilities for existingsanitary pump station. That works were not contemplted in the design. • Others situations that are affecting the project: The installationof the restrainers in the 36 inches ductile iron forced line was not completed in this period. A 70% of the total pipe line need to be reinstalling. A wprkplan was by KBI to the Contractor to define this work to be done during summer school vacation as requested. | Active
3105 | San Juan | Ext. Manuel A. Pérez | Arturo Acevedo | MAS Corp. | Klassik Builders | DDHK | LPC&D | 324 | 188 | 12 | 200 | 12 | 1098 | 433 | 1531 | 39.44% | 1385 | 90.46% | 2010-07-15 | 2013-07-16 | 2014-09-22 |  |  | 2015-08-06 | HOPE IV |  | 24800000 | 1110120.04 | 25910120.04 | 4.476% | 19847694.84 | 161086 | 20008780.84 | 77.22% |  |  |  | • Project situation according to the CPM updated • Reasons of the Delay (if applies) • Payments Certifications Status- Lastcertification rendered for payment is certification # 42, for the period of January 2014. • Change Orders: • Extraordinary Situations with Relocation (if applies)-N/A • Situations with Governmental Agencies (if applies)-N/A • Others situations that are affecting the project (if applies)-N/A • Withheld: | Active
5034 | San Juan | Alturas de Cupey | José M. Paris | SP Management Corp. | Klassik Builders | CSA | F&R Construction | 96 | 48 | 16 | 64 | 0 | 732 | 256 | 988 | 34.97% | 1057 | 107% | 2011-06-08 | 2013-06-08 | 2014-02-19 |  |  | 2015-06-20 | CFP |  | 7936000 | 1003018.78 | 8939018.78 | 12.64% | 7832237.98 | 470242.15 | 8302480.13 | 92.88% |  |  |  | • Project situation according to the CPM updated: According to the last CPM updated on June 2013, the project is 72 calendar days ahead schedule with a possible termination date on December 19, 2013. • Reasons of the Delay (if applies) • Bad execution by the Contractor (if applies)- N/A • Change Orders pending for approval - N/A • Others (if applies) - a) Weather and site conditions (Soil Moisture) • Change Order in PRPHA pending for approval: N/A • Latest Certification: The last certification for payment submitted by the Contractor correspond to the period of July 26, 2013 thru August 25, 2013 (Certification #27 for the amount of $470,242.15 • Extraordinary Situations with Relocation (if applies) - N/A • Situations with Governmental Agencies (if applies) - N/A • Others situations that are affecting the project (if applies) - N/A | Active
5068 | San Juan | Las Amapolas (Demolition) | Noefebdo Ramírez | SP Management Corp. | AVP | Integra | Anibal Díaz Construction, Inc. | 204 | 138 | 50 | 188 | 16 | 365 | 0 | 365 | 0% | 176 | 48.22% | 2013-11-05 | 2014-11-04 | 2014-11-04 |  |  | 2015-10-30 | CFP |  | 948000 | 0 | 948000 | 0% | 231193.27 | 0 | 231193.27 | 24.39% |  |  |  | • Project situation according to CPM (updated): According to the CPM, the project is on schedule. • Reasons of Delay: none • Change Orders in PRPHA pending for Approval: none • Payments CertificationS Status: The contractor has pending to submit to PRPHA the certificactions for the partial Payments # 3 (February 2014) and #4 (March 2014 period) • Extraordinary situations with Relocation: N/A • Situations with Governmental Agencies: none • Other situations that are affecting the project: No report in this moment. | Active
5028 | Yauco | Ana Catalina Rodríguez Vélez (Santa Catalina) | Arturo Acevedo | JA Machuca | AVP | URS Caribe LLC | La Mar Construction Corporation | 200 | 154 | 0 | 154 | 8 | 1098 | 339 | 1437 | 30.87% | 1525 | 106.1% | 2010-02-25 | 2013-02-26 | 2014-01-31 |  |  | 2014-11-26 | ARRA/Mixed |  | 17447000 | 1678841 | 19125841 | 9.623% | 17208971.22 | 242602.15 | 17451573.37 | 91.25% |  |  |  | • Project situation according to CPM (updated): • Reasons of Delay: • Change Orders in PRPHA pending for Approval: • latest Certification: Last certification rendered for payment is certification # 49 (February 2014) • Extraordinary situations with Relocation: N/A • Situations with Governmental Agencies: N/A • Other situations that are affecting the project: N/A | Active
5011 | San Juan | Jardines del Paraíso | José Negrón | Cost Control Company, Inc. | BMA | Andrés Hernández & Asoc. |  | 112 | 0 | 0 | 0 | 0 |  |  | 0 | #DIV/0! | 41759 | #DIV/0! |  | -1 | -1 | [7 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  |  |  | Proyecto en Re-Subasta. Subasta declarada Desierta. No se ha Comenzado el proyecto. | Stopped
3049 | Lajas | Las Américas | Noefebdo Ramírez | Inn Capital Housing Division Joint Venture | none | URS Caribe, LLP | none | 80 | 16 | 0 | 16 | 0 |  |  | 0 | #DIV/0! | 41759 | #DIV/0! |  | -1 | -1 | [7 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  |  |  | Design completed. Pending for will be assigned construction funds by PHA. | Stopped
3100 | Aguadilla | Agustín Stahl I | Arturo Acevedo | American Management Corp. | CCC-JV | René Acosta Arquitectos | Karimar Construction, Inc. | 180 | 180 | 0 | 180 | 0 | 915 | 192 | 1107 | 20.98% | 1100 | 100% | 2010-03-23 | 2012-09-22 | 2013-04-02 | 2013-03-27 |  |  | ARRA/CFP |  | 13875675 | 597322.95 | 14472997.95 | 4.305% | 13367679 | 0 | 13367679 | 92.36% | 6.1111 |  |  | Project started on march 23, 2010. substantial completion was awarded on March 27 2013 Last certification rendered for payment is certification # 38, for the period of March 1 to 30, 2013. | Substantial Completion
5201 | Cayey | Alturas de Montellano | Jorge Mercado | Municipio | LMC | Arq. José Luzunaris | RC Group S.E. | 80 | 50 | 0 | 50 | 0 | 730 | 846 | 1576 | 115.9% | 1970 | 100% | 2001-09-04 | 2003-09-03 | 2005-12-27 | 2007-01-26 |  |  | CFP | 2001-11-21 | 4790000 | 2327268.37 | 7117268.37 | 48.59% | 7036300.8 | 0 | 7036300.8 | 98.86% | 24.625 |  |  | Nunca se aprobaron las ordenes de cambio #17 y #18 porque el contratista no sometió los documentos solicitados por el Área de Adquisición y Contratación. Nunca se le otorgó el "Final Acceptance". El caso esta siendo atendido en la División Legal de la Admnisitración de Vivienda Pública. Queda un balance de $80,967.57 en espera se resuelva la controversia. | Substantial Completion
3089 | Juana Díaz | Villa del Parque (Take over agreement) | Rubén Cotto | J.A. Machuca | MD | GMG Eng. Consultants | (USF & G) | 100 | 100 | 0 | 100 | 0 | 547 | 746 | 1293 | 136.4% | 552 | 100% | 2000-12-18 | 2002-06-17 | 2004-07-02 | 2002-06-23 |  |  | CFP | 2000-09-30 | 3105100 | 239005.38 | 3344105.38 | 7.697% | 3171314 | 0 | 3171314 | 94.83% | 5.52 |  |  | El "final acceptance" le fue entregado a la Administracion del proyecto , JA Machuca, no obstante los mismos no lo han firmado ya que la Aseguradora no ha sometido aun los documentos de garantía de techo. Se le indicó vervalmente al Ing. Carrasquillo, representante de la Aseguradora. | Substantial Completion
3093 | Juncos | Narciso Varona Fase II | José González | MJ Consulting | AVP | DG3A Design Group, PSC | F & R Construction Group, Inc. | 172 | 172 | 0 | 172 | 0 | 1220 | 235 | 1455 | 19.26% | 1385 | 100% | 2010-02-24 | 2013-06-27 | 2014-02-17 | 2013-12-10 |  |  | Arra/Mixed |  | 13189000 | 822958.39 | 14011958.39 | 6.24% | 13762592.18 | 0 | 13762592.18 | 98.22% | 8.0523 |  |  | Project is almost completed. | Substantial Completion
5053 | Mayagüez | Ramírez de Arellano | Pedro Vega | JA Machuca | LMC | GMG Engineering | Comas & Comas Contractors, Corp | 80 | 80 | 0 | 80 | 0 | 720 | 661 | 1381 | 91.81% | 1375 | 100% | 2009-07-13 | 2011-07-02 | 2013-04-23 | 2013-04-18 |  |  | ARRA/CFP |  | 4040000 | 2215708.24 | 6255708.24 | 54.84% | 6011262.53 | 0 | 6011262.53 | 96.09% | 17.1875 |  |  | Final Completion and Close Out era specting for: 1) PRPHA approval CO#9 and CO#10; 2)Contractor correction of payroll defiecience | Substantial Completion
3058 | Moca | José N. Gándara | Noefebdo Ramírez | NFC | CMS | Ray Engineers PSC | Moss Construction | 74 | 74 | 0 | 74 | 0 | 896 | 73 | 969 | 8.147% | 940 | 100% | 1999-11-08 | 2002-04-21 | 2002-07-03 | 2002-06-05 |  |  | CFP-02 | 2000-01-13 | 4671000 | 238289 | 4909289 | 5.101% | 4805897.22 | 0 | 4805897.22 | 97.89% | 12.7027 |  |  | The close out was not completed because the Contractor not submit to PRPHA the final documents required by the Construction and Management Bureau and the Legal Division of the PRPHA. The solution of this case was referred to Legal Division of the PRPHA. | Substantial Completion
5088 | Ponce | Lirios del Sur | Arturo Acevedo | MJ Consulting | CMS | CSA | Caribe General Constructors | 400 | 400 | 0 | 400 | 0 | 791 | 487 | 1278 | 61.57% | 1267 | 100% | 2009-03-02 | 2011-05-01 | 2012-08-30 | 2012-08-20 |  |  | CFP |  | 16598000 | 2352431.7 | 18950431.7 | 14.17% | 17140589.22 | 0 | 17140589.22 | 90.45% | 3.1675 |  |  | Project started in march 2009, The contrator finished the instalation of the luminaries on the fence of the west side of the project. Last certification rendered for payment is certification # 35, which is the 50% of retainage. | Substantial Completion
5056 | Guaynabo | Loa Alamos | José González | Municipio de Guaynabo | Klassik | Hernández-Bauzá | Homeca Recycling | 376 | 376 | 0 | 376 | 0 | 549 | 0 | 549 | 0% | 547 | 100% | 2012-09-17 | 2014-03-19 | 2014-03-19 | 2014-03-18 |  |  | CFP |  | 2339000 | -40565.21 | 2298434.79 | -1.734% | 2149223.01 | 0 | 2149223.01 | 93.51% | 1.4548 |  |  | Project is almost completed. | Substantial Completion
5166 | San Juan | Brisas de Cupey | José M. Paris | SP Management Corp. | CCC-JV | Fracinetti Arquitectos | Pitirre Copnstruction | 184 | 184 | 0 | 184 | 0 | 993 | 127 | 1120 | 12.79% | 1251 | 100% | 2010-02-26 | 2012-11-14 | 2013-03-21 | 2013-07-31 |  |  | ARRA/CFP |  | 15326960 | 1013140.06 | 16340100.06 | 6.61% | 16340100.06 | 0 | 16340100.06 | 100% | 6.7989 |  |  | The Program Manager is preparing the change order # 10, this CO has time extension by wheater condition and delay in the delivery of the building # 12 to the Contractor. The six building completed and we are waiting for legal RW documents, | Substantial Completion
3070 | Trujillo Alto | Pedro Regalado Díaz | José González | Inn Capital Housing Division Joint Venture | MD | Ray Engineers PSC | José L. Colón | 10 | 10 | 0 | 10 | 0 | 273 | 226 | 499 | 82.78% | 498 | 100% | 2008-04-14 | 2009-01-11 | 2009-08-25 | 2009-08-25 |  |  | CFP |  | 1991000 | 435116 | 2426116 | 21.85% | 2304810.1 | 0 | 2304810.1 | 95% | 49.8 |  |  | ♦ Repair of Units and Administration Building - The Management Agent has prepared a report about the scope of work and cost to repair units that will be delivered to the residents. Extraordinary Maintenance Office (PHAPR) is working with this item. ♦ Existing post removal - This work will be performed once the AEE connects the project and the Cable TV Company removes its wiring. ♦ Claim of the Contractor Jose Luis Colon - it was assigned to PGES to work with it. | Substantial Completion
3030 | Adjuntas | Villa Valle Verde | Pedro Vega | J.A. Machuca | URS | Jorge L. Roberts, PSC | Venegas Construction | 150 | 150 | 0 | 150 | 0 | 913 | 144 | 1057 | 15.77% | 1743 | 100% | 2001-01-15 | 2003-07-16 | 2003-12-07 | 2005-10-24 | 2007-02-06 |  |  |  | 11829000 | 337235 | 12166235 | 2.851% | 12103923 | 0 | 12103923 | 99.49% | 11.62 | 100% | 0 | These Close out is in process by PGES. | Final Acceptance
3034 | Aguada | Francisco Egipciaco | Noefebdo Ramírez | NFC | CMS | Arq. José Luzunaris | NLL Construction | 100 | 100 | 0 | 100 | 0 | 887 | 0 | 887 | 0% | 819 | 100% | 2000-03-23 | 2002-08-26 | 2002-08-26 | 2002-06-20 | 2002-10-04 |  |  |  | 8107810 | 207539 | 8315349 | 2.56% | 8315349 | 0 | 8315349 | 100% | 8.19 | 100% | 0 | Project Closed | Final Acceptance
5252 | Aguada | Los Robles | Noefebdo Ramírez | NFC | CMS | Joglar & Architects | 422 Corporation | 62 | 62 | 0 | 62 | 0 | 669 | 0 | 669 | 0% | 692 | 100% | 2001-01-18 | 2002-11-17 | 2002-11-17 | 2002-12-11 | 2003-10-02 |  |  |  | 2640000 | -11465 | 2628535 | -0.4343% | 2628535 | 0 | 2628535 | 100% | 11.1613 | 100% | 0 | Project Closed | Final Acceptance
5158 | Aguadilla | La Montaña | Frank Nieves | American Management | URS | Unipro | Caribe Tecno Habitat | 220 | 220 | 0 | 220 | 0 | 895 | 458 | 1353 | 51.17% | 1341 | 100% | 2003-07-28 | 2006-01-07 | 2007-04-10 | 2007-03-30 | 2007-03-30 |  | CFP |  | 16148000 | 1232941.34 | 17380941.34 | 7.635% | 16890921 | 0 | 16890921 | 97.18% | 6.0955 | 100% | 0 | Project Closed | Final Acceptance
3035 | Aguas Buenas | Vista Alegre | Rubén Cotto | MJ Consulting | URS Caribe | Carlos E. Betancourt | Constructores Gilmar | 74 | 74 | 0 | 74 | 0 | 912 | 752 | 1664 | 82.46% | 1645 | 100% | 2005-06-06 | 2007-12-04 | 2009-12-25 | 2009-12-07 | 2010-09-10 |  | Tax Credit 908-2008 |  | 6690000 | 2657915 | 9347915 | 39.73% | 8143277.42 | 0 | 8143277.42 | 87.11% | 22.2297 | 100% | 0 | Project Closed | Final Acceptance
3082 | Arecibo | Ramón Marín Solá (Fase II) | Arturo Acevedo | MAS Corporation | CMS | Andrés Hernández | Nogama Construction | 96 | 96 | 0 | 96 | 0 | 612 | 44 | 656 | 7.19% | 626 | 100% | 2000-05-15 | 2002-01-16 | 2002-03-01 | 2002-01-31 | 2002-03-15 |  |  |  | 7837000 | 0 | 7837000 | 0% | 7837000 | 0 | 7837000 | 100% | 6.5208 | 100% | 0 | Project Closed | Final Acceptance
3097 | Arecibo | Trina Padilla de Sanz | Frank Nieves | Cost Control Company, Inc. | ISS Corp | Ray Engineers PSC | Nogama Construction | 240 | 240 | 0 | 240 | 0 | 1278 | 97 | 1375 | 7.59% | 1464 | 100% | 2006-01-09 | 2009-07-09 | 2009-10-14 | 2010-01-12 | 2010-08-16 |  | Tax Credit |  | 23814529 | 1556413.89 | 25370942.89 | 6.536% | 25198434.68 | 0 | 25198434.68 | 99.32% | 6.1 | 100% | 0 | Project Closed | Final Acceptance
5127 | Arecibo | La Meseta | Pedro Vega | Cost Control Company, Inc. | URS Caribe | Enrique Ruiz & Asoc. | Venegas Construction | 300 | 300 | 0 | 300 | 0 | 1098 | 871 | 1969 | 79.33% | 1947 | 100% | 2005-05-31 | 2008-06-01 | 2010-10-20 | 2010-09-29 | 2011-01-24 |  | Tax Credit |  | 24161000 | 1903823.57 | 26064823.57 | 7.88% | 26064823.57 | 0 | 26064823.57 | 100% | 6.49 | 100% | 0 | Project Closed. | Final Acceptance
3099 | Arecibo | Antonio Márquez Arbona | Frank Nieves | American Management | Klassik Builders | Enrique Ruiz & Asoc. | Karimar Construction, Inc. | 104 | 104 | 0 | 104 | 0 | 730 | 183 | 913 | 25.07% | 912 | 100% | 2010-03-25 | 2012-03-23 | 2012-09-22 | 2012-09-22 | 2013-04-01 |  | ARRA/CFP |  | 9085636 | 263361.39 | 9348997.39 | 2.899% | 9223663.18 | 0 | 9223663.18 | 98.66% | 8.7692 | 100% | 0 | In Closing Process. | Final Acceptance
3021 | Arroyo | Isidro Cora | Rubén Cotto | MJ Consulting | MD | GMG Eng. Consultants | Venegas Construction | 150 | 150 | 0 | 150 | 0 | 1095 | 302 | 1397 | 27.58% | 1396 | 100% | 1999-09-27 | 2002-09-25 | 2003-07-24 | 2003-07-24 | 2004-09-30 |  |  |  | 10247000 | 437000 | 10684000 | 4.265% | 10654500 | 0 | 10654500 | 99.72% | 9.3067 | 100% | 0 | The close out documents are under correction process by the Program Manager and General Contractor. | Final Acceptance
3036 | Barceloneta | Antonio Dávila Freytes | José Negrón | MAS Corporation | LMC | Andrés Hernández & Asoc. | Caribe Tecno | 100 | 100 | 0 | 100 | 0 | 904 | 413 | 1317 | 45.69% | 1316 | 100% | 1999-10-15 | 2002-04-05 | 2003-05-23 | 2003-05-23 | 2003-06-30 |  |  |  | 6970000 | 1305876.67 | 8275876.67 | 18.74% | 8275877 | 0 | 8275877 | 100% | 13.16 | 100% | 0 | Project Closed | Final Acceptance
3037 | Barranquitas | Villa Universitaria | Jorge Mercado | MJ Consulting | AVP | GMG Eng. Consultants | Royal & Sun Alliance | 100 | 100 | 0 | 100 | 0 | 540 | 913 | 1453 | 169.1% | 1678 | 100% | 1997-11-25 | 1999-05-18 | 2001-11-16 | 2002-06-30 | 2002-11-12 |  |  |  | 5299000 | 804839 | 6103839 | 15.19% | 6103839 | 0 | 6103839 | 100% | 16.78 | 100% | 0 | Project Closed | Final Acceptance
5093 | Bayamón | Brisas de Bayamón | Arturo Acevedo | Cost Control Company, Inc. | URS Caribe | Edison Avilés Deliz | Omega Engineering | 300 | 300 | 0 | 300 | 0 | 1400 | 1372 | 2772 | 98% | 2518 | 100% | 2002-01-09 | 2005-11-08 | 2009-08-11 | 2008-12-01 | 2010-03-22 |  | Tax Credit |  | 23965851 | 5030471 | 28996322 | 20.99% | 27007484 | 0 | 27007484 | 93.14% | 8.3933 | 100% | 0 | Project Closed | Final Acceptance
5151 | Bayamón | Sierra Linda | Arturo Acevedo | Martinal Property | URS | Gautier & De Torres | JR Builders | 200 | 200 | 0 | 200 | 0 | 1015 | 1071 | 2086 | 105.5% | 2136 | 100% | 2002-04-15 | 2005-01-23 | 2007-12-30 | 2008-02-19 | 2008-08-08 |  | CFP-02 |  | 13395440 | 1036113 | 14431553 | 7.735% | 14344606 | 0 | 14344606 | 99.4% | 10.68 | 100% | 0 | Project Closed | Final Acceptance
5096 | Bayamón | La Alhambra | Luis Rodríguez | Cost Control Company, Inc. | LMC | Jorge del Río Arquitectos | Del Valle Group | 96 | 96 | 0 | 96 | 0 | 730 | 236 | 966 | 32.33% | 793 | 100% | 2009-07-28 | 2011-07-27 | 2012-03-19 | 2011-09-29 | 2012-05-17 |  | ARRA-CFP |  | 9555000 | 752914.59 | 10307914.59 | 7.88% | 10307914.59 | 0 | 10307914.59 | 100% | 8.2604 | 100% | 0 | Project Closed | Final Acceptance
5094 | Bayamón | Las Gardenias | Jorge Mercado | Housing Promoters | AVP/Prann | Gautier & Benítez | Del Valle Group | 164 | 164 | 0 | 164 | 0 | 671 | 302 | 973 | 45.01% | 1033 | 100% | 1997-05-29 | 1999-03-30 | 2000-01-26 | 2000-03-27 | 2000-06-08 |  |  |  | 7117000 | 152286.5 | 7269286.5 | 2.14% | 7234564.4 | 0 | 7234564.4 | 99.52% | 6.2988 | 100% | 0 | Project Closed | Final Acceptance
5138 | Caguas | Villa del Rey (With Take Over Agreement) | Fco. Palacios | MJ Consulting | AVP / Vivonis & Villegas | Guillermety, Ortiz & Asoc. | American Intl. | 100 | 100 | 0 | 100 | 0 | 620 | 165 | 785 | 26.61% | 903 | 100% | 2000-08-04 | 2002-04-15 | 2002-09-27 | 2003-01-24 | 2003-01-24 |  |  |  | 2110081 | 192030 | 2302111 | 9.101% | 2302111 | 0 | 2302111 | 100% | 9.03 | 100% | 0 | Project Closed | Final Acceptance
5066 | Caguas | Turabo Heights | Luis Rodríguez | MJ Consulting | LMC | Andrés Hernández & Asoc. | Del Valle Group | 254 | 254 | 0 | 254 | 0 | 1300 | 471 | 1771 | 36.23% | 1641 | 100% | 2006-01-16 | 2009-08-07 | 2010-11-21 | 2010-07-15 | 2010-09-30 |  | Tax Credit |  | 25534940 | 2776195 | 28311135 | 10.87% | 28311135.04 | 0 | 28311135.04 | 100% | 6.4606 | 100% | 0 | Project Closed | Final Acceptance
3038 | Camuy | M. Román Adames | Arturo Acevedo | NFC | CMS | Gutierez & Gutierrez | Pintores Metropolitanos | 64 | 64 | 0 | 64 | 0 | 396 | 491 | 887 | 124% | 1101 | 100% | 1997-05-19 | 1998-06-18 | 1999-10-22 | 2000-05-24 | 2001-03-19 |  |  |  | 3600000 | 403566 | 4003566 | 11.21% | 4003566 | 0 | 4003566 | 100% | 17.2031 | 100% | 0 | Project Closed | Final Acceptance
3053 | Canóvanas | Jesús T. Piñero | Katherine Vázquez | Peregrine Group Inc. | Klassik Builders | Ray Engineers, PSC | LPC&D | 124 | 124 | 0 | 124 | 0 | 913 | 237 | 1150 | 25.96% | 1149 | 100% | 2009-07-15 | 2012-01-13 | 2012-09-06 | 2012-09-06 | 2013-06-30 |  | ARRA/CFP |  | 16575250 | 2355453 | 18930703 | 14.21% | 18827830.65 | 0 | 18827830.65 | 99.46% | 9.2661 | 100% | 0 | The following items are pending: comments from payroll non-compliance issues, to submit certification # 38. | Final Acceptance
5082 | Carolina | Alturas de Country Club | José González | PROMMA | URS | Jorge del Rio | North Construction | 72 | 72 | 0 | 72 | 0 | 548 | 373 | 921 | 68.07% | 893 | 100% | 2004-09-27 | 2006-03-28 | 2007-04-05 | 2007-03-09 | 2009-04-24 |  | CFP |  | 5977756.15 | 1066756.51 | 7044512.66 | 17.85% | 7044512.67 | 0 | 7044512.67 | 100% | 12.4028 | 100% | 0 | Project Closed | Final Acceptance
5057 | Carolina | Los Mirtos | José González | Cost Control | CCC-JV | Hernández - Bauzá | Del Valle group | 144 | 144 | 0 | 144 | 0 | 545 | 121 | 666 | 22.2% | 690 | 100% | 2010-11-08 | 2012-05-05 | 2012-09-03 | 2012-09-28 | 2013-07-17 |  | Tax Credit |  | 14841000 | 272983 | 15113983 | 1.839% | 14923649 | 0 | 14923649 | 98.74% | 4.7917 | 100% | 0 | Project Closed | Final Acceptance
5076 | Carolina | Catañito Gardens | Luis Rodríguez | Inn Capital Housing Division Joint Venture | MD | URS Caribe | RBC Construction | 124 | 124 | 0 | 124 | 0 | 730 | 937 | 1667 | 128.4% | 0 | 100% | 2006-02-08 | 2008-02-07 | 2010-09-01 | 2006-02-08 | 2011-03-28 |  | Tax Credit 908-2008 |  | 13938100 | 819027.62 | 14757127.62 | 5.876% | 14757127.62 | 0 | 14757127.62 | 100% | 0 | 100% | 0 | Project Closed | Final Acceptance
5102 | Carolina | El Coral | José A. González | Cost Control Company, Inc. | URS Caribe | Francinetti Arquitectos | Orion Contractors | 100 | 100 | 0 | 100 | 0 | 913 | 1268 | 2181 | 138.9% | 2180 | 100% | 2006-01-09 | 2008-07-09 | 2011-12-29 | 2011-12-29 | 2012-06-29 |  | Tax Credit |  | 9718830 | 1196730.19 | 10915560.19 | 12.31% | 10915560.19 | 0 | 10915560.19 | 100% | 21.8 | 100% | 0 | Project Closed | Final Acceptance
5101 | Carolina | La Esmeralda | Luis Rodríguez | Inn Capital Housing Division Joint Venture | BMA | Carlos E. Betancourt | Construction Zone Corp. | 84 | 84 | 0 | 84 | 0 | 549 | 65 | 614 | 11.84% | 612 | 100% | 2008-12-22 | 2010-06-23 | 2010-08-27 | 2010-08-26 | 2010-12-10 |  | Tax Credit |  | 4462898 | 32305.97 | 4495203.97 | 0.7239% | 4495203.77 | 0 | 4495203.77 | 100% | 7.2857 | 100% | 0 | Project Closed | Final Acceptance
5075 | Carolina | Lagos de Blasina | José A. González | Cost Control Company, Inc. | CMS | Guillermety, Ortiz & Asoc. (DG3A Design Group, PSC is actually supervising the works) | Mejia Construction | 240 | 240 | 0 | 240 | 0 | 800 | 289 | 1089 | 36.12% | 1077 | 100% | 2009-06-08 | 2011-08-16 | 2012-05-31 | 2012-05-20 | 2012-09-20 |  | Tax Credit |  | 15411000 | 809595.16 | 16220595.16 | 5.253% | 16220595.16 | 0 | 16220595.16 | 100% | 4.4875 | 100% | 0 | Project Closed | Final Acceptance
5212 | Carolina | Roberto Clemente | Luz Acevedo | SEG | CMS | Jorge del Río | North Connstruction | 126 | 126 | 0 | 126 | 0 | 730 | 242 | 972 | 33.15% | 1038 | 100% | 2004-08-09 | 2006-08-08 | 2007-04-07 | 2007-06-13 | 2008-02-22 |  |  |  | 11135000 | 586931 | 11721931 | 5.271% | 11610417 | 0 | 11610417 | 99.05% | 8.2381 | 100% | 0 | Project Closed | Final Acceptance
3102 | Cataño | Juana Matos I (Fase I) | Luz Acevedo | A & M | AVP / Erwin Rodriguez | Roca & Associates | Quintero Const. | 212 | 212 | 0 | 212 | 0 | 892 | 744 | 1636 | 83.41% | 1628 | 100% | 1997-05-29 | 1999-11-06 | 2001-11-19 | 2001-11-12 | 2002-07-22 |  |  |  | 11640000 | 424857 | 12064857 | 3.65% | 11679790.2 | 0 | 11679790.2 | 96.81% | 7.6792 | 100% | 0 | Project Closed | Final Acceptance
3102 | Cataño | Juana Matos I (Fase II) | Pedro Vega | A & M | BMA | Roca & Associates | Rodríguez & del Valle | 188 | 188 | 0 | 188 | 0 | 1150 | 141 | 1291 | 12.26% | 1179 | 100% | 2002-09-30 | 2005-11-22 | 2006-04-12 | 2005-12-22 | 2006-01-12 |  |  |  | 14243000 | 831198 | 15074198 | 5.836% | 15074198 | 0 | 15074198 | 100% | 6.2713 | 100% | 0 | Project Closed | Final Acceptance
5037 | Cataño | Jardines de Cataño | Pedro Vega | Martinal Property | CMS | Interplan | Francisco Levy Hijo Inc. | 180 | 180 | 0 | 180 | 0 | 810 | 369 | 1179 | 45.56% | 1175 | 100% | 2004-03-22 | 2006-06-09 | 2007-06-13 | 2007-06-10 | 2007-06-14 |  | CFP |  | 14181600 | 1145235.46 | 15326835.46 | 8.076% | 15326835.44 | 0 | 15326835.44 | 100% | 6.5278 | 100% | 0 | Project Closed | Final Acceptance
3083 | Cayey | Luis Muñoz Morales | Luz Acevedo | MJ Consulting | AVP | Istra Hernández | I Melendez | 280 | 280 | 0 | 280 | 0 | 913 | 416 | 1329 | 45.56% | 1342 | 100% | 1997-08-01 | 2000-01-30 | 2001-03-21 | 2001-04-04 | 2001-09-19 |  |  |  | 12895800 | 452279 | 13348079 | 3.507% | 13348079 | 0 | 13348079 | 100% | 4.7929 | 100% | 0 | Project Close | Final Acceptance
5127 | Cayey | Jardines de Montellanos | Rubén Cotto | Cost Control | CCC-JV | Hernández - Bauzá | Constructora I. Meléndez | 130 | 130 | 0 | 130 | 0 | 836 | 307 | 1143 | 36.72% | 1142 | 100% | 2009-09-30 | 2012-01-13 | 2012-11-15 | 2012-11-15 |  |  | Tax Credit |  | 17226575.94 | 2771225.7 | 19997801.64 | 16.09% | 19987858.29 | 0 | 19987858.29 | 99.95% | 8.7846 | 100% | 0 | Project Closed | Final Acceptance
5157 | Cayey | Brisas de Cayey | Rubén Cotto | MJ Consulting | MD | Ray Engineers PSC | Three O. Construction | 210 | 210 | 0 | 210 | 0 | 1491 | 1200 | 2691 | 80.48% | 1887 | 100% | 2005-01-12 | 2009-02-10 | 2012-05-25 | 2010-03-14 | 2010-04-06 |  | Tax Credit |  | 24696653 | 5611698 | 30308351 | 22.72% | 30308351 | 0 | 30308351 | 100% | 8.9857 | 100% | 0 | Project Closed | Final Acceptance
3040 | Ciales | Fernando Sierra Berdecía | José Negrón | MAS Corporation | LMC | Luis Flores & Asociados | Constructores Gilmar | 100 | 100 | 0 | 100 | 0 | 780 | 165 | 945 | 21.15% | 983 | 100% | 2001-08-21 | 2003-10-09 | 2004-03-22 | 2004-04-30 | 2006-05-16 |  |  |  | 9285527 | 414901 | 9700428 | 4.468% | 9700428 | 0 | 9700428 | 100% | 9.83 | 100% | 0 | Project Closed | Final Acceptance
3041 | Cidra | Práxedes Santiago | Rubén Cotto | MJ Consulting | URS | Carlos E. Betancourt | DGM Engineering | 124 | 124 | 0 | 124 | 0 | 912 | 901 | 1813 | 98.79% | 2235 | 100% | 2005-04-28 | 2007-10-26 | 2010-04-14 | 2011-06-11 | 2012-03-09 |  | Tax Credit |  | 11616773 | 3604885 | 15221658 | 31.03% | 14100168 | 0 | 14100168 | 92.63% | 18.0242 | 100% | 0 | Project Closed | Final Acceptance
3043 | Dorado | El Dorado | Frank Nieves | Cost Control Company, Inc. | BMA | Guillermety, Ortiz & Asoc. | Torres & Colón, Inc | 37 | 37 | 0 | 37 | 0 | 430 | 180 | 610 | 41.86% | 666 | 100% | 2007-06-04 | 2008-08-06 | 2009-02-02 | 2009-03-31 | 2009-04-14 |  | Tax Credit |  | 3991977 | 753900 | 4745877 | 18.89% | 4745877 | 0 | 4745877 | 100% | 18 | 100% | 0 | Project Closed | Final Acceptance
3095 | Fajardo | Pedro Rosario Nieves | José M. Paris Escalera | Inn Capital Housing Division Joint Venture | CMS | Carlos E. Betancourt | Nogama Construction | 168 | 168 | 0 | 168 | 0 | 915 | 27.5 | 942.5 | 3.005% | 904 | 100% | 2008-12-22 | 2011-06-24 | 2011-07-21 12:00 | 2011-06-14 | 2011-09-06 |  | Tax Credit |  | 16474000 | -148386.07 | 16325613.93 | -0.9007% | 16325613.93 | 0 | 16325613.93 | 100% | 5.381 | 100% | 0 | Project Closed | Final Acceptance
5021 | Fajardo | Puerto Real | Germán Acevedo | A & M | URS | René Vélez Marichal | Quality Const. | 100 | 100 | 0 | 100 | 0 | 945 | 282 | 1227 | 29.84% | 1124 | 100% | 2001-01-22 | 2003-08-24 | 2004-06-01 | 2004-02-20 | 2004-04-20 |  |  |  | 8220000 | 910990 | 9130990 | 11.08% | 9130990 | 0 | 9130990 | 100% | 11.24 | 100% | 0 | Project Closed | Final Acceptance
5204 | Fajardo | Valle Puerto Real | Germán Acevedo | A & M | URS | Enrique Ruiz & Assoc. | Quality Const. | 75 | 75 | 0 | 75 | 0 | 945 | 181 | 1126 | 19.15% | 1129 | 100% | 2001-01-02 | 2003-08-04 | 2004-02-01 | 2004-02-05 | 2004-05-14 |  |  |  | 6316000 | 725553 | 7041553 | 11.49% | 7041553 | 0 | 7041553 | 100% | 15.0533 | 100% | 0 | Project Closed | Final Acceptance
5176 | Fajardo | Santiago Veve Calzada | Robert H. Cole | A & M | BMA | Ramón W. Costacamps | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 730 | 214 | 944 | 29.32% | 906 | 100% | 2004-06-21 | 2006-06-20 | 2007-01-20 | 2006-12-14 | 2007-01-18 |  |  |  | 8559000 | 558385.32 | 9117385.32 | 6.524% | 9117385.32 | 0 | 9117385.32 | 100% | 9.06 | 100% | 0 | Project Closed | Final Acceptance
5183 | Guánica | Jardines de Guánica | Noefebdo Ramírez | JA Machuca | CCC-JV | Donato Design Development | RAMA Construction | 70 | 70 | 0 | 70 | 0 | 732 | 89 | 821 | 12.16% | 794 | 100% | 2009-11-23 | 2011-11-24 | 2012-02-21 | 2012-01-26 | 2012-01-31 |  | ARRA/CFP |  | 5499000 | 487497.62 | 5986497.62 | 8.865% | 5986498 | 0 | 5986498 | 100% | 11.3429 | 100% | 0 | Project Closed | Final Acceptance
3084 | Guánica | Luis Muñoz Rivera | Noefebdo Ramírez | Cost Control Company, Inc. | CCC-JV | Behar & Ybarra Associates, PSC | F & R Construction Group, Inc. | 124 | 124 | 0 | 124 | 0 | 485 | 423 | 908 | 87.22% | 970 | 100% | 2009-12-14 | 2011-04-12 | 2012-06-08 | 2012-08-10 | 2013-04-18 |  | Tax Credit |  | 9009000 | 589263.71 | 9598263.71 | 6.541% | 9590758.22 | 0 | 9590758.22 | 99.92% | 7.8226 | 100% | 0 | Project Closed | Final Acceptance
3085 | Guayama | Luis Palés Matos | Rubén Cotto | MJ Consulting | MD (Grupo C) | Guillermety, Ortiz & Asoc. | Héctor M. Valera Inc. | 298 | 298 | 0 | 298 | 0 | 1130 | 0 | 1130 | 0% | 1375 | 100% | 2002-03-25 | 2005-04-27 | 2005-04-27 | 2005-12-29 | 2006-01-03 |  |  |  | 22466000 | 0 | 22466000 | 0% | 22466000 | 0 | 22466000 | 100% | 4.6141 | 100% | 0 | Project Closed | Final Acceptance
5048 | Guayama | San Antonio Carioca | Jorge Mercado | MJ Consulting | MD (Grupo C) | DDHK | Constructora I. Melendez | 200 | 200 | 0 | 200 | 0 | 900 | 568 | 1468 | 63.11% | 1537 | 100% | 2004-03-15 | 2006-08-31 | 2008-03-21 | 2008-05-30 | 2008-07-30 |  | Tax Credit |  | 18456662 | 1765148 | 20221810 | 9.564% | 20221810 | 0 | 20221810 | 100% | 7.685 | 100% | 0 | Project Closed | Final Acceptance
5131 | Humacao | Jardines de Oriente | José A. González | Cost Control | CCC-JV | GMG Engineering Conslutants PSC | Ossam Construction | 88 | 88 | 0 | 88 | 0 | 365 | 242 | 607 | 66.3% | 937 | 100% | 2010-05-31 | 2011-05-30 | 2012-01-27 | 2012-12-23 | 2012-07-20 |  | Tax Credit |  | 5939925 | 394882.55 | 6334807.55 | 6.648% | 6334807.55 | 0 | 6334807.55 | 100% | 10.6477 | 100% | 0 | Project Closed | Final Acceptance
5020 | Humacao | Pedro J. Palou | Fco. Palacios | MJ Consulting | URS | R & del Valle | R & del Valle | 150 | 150 | 0 | 150 | 0 | 1095 | 180 | 1275 | 16.44% | 1145 | 100% | 1999-09-27 | 2002-09-25 | 2003-03-24 | 2002-11-15 | 2002-12-20 |  |  |  | 10968000 | 86049 | 11054049 | 0.7845% | 11054049 | 0 | 11054049 | 100% | 7.6333 | 100% | 0 | Project closed. | Final Acceptance
3094 | Humacao | Padre Rivera (Fase I) | Germán Acevedo | MJ Consulting | BMA | Yañez, Mayol & Asoc. | J R Builders | 128 | 128 | 0 | 128 | 0 | 840 | 731 | 1571 | 87.02% | 1548 | 100% | 1997-10-20 | 2000-02-06 | 2002-02-06 | 2002-01-15 | 2002-02-01 |  |  |  | 6625000 | 386337.2 | 7011337.2 | 5.832% | 7011337 | 0 | 7011337 | 100% | 12.0938 | 100% | 0 | Project Closed | Final Acceptance
3094 | Humacao | Padre Rivera (Fase II) | Jorge Mercado | MJ Consulting | BMA | Yañez & Mayol | Jafer Construction | 132 | 132 | 0 | 132 | 0 | 790 | 299 | 1089 | 37.85% | 861 | 100% | 2004-11-10 | 2007-01-08 | 2007-11-03 | 2007-03-21 | 2008-03-12 |  |  |  | 10199820 | 1471265 | 11671085 | 14.42% | 11237717 | 0 | 11237717 | 96.29% | 6.5227 | 100% | 0 | Project Closed | Final Acceptance
3048 | Jayuya | La Montaña | Pedro Vega | MAS Corporation | URS | OPQ-Pablo Quiñonez | Orama Const. | 100 | 100 | 0 | 100 | 0 | 780 | 128 | 908 | 16.41% | 1026 | 100% | 2000-10-23 | 2002-12-11 | 2003-04-18 | 2003-08-15 | 2004-04-26 |  |  |  | 8790000 | 208826 | 8998826 | 2.376% | 8998826 | 0 | 8998826 | 100% | 10.26 | 100% | 0 | Project Closed | Final Acceptance
5064 | Juncos | Colinas de Magnolia | Iván Blanco | MJ Consulting | BMA | Edison Avilés Deliz | Quality Construction | 148 | 148 | 0 | 148 | 0 | 840 | 614 | 1454 | 73.1% | 1201 | 100% | 2004-11-08 | 2007-02-25 | 2008-10-31 | 2008-02-22 | 2008-04-04 |  | CFP |  | 13860000 | 854562 | 14714562 | 6.166% | 14438155 | 0 | 14438155 | 98.12% | 8.1149 | 100% | 0 | Project Closed | Final Acceptance
3093 | Juncos | Narciso Varona I | Rubén Cotto | MJ Consulting | ISS | DG3A | Torres & Colón, Inc | 88 | 88 | 0 | 88 | 0 | 600 | 199 | 799 | 33.17% | 798 | 100% | 2009-05-29 | 2011-01-18 | 2011-08-05 | 2011-08-05 |  |  | ARRA/CFP |  | 9879114 | 196304 | 10075418 | 1.987% | 10058405.83 | 0 | 10058405.83 | 99.83% | 9.0682 | 100% | 0 | Project Closed | Final Acceptance
5226 | Las Marías | Jardines de las Marías | Arturo Acevedo | NFC | CMS | José L. Irizarry & Assoc. | Lebrón & Assoc. | 55 | 55 | 0 | 55 | 0 | 730 | 32 | 762 | 4.384% | 766 | 100% | 2001-02-27 | 2003-02-26 | 2003-03-30 | 2003-04-04 | 2003-10-03 |  |  |  | 4156000 | 71269 | 4227269 | 1.715% | 4227269 | 0 | 4227269 | 100% | 13.9273 | 100% | 0 | Project Closed | Final Acceptance
5090 | Las Piedras | Jardines de Judely | Iván Blanco | MJ Consulting | URS | René Acosta Ingenieros | Gilmar Roofing & Painting | 32 | 32 | 0 | 32 | 0 | 365 | 118 | 483 | 32.33% | 555 | 100% | 2005-04-04 | 2006-04-03 | 2006-07-30 | 2006-10-11 | 2006-11-02 |  | Tax Credit |  | 3481720 | 109596.22 | 3591316.22 | 3.148% | 3573356 | 0 | 3573356 | 99.5% | 17.3438 | 100% | 0 | Project Closed | Final Acceptance
5132 | Loíza | Yuquiyú | Luz Acevedo | A & M | BMA | Roca, González Villamil | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 945 | 60 | 1005 | 6.349% | 754 | 100% | 2001-01-22 | 2003-08-24 | 2003-10-23 | 2003-02-15 | 2003-03-21 |  |  |  | 8644000 | 611853 | 9255853 | 7.078% | 9255853.0708 | 0 | 9255853.0708 | 100% | 7.54 | 100% | 0 | Project Closed | Final Acceptance
5186 | Luquillo | Yuquiyú II | Luz Acevedo | Inn Capital Housing Division Joint Venture | BMA | Enrique Ruiz & Asoc. | Unique Builders | 70 | 70 | 0 | 70 | 0 | 730 | 299 | 1029 | 40.96% | 1092 | 100% | 2006-02-15 | 2008-02-14 | 2008-12-09 | 2009-02-11 | 2009-06-09 |  | Tax Credit |  | 6964727 | 157419 | 7122146 | 2.26% | 6424134.91 | 0 | 6424134.91 | 90.2% | 15.6 | 100% | 0 | Project Closed | Final Acceptance
3056 | Maricao | Juan Ferrer | Noefebdo Ramírez | J. A. Machuca | NFC | René Batista & Assoc. | Comas & Comas | 30 | 30 | 0 | 30 | 0 | 420 | 251 | 671 | 59.76% | 610 | 100% | 2000-08-02 | 2001-09-25 | 2002-06-03 | 2002-04-04 | 2002-04-30 |  |  |  | 2210000 | 178940 | 2388940 | 8.097% | 2388940 | 0 | 2388940 | 100% | 20.3333 | 100% | 0 | Project Closed | Final Acceptance
3057 | Maunabo | Carmen Vda. Martorell (take over agreement) | Rubén Cotto | AVP | AVP | Rene Batista | American Intl. | 50 | 50 | 0 | 50 | 0 | 375 | 327 | 702 | 87.2% | 703 | 100% | 2000-08-18 | 2001-08-27 | 2002-07-20 | 2002-07-22 | 2005-06-02 |  |  |  | 1308221 | 116706 | 1424927 | 8.921% | 1424927 | 0 | 1424927 | 100% | 14.06 | 100% | 0 | Project Closed | Final Acceptance
5126 | Maunabo | Villa Navarro | Rubén Cotto | MJ Consulting | MD | José L. Irizarry & Assoc. | Inversiones OLPERI | 101 | 101 | 0 | 101 | 0 | 907 | 335 | 1242 | 36.93% | 1241 | 100% | 2000-01-24 | 2002-07-18 | 2003-06-18 | 2003-06-18 | 2003-06-18 |  |  |  | 6745000 | 238239 | 6983239 | 3.532% | 6983239 | 0 | 6983239 | 100% | 12.2871 | 100% | 0 | Project Closed | Final Acceptance
5012 | Mayagüez | Ext. Sábalos Gardens | Noefebdo Ramírez | Inn Capital Housing Division Joint Venture | URS Caribe / AVP | Joint Venture | Venegas Construction | 300 | 300 | 0 | 300 | 0 | 1281 | 690 | 1971 | 53.86% | 1963 | 100% | 2005-05-16 | 2008-11-16 | 2010-10-07 | 2010-09-30 | 2011-04-29 |  | Tax Credit 908-2008 |  | 28259000 | 14189.7 | 28273189.7 | 0.05021% | 29677970 | 0 | 29677970 | 105% | 6.5433 | 100% | 0 | Project Closed | Final Acceptance
4004 | Mayagüez | Sábalos Gdns. | Arturo Acevedo | Zeta | CMS | Héctor Rodríguez Amezquita | Caribe Tecno | 140 | 140 | 0 | 140 | 0 | 881 | 24 | 905 | 2.724% | 900 | 100% | 1999-11-15 | 2002-04-13 | 2002-05-07 | 2002-05-03 | 2002-11-06 |  |  |  | 11790000 | -294361.74 | 11495638.26 | -2.497% | 11495638 | 0 | 11495638 | 100% | 6.4286 | 100% | 0 | Project Closed | Final Acceptance
4006 | Mayagüez | Cuesta las Piedras | Arturo Acevedo | Zeta | CMS | García Cabot | RC Enginering | 142 | 142 | 0 | 142 | 0 | 1093 | 0 | 1093 | 0% | 907 | 100% | 2000-02-10 | 2003-02-06 | 2003-02-06 | 2002-08-05 | 2002-11-21 |  |  |  | 10673000 | 158657 | 10831657 | 1.487% | 10831657 | 0 | 10831657 | 100% | 6.3873 | 100% | 0 | Se aprobó el "close out". Contratista no cobró el total del contrato debido a ajustes deductivos recomendados por el "Program Manager"C.M. Services. | Final Acceptance
4008 | Mayagüez | Yagüez | Arturo Acevedo | ZETA | CMS | GDA Ing. Consultores | NLL Construction | 200 | 200 | 0 | 200 | 0 | 1399 | 0 | 1399 | 0% | 1177 | 100% | 2000-05-22 | 2004-03-20 | 2004-03-20 | 2003-08-12 | 2003-10-06 |  |  |  | 16799671 | -872594 | 15927077 | -5.194% | 15927077 | 0 | 15927077 | 100% | 5.885 | 100% | 0 | Project Closed | Final Acceptance
4005 | Mayagüez | Marini Farm | Frank Nieves | Zeta | BMA | CSA Architects | Empresas Toledo | 100 | 100 | 0 | 100 | 0 | 218 | 50 | 268 | 22.94% | 247 | 100% | 2004-05-12 | 2004-12-15 | 2005-02-03 | 2005-01-14 | 2005-09-07 |  |  |  | 845900 | 30508 | 876408 | 3.607% | 876408 | 0 | 876408 | 100% | 2.47 | 100% | 0 | Project Closed | Final Acceptance
5005 | Mayagüez | Mar y Sol | Noefebdo Ramírez | Zeta | CMS | Arq. Amadeo Pino | RC Enginering | 124 | 124 | 0 | 124 | 0 | 1055 | 14 | 1069 | 1.327% | 1068 | 100% | 2001-01-22 | 2003-12-12 | 2003-12-26 | 2003-12-26 | 2004-05-26 |  |  |  | 10513000 | 269417 | 10782417 | 2.563% | 10782417 | 0 | 10782417 | 100% | 8.6129 | 100% | 0 | Project Closed | Final Acceptance
5133 | Naguabo | Villas del Río | Félix Ortiz | MJ Consulting | MD | N/A | DGM Engineering | 100 | 100 | 0 | 100 | 0 | 730 | 906 | 1636 | 124.1% | 1640 | 100% | 2006-02-15 | 2008-02-14 | 2010-08-08 | 2010-08-13 | 2011-06-27 |  | Tax Credit |  | 11008930 | 1560851 | 12569781 | 14.18% | 12120952 | 0 | 12120952 | 96.43% | 16.4 | 100% | 0 | Project Closed | Final Acceptance
3063 | Peñuela | Los Flamboyanes | Noefebdo Ramírez | J.A. Machuca | MD | Fuertes, La Font & Asoc. | St. Paul Surety | 24 | 24 | 0 | 24 | 0 | 345 | 502 | 847 | 145.5% | 845 | 100% | 2003-04-15 | 2004-03-24 | 2005-08-08 | 2005-08-07 | 2005-09-26 |  |  |  | 1235996 | 568973 | 1804969 | 46.03% | 1804969 | 0 | 1804969 | 100% | 35.2083 | 100% | 0 | Project Closed | Final Acceptance
1014 | Ponce | Aristides Chavier | Noefebdo Ramírez | MJ Consulting | CCC Joint Venture | Unipro | Del Valle Group | 480 | 480 | 0 | 480 | 0 | 1464 | 552 | 2016 | 37.7% | 2003 | 100% | 2005-08-01 | 2009-08-03 | 2011-02-06 | 2011-01-25 | 2011-08-16 |  | Tax Credit 908-2008 |  | 43792000 | 2045988.7 | 45837988.7 | 4.672% | 45837989 | 0 | 45837989 | 100% | 4.1729 | 100% | 0 | Project Closed | Final Acceptance
5088 | Ponce | Lirios del Sur | Arturo Acevedo | J.A. Machuca | CMS | CSA Architects | Omega Engineering | 238 | 238 | 0 | 238 | 0 | 730 | 340 | 1070 | 46.58% | 1083 | 100% | 2003-02-12 | 2005-02-10 | 2006-01-16 | 2006-01-30 | 2006-04-12 |  |  |  | 18140000 | 570661 | 18710661 | 3.146% | 18710661 | 0 | 18710661 | 100% | 4.5504 | 100% | 0 | Project Closed | Final Acceptance
1001 | Ponce | Ponce de León ( Take Over Agreement) Fase I | José González | J. A. Machuca | MD | Interplan | American Intl. | 168 | 168 | 0 | 168 | 0 | 732 | 171 | 903 | 23.36% | 862 | 100% | 2000-08-28 | 2002-08-29 | 2003-02-16 | 2003-01-07 | 2003-01-30 |  |  |  | 10990000 | 512271 | 11502271 | 4.661% | 11447321.14 | 0 | 11447321.14 | 99.52% | 5.131 | 100% | 0 | Project Closed | Final Acceptance
1001 | Ponce | Ponce de León (Fase II) | Noefebdo Ramírez | MJ Consulting | BMA | Interplan | Constructora I. Meléndez | 132 | 132 | 0 | 132 | 0 | 730 | 748 | 1478 | 102.5% | 1442 | 100% | 2005-01-10 | 2007-01-09 | 2009-01-26 | 2008-12-22 | 2009-03-31 |  | Tax Credit 908-2008 |  | 13680284 | 787807 | 14468091 | 5.759% | 14448030 | 0 | 14448030 | 99.86% | 10.9242 | 100% | 0 | Project Closed | Final Acceptance
1002 | Ponce | Santiago Iglesias (Fase I) | Noefebdo Ramírez | Zeta | CMS | CSA | Ferrovial & Agroman | 160 | 160 | 0 | 160 | 0 | 487 | 505 | 992 | 103.7% | 1791 | 100% | 1997-10-28 | 1999-02-26 | 2000-07-15 | 2002-09-23 | 2002-11-02 |  |  |  | 9445984 | 580020 | 10026004 | 6.14% | 9993950 | 0 | 9993950 | 99.68% | 11.1937 | 100% | 0 | Project Closed | Final Acceptance
1016 | Ponce | Rafael López Nussa | Noefebdo Ramírez | MJ Consulting | BMA | URS Caribe | Del Valle Group | 404 | 404 | 0 | 404 | 0 | 1464 | 369 | 1833 | 25.2% | 1832 | 100% | 2004-10-25 | 2008-10-27 | 2009-10-31 | 2009-10-31 | 2010-06-16 |  | Tax Credit 908-2008 |  | 38744000 | 738951.13 | 39482951.13 | 1.907% | 39482951.13 | 0 | 39482951.13 | 100% | 4.5347 | 100% | 0 | Project Closed | Final Acceptance
1003 | Ponce | Caribe | Rubén Cotto | J.A. Machuca | MD | Lombardo Pérez | Caribe General Constructors | 116 | 116 | 0 | 116 | 0 | 720 | 358.4 | 1078.4 | 49.78% | 1192 | 100% | 2002-12-01 | 2004-11-19 | 2005-11-12 09:36 | 2006-03-07 | 2006-06-07 |  |  |  | 11468000 | 1539402.23 | 13007402.23 | 13.42% | 13007402 | 0 | 13007402 | 100% | 10.2759 | 100% | 0 | Project Closed | Final Acceptance
5022 | Ponce | La Ceiba | Rubén Cotto | MJ Consulting | BMA | Ray Engineers PSC | Jafer Construction | 300 | 300 | 0 | 300 | 0 | 1281 | 283 | 1564 | 22.09% | 1514 | 100% | 2004-10-11 | 2008-04-13 | 2009-01-21 | 2008-12-03 | 2009-01-30 |  | Tax Credit |  | 29600820 | 1001464.91 | 30602284.91 | 3.383% | 30602284.91 | 0 | 30602284.91 | 100% | 5.0467 | 100% | 0 | Project Closed | Final Acceptance
5095 | Ponce | Las Terrazas | Rubén Cotto | AVP | ISS Corp. | Méndez, Brunner, Badillo & Associates | Homeca Recycling Center Co., Inc. | 100 | 100 | 0 | 100 | 0 | 365 | 0 | 365 | 0% | 344 | 100% | 2009-07-28 | 2010-07-27 | 2010-07-27 | 2010-07-07 | 2010-07-27 |  | Mixed Fund |  | 1085000 | 0 | 1085000 | 0% | 918124.83 | 0 | 918124.83 | 84.62% | 3.44 | 100% | 0 | Se entregaron los documentos de cierre, pero aun le falta por cobrar al contratista la Cert # 8 - Parcial (10/Agosto/10) $ 36,954.06 y Cert.#10 - Retenido Final (22/Oct/10) $108,500.00, para un Totasl de $145,454.06, mas reclamacion de intereses por pago tardio. Alega el contratista que le han informado de finanzas que los fondos estan congelados, pero no le han explicado razon. | Final Acceptance
1002 | Ponce | Santiago Iglesias (Fase II) | Noefebdo Ramírez | Individual Management | Klassik Builders | CSA | Jafer Construction | 120 | 120 | 0 | 120 | 0 | 790 | 66 | 856 | 8.354% | 855 | 100% | 2009-06-15 | 2011-08-13 | 2011-10-18 | 2011-10-18 | 2012-01-26 |  | ARRA |  | 14498820 | 637269.47 | 15136089.47 | 4.395% | 15136089.47 | 0 | 15136089.47 | 100% | 7.125 | 100% | 0 | Project Closed | Final Acceptance
3066 | Río Grande | José H. Ramírez | Luz Acevedo | A & M | AVP / ORAM | Raúl Feliciano & Asoc. | J R Builders | 80 | 80 | 0 | 80 | 0 | 540 | 317 | 857 | 58.7% | 853 | 100% | 2000-03-29 | 2001-09-19 | 2002-08-02 | 2002-07-30 | 2002-11-15 |  |  |  | 3404949 | 226802 | 3631751 | 6.661% | 3631751 | 0 | 3631751 | 100% | 10.6625 | 100% | 0 | Project Closed | Final Acceptance
5145 | San Germán | Manuel F. Rossy | Frank Nieves | Municipio de San Germán | MD | Unipro | Cap Con Inc. | 101 | 101 | 0 | 101 | 0 | 732 | 84 | 816 | 11.48% | 815 | 100% | 2009-06-22 | 2011-06-23 | 2011-09-15 | 2011-09-15 | 2011-12-31 |  | CFP/ARRA |  | 10316000 | 610969.8 | 10926969.8 | 5.923% | 10908277 | 0 | 10908277 | 99.83% | 8.0693 | 100% | 0 | Project Closed | Final Acceptance
5035 | San Juan | Villa Esperanza | Luz Acevedo |  | LMC | Guillermety, Ortiz & Asoc. | Del Valle Group | 300 | 300 | 0 | 300 | 0 | 1130 | 233 | 1363 | 20.62% | 1323 | 100% | 2003-06-18 | 2006-07-21 | 2007-03-11 | 2007-01-31 | 2007-03-30 |  | CFP |  | 19819000 | 1078350.46 | 20897350.46 | 5.441% | 20897350.46 | 0 | 20897350.46 | 100% | 4.41 | 100% | 0 | Project Closed | Final Acceptance
5077 | San Juan | La Rosa | Jorge Mercado | AUTO ADM. | LMC | García Joglar & Arq. | DGM Engineers | 52 | 52 | 0 | 52 | 0 | 730 | 270 | 1000 | 36.99% | 984 | 100% | 2000-10-02 | 2002-10-01 | 2003-06-28 | 2003-06-13 | 2004-07-19 |  |  |  | 4491000 | 510039 | 5001039 | 11.36% | 5001039 | 0 | 5001039 | 100% | 18.9231 | 100% | 0 | Project Closed | Final Acceptance
5026 | San Juan | Los Lirios | Frank Nieves | A & M | CCC Joint Venture | DG3A | Builders Associates, LLC | 150 | 150 | 0 | 150 | 0 | 854 | 275 | 1129 | 32.2% | 1142 | 100% | 2009-11-12 | 2012-03-14 | 2012-12-14 | 2012-12-28 | 2013-04-19 |  | ARRA/CFP |  | 15075000 | 523404.07 | 15598404.07 | 3.472% | 15598404.07 | 0 | 15598404.07 | 100% | 7.6133 | 100% | 0 | The Contractor submitted a claim for extended overhead by amount of $989,402.32 | Final Acceptance
5099 | San Juan | El Prado | José González | Cost Control | BMA | Ray Architects | Del Valle Group | 220 | 220 | 0 | 220 | 0 | 1260 | 78 | 1338 | 6.19% | 1202 | 100% | 2000-09-15 | 2004-02-26 | 2004-05-14 | 2003-12-31 | 2004-01-28 |  | CFP |  | 15715000 | 1037001 | 16752001 | 6.599% | 16752001 | 0 | 16752001 | 100% | 5.4636 | 100% | 0 | Project Closed | Final Acceptance
5192 | San Juan | Antigua Via | José González | MAS Corporation | BMA | Rodríguez & del Valle (Design & Build) | Rodríguez & del Valle | 200 | 200 | 0 | 200 | 0 | 882 | 147 | 1029 | 16.67% | 1338 | 100% | 2000-01-10 | 2002-06-09 | 2002-11-03 | 2003-09-09 | 2003-09-09 |  | CFP |  | 13397000 | 211211 | 13608211 | 1.577% | 13608211 | 0 | 13608211 | 100% | 6.69 | 100% | 0 | Project Closed | Final Acceptance
2010 | San Juan | Vista Hermosa II (Fase II) | José Negrón | MAS Corporation | AVP / Jorge L. Robert | Guillermety, Ortiz & Asoc. | Urban Builders | 476 | 476 | 0 | 476 | 0 | 1216 | 590 | 1806 | 48.52% | 1442 | 100% | 1997-04-07 | 2000-08-04 | 2002-03-17 | 2001-03-19 | 2001-12-13 |  |  |  | 17900000 | 1037096.5 | 18937096.5 | 5.794% | 18371767.14 | 0 | 18371767.14 | 97.01% | 3.0294 | 100% | 0 | Project Closed | Final Acceptance
5031 | San Juan | Jardines de Campo Rico | José Negrón | Cost Control | CMS | DG3A | North Connstruction | 196 | 196 | 0 | 196 | 0 | 750 | 263 | 1013 | 35.07% | 1012 | 100% | 2006-01-30 | 2008-02-18 | 2008-11-07 | 2008-11-07 | 2008-12-04 |  | Tax Credit |  | 19483000 | 17564 | 19500564 | 0.09015% | 19500564 | 0 | 19500564 | 100% | 5.1633 | 100% | 0 | Project Closed | Final Acceptance
5143 | San Juan | Monte Park | José Negrón | Housing Promoters | AVP / SAGA | Molinary | Fernández & Gutiérrez | 224 | 224 | 0 | 224 | 0 | 874 | 345 | 1219 | 39.47% | 1517 | 100% | 1996-11-01 | 1999-03-24 | 2000-03-03 | 2000-12-27 | 2001-03-09 |  |  |  | 10585212 | 350973 | 10936185 | 3.316% | 10936185 | 0 | 10936185 | 100% | 6.7723 | 100% | 0 | Project Closed | Final Acceptance
5017 | San Juan | San Martín | Luis Rodríguez | Housing Promoters | LMC | Enrique Ruiz & Assoc. | Del Valle Group | 300 | 300 | 0 | 300 | 0 | 1095 | 353 | 1448 | 32.24% | 1631 | 100% | 2003-05-14 | 2006-05-12 | 2007-04-30 | 2007-10-31 | 2008-01-30 |  |  |  | 19703000 | 845652.15 | 20548652.15 | 4.292% | 20180652.15 | 0 | 20180652.15 | 98.21% | 5.4367 | 100% | 0 | Project Closed | Final Acceptance
5023 | San Juan | San Fernando | Luis Rodríguez | Cost Control Company, Inc. | LMC | DDHK | Del Valle Group | 334 | 334 | 0 | 334 | 0 | 1190 | 807 | 1997 | 67.82% | 1965 | 100% | 2004-12-10 | 2008-03-13 | 2010-05-29 | 2010-04-28 | 2010-10-15 |  | Tax Credit |  | 32133000 | 1051432.05 | 33184432.05 | 3.272% | 33163350.99 | 0 | 33163350.99 | 99.94% | 5.8832 | 100% | 0 | Project Closed | Final Acceptance
5135 | San Juan | Las Dalias | Luis Rodríguez | Housing Promoters | CMS | CSA Architects | Del Valle Group | 240 | 240 | 0 | 240 | 0 | 1195 | 271 | 1466 | 22.68% | 1458 | 100% | 2004-02-25 | 2007-06-03 | 2008-02-29 | 2008-02-22 | 2008-04-22 |  | Tax Credit 908-2008 |  | 22437872.18 | 818872.18 | 23256744.36 | 3.65% | 23256744.36 | 0 | 23256744.36 | 100% | 6.075 | 100% | 0 | Project Closed | Final Acceptance
5161 | San Juan | El Manatial | Luis Rodríguez | MAS Corporation | CMS | Behar-Ybarra | Del Valle Group | 200 | 200 | 0 | 200 | 0 | 890 | 345 | 1235 | 38.76% | 1234 | 100% | 2004-01-26 | 2006-07-03 | 2007-06-13 | 2007-06-13 | 2008-05-19 |  |  |  | 12929000 | 1024355.41 | 13953355.41 | 7.923% | 13953355.41 | 0 | 13953355.41 | 100% | 6.17 | 100% | 0 | Project Closed | Final Acceptance
5080 | San Juan | Jardines de Cupey | Félix Ortiz | Cost Control Company, Inc. | URS Caribe | Gautier & de Torres | Ferrovial Agroman | 308 | 308 | 0 | 308 | 0 | 1095 | 628 | 1723 | 57.35% | 1660 | 100% | 2006-02-15 | 2009-02-13 | 2010-11-03 | 2010-09-02 | 2011-08-22 |  | Tax Credit |  | 33630461 | 1042731.4 | 34673192.4 | 3.101% | 34673192.4 | 0 | 34673192.4 | 100% | 5.3896 | 100% | 0 | Project Closed | Final Acceptance
5040 | San Juan | Jardines de Sellés Fase I (Take over agreement) | Luz Acevedo |  | BMA | URS Dames & Moore | Urban Builders (St. Paul Surety) | 184 | 184 | 0 | 184 | 0 | 90 | 0 | 90 | 0% | 114 | 100% | 2003-08-20 | 2003-11-17 | 2003-11-17 | 2003-12-12 | 2004-02-17 |  | CFP |  | 9975000 | 231719 | 10206719 | 2.323% | 10206719 | 0 | 10206719 | 100% | 0.61957 | 100% | 0 | Project Closed | Final Acceptance
5040 | San Juan | Jardines de Sellés (Fase II) | Luz Acevedo | Housing Promoters | BMA | URS Caribe | Rodríguez & del Valle | 216 | 216 | 0 | 216 | 0 | 1095 | 320 | 1415 | 29.22% | 1415 | 100% | 2002-06-17 | 2005-06-15 | 2006-05-01 | 2006-05-02 | 2007-05-27 |  |  |  | 15268000 | 968748 | 16236748 | 6.345% | 16236748 | 0 | 16236748 | 100% | 6.5509 | 100% | 0 | Project Closed | Final Acceptance
5015-5140 | San Juan | Las Gladiolas I & II | Félix Ortiz | MAS Corp. | CCC-JV | Méndez-Brunner | Del Valle Group | 676 | 676 | 0 | 676 | 0 | 365 | 77 | 442 | 21.1% | 449 | 100% | 2011-04-11 | 2012-04-09 | 2012-06-25 | 2012-07-03 | 2013-02-08 |  | CFP |  | 2932000 | 129200.55 | 3061200.55 | 4.407% | 3061200.55 | 0 | 3061200.55 | 100% | 0.6642 | 100% | 0 | Pending Close Out | Final Acceptance
2003 | San Juan | Puerta de Tierra | Pedro Vega | Cost Control Company, Inc. | LMC | Guillermety, Ortiz & Asoc. | Homeca Recycling 2007-0498A | 148 | 148 | 0 | 148 | 0 | 150 | 300 | 450 | 200% | 543 | 100% | 2007-03-22 | 2007-08-18 | 2008-06-13 | 2008-09-15 |  |  | CFP |  | 678000 | 152491.82 | 830491.82 | 22.49% | 830492 | 0 | 830492 | 100% | 3.6689 | 100% | 0 | Project Closed | Final Acceptance
2003 | San Juan | New Puerta de Tierra | Pedro Vega | Cost Control Company, Inc. | LMC | Guillermety, Ortiz & Asoc. | Cué & López Construction, Inc | 85 | 85 | 0 | 85 | 0 | 900 | 20 | 920 | 2.222% | 823 | 100% | 2008-11-10 | 2011-04-28 | 2011-05-18 | 2011-02-11 | 2011-05-17 |  | CFP/Línea de Crédito |  | 16770000 | 813871.99 | 17583871.99 | 4.853% | 17583871.99 | 0 | 17583871.99 | 100% | 9.6824 | 100% | 0 | Project Closed | Final Acceptance
2004 | San Juan | San Agustín | José M. Paris Escalera | AM Contractors | Klassik Builders | Ray Engineers PSC | Cuè & López Construction, Inc | 84 | 84 | 0 | 84 | 0 | 570 | 304 | 874 | 53.33% | 869 | 100% | 2009-12-14 | 2011-07-06 | 2012-05-05 | 2012-05-01 | 2012-07-18 |  | ARRA |  | 3746000 | 1029880.39 | 4775880.39 | 27.49% | 4775880.39 | 0 | 4775880.39 | 100% | 10.3452 | 100% | 0 | Project Closed | Final Acceptance
2012 | San Juan | Villa España | Pedro Vega | Cost Control Company | LMC | Ray Engineers, PSC | Rodríguez & del Valle | 500 | 500 | 0 | 500 | 0 | 1280 | 929 | 2209 | 72.58% | 2208 | 100% | 2003-09-29 | 2007-03-31 | 2009-10-15 | 2009-10-15 | 2010-10-21 |  | Tax Credit |  | 33768000 | 1862123 | 35630123 | 5.514% | 35630123 | 0 | 35630123 | 100% | 4.416 | 100% | 0 | Project Closed | Final Acceptance
3090 | Salinas | Bella Vista | Félix Ortiz | MJ Consulting | Klassik Builders | INTEGRA | LPC&D | 100 | 100 | 0 | 100 | 0 | 730 | 160 | 890 | 21.92% | 889 | 100% | 2009-09-08 | 2011-09-07 | 2012-02-14 | 2012-02-14 | 2012-07-16 |  | ARRA |  | 10500000 | 749675.93 | 11249675.93 | 7.14% | 11249675.93 | 0 | 11249675.93 | 100% | 8.89 | 100% | 0 |  | Final Acceptance
5092 | San Lorenzo | La Lorenzana | Iván Blanco | MJ Consulting | URS | René Acosta Ingenieros | CD Builders | 100 | 100 | 0 | 100 | 0 | 730 | 351 | 1081 | 48.08% | 1147 | 100% | 2005-09-14 | 2007-09-13 | 2008-08-29 | 2008-11-04 | 2009-09-17 |  | Tax Credit |  | 10310000 | 828444.55 | 11138444.55 | 8.035% | 11138444.55 | 0 | 11138444.55 | 100% | 11.47 | 100% | 0 | Project Closed | Final Acceptance
3087 | San Sebastian | Andrés Méndez Liceaga | Arturo Acevedo | Inn Capital Housing Division Joint Venture | CMS | Interplan | RC Engineering | 150 | 150 | 0 | 150 | 0 | 960 | 729 | 1689 | 75.94% | 1688 | 100% | 2004-05-24 | 2007-01-08 | 2009-01-06 | 2009-01-06 | 2009-02-16 |  | Tax Credit |  | 13130000 | 401586.86 | 13531586.86 | 3.059% | 13531587 | 0 | 13531587 | 100% | 11.2533 | 100% | 0 | Project Closed | Final Acceptance
5144 | Santa Isabel | Rincón Taíno | Rubén Cotto | J. A. Machuca | BMA | Hernández - Bauzá | Constructora I. Meléndez | 100 | 100 | 0 | 100 | 0 | 810 | 499 | 1309 | 61.6% | 1087 | 100% | 2003-07-28 | 2005-10-14 | 2007-02-25 | 2006-07-19 | 2006-09-30 |  |  |  | 7231087 | 175900 | 7406987 | 2.433% | 6372476 | 0 | 6372476 | 86.03% | 10.87 | 100% | 0 | Las OC # 7 y 8 fueron sometidas por el CM, pero le fueron devueltas para aclaracion o correccion, ya que el NGC no esta de acuerdo con el tiempo de extension otorgado y los "supporting documents". Posteriormente el CM las entrego fuera del termino de vigencia y las mismas no se pudieron procesar. El contratista sometio demanda y se efectuo reunion entre ambas representaciones legales. Se llego a un acuerdo: AVP de pagar lo que se le adeudaba por concepto de daños liquidos y retenido, Contratista: No reclamar "extended overhead" ni la OC #8. Esto hace varios meses y AVP tiene pendiente procesar los pagos correspondientes. | Final Acceptance
5198 | Toa Alta | Jardines de San Fernando | Luis Rodríguez | Housing Promoters | MD | URS Caribe, LLP | Orion Contractors | 51 | 51 | 0 | 51 | 0 | 800 | 1627 | 2427 | 203.4% | 2502 | 100% | 2006-01-09 | 2008-03-18 | 2012-08-31 | 2012-11-15 | 2013-10-15 |  | BFP-2003 |  | 7227000 | -982226.89 | 6244773.11 | -13.59% | 6244773.11 | 0 | 6244773.11 | 100% | 49.0588 | 100% | 0 | The PRPHA and the Contractor signed a Termination by Convinience (TBC), where the contractor grants a creditfor the amount of $2,182,368.61 for the remaining work phase IV,V and VIII. The PRPHA extends the contract by 744 calendar days providing a substantial termination effective at the August 31, 2012. The contractor walves its claim for extended overhead. | Final Acceptance
3069 | Toa Baja | El Toa | Jorge Mercado | MJ Consulting | AVP | Soler Cloquel & Asoc. | Royal Ins. | 80 | 80 | 0 | 80 | 0 | 669 | 458 | 1127 | 68.46% | 1205 | 100% | 1997-06-30 | 1999-04-29 | 2000-07-30 | 2000-10-17 | 2001-05-18 |  |  |  | 4045086 | 299127 | 4344213 | 7.395% | 4344213 | 0 | 4344213 | 100% | 15.0625 | 100% | 0 | Project Closed | Final Acceptance
5193 | Trujillo Alto | Los Rosales | José M. Paris Escalera | Peregrine Group Inc. | Klassik Builders | URS Caribe, LLP | Cidra Excavation, SE | 74 | 74 | 0 | 74 | 0 | 730 | 138 | 868 | 18.9% | 821 | 100% | 2009-11-16 | 2011-11-15 | 2012-04-01 | 2012-02-15 | 2012-08-14 |  | ARRA |  | 7947800 | 1458351.48 | 9406151.48 | 18.35% | 9406151.48 | 0 | 9406151.48 | 100% | 11.0946 | 100% | 0 | Project Closed | Final Acceptance
3071 | Vega Alta | Fco. Vega Sánchez | José Negrón | MJ Consulting | LMC | Hernández - Bauzá | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 782 | 109 | 891 | 13.94% | 890 | 100% | 2000-10-02 | 2002-11-22 | 2003-03-11 | 2003-03-11 | 2003-04-11 |  |  |  | 9309000 | 70614.85 | 9379614.85 | 0.7586% | 9379616 | 0 | 9379616 | 100% | 8.9 | 100% | 0 | Project Closed | Final Acceptance
5105 | Vega Alta | Las Violetas | Luis Rodríguez | Cost Control Company, Inc. | ISS | URS Dames & Moore | Del Valle Group | 88 | 88 | 0 | 88 | 0 | 730 | 150 | 880 | 20.55% | 1000 | 100% | 2006-02-01 | 2008-01-31 | 2008-06-29 | 2008-10-28 | 2009-09-30 |  | Tax Credit |  | 9203600 | 46081.53 | 9249681.53 | 0.5007% | 9007681.53 | 0 | 9007681.53 | 97.38% | 11.3636 | 100% | 0 | Project Closed | Final Acceptance
3073 | Villalba | Efraín Suárez Negrón | Arturo Acevedo | J.A. Machuca | CMS | Yañez & Mayol | Ravaro Construction | 60 | 60 | 0 | 60 | 0 | 660 | 295 | 955 | 44.7% | 1240 | 100% | 2002-04-15 | 2004-02-03 | 2004-11-24 | 2005-09-06 | 2005-09-06 |  |  |  | 4033500 | 93123 | 4126623 | 2.309% | 4126623 | 0 | 4126623 | 100% | 20.6667 | 100% | 0 | Project Closed | Final Acceptance
5164 | Villalba | Maximino Miranda Jiménez | Félix Ortiz | Municipio de Villalba | Klassik Builders | LPA Group, Arq. | Constructora I. Meléndez | 100 | 100 | 0 | 100 | 0 | 732 | 180 | 912 | 24.59% | 911 | 100% | 2009-05-20 | 2011-05-21 | 2011-11-17 | 2011-11-17 | 2012-01-19 |  | CFP/ARRA |  | 12392438 | 408291.81 | 12800729.81 | 3.295% | 12800729.81 | 0 | 12800729.81 | 100% | 9.11 | 100% | 0 | Project Closed | Final Acceptance
5067 | Yauco | Ext. Santa Catalina | Rubén Cotto | Inn Capital Housing Division Joint Venture | URS | René Acosta Ingenieros | A. Rivera & Asociados | 24 | 24 | 0 | 24 | 0 | 548 | 319 | 867 | 58.21% | 814 | 100% | 2006-01-16 | 2007-07-17 | 2008-05-31 | 2008-04-09 | 2008-08-26 |  | CFP-2003 |  | 1972404 | 50556.96 | 2022960.96 | 2.563% | 2022961 | 0 | 2022961 | 100% | 33.9167 | 100% | 0 | Project Closed | Final Acceptance
| 7 | Active | [5 empty] | 20299 | 19627 | 78 | 19705 | 60 | [14 empty] | 74867307 | 4238267.63 | 1591160223.14 |  | 59995942.25 | 1271462.02 | 1560151505.8908 |  |  |  | #DIV/0! |  | Active
| 2 | Stopped | [5 empty] | 192 | 16 | 0 | 16 | 0 | [14 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | Stopped
| 10 | Substantial | [5 empty] | 1656 | 1626 | 0 | 1626 | 0 | [14 empty] | 79925735 | 10200674.88 | 90126409.88 |  | 86089768.12 | 0 | 86089768.12 |  | 13.542 |  |  |  | Substantial Completion
| 110 | Final Acceptance | [5 empty] | 17405 | 17405 | 0 | 17405 | 0 | [14 empty] | 1338745030.27 | 83183208.36 | 1421928238.63 |  | 1412794333.5008 | 0 | 1412794333.5008 |  | 9.8658 |  |  |  | Final Acceptance
Total | 129 | [6 empty] | 20299 | 19627 | 78 | 19705 | 60 | [14 empty] | 1493538072.27 | 97622150.87 | 3182320446.28 |  | 1558880043.8708 | 1271462.02 | 3120303011.7816 |  | 10.1721 |  | 0 |  | Total
| Revised by: |  |  |  | Approved by: | [19 empty] | Approved by:
|  | Luz M. Acevedo Pellot, PE |  |  |  |  | Germán Acevedo Marín, PE | [18 empty] | Arturo A. Garcia de la Noceda Castro, PE
|  | Project Coordinator |  |  |  |  | Director | [18 empty] | Deputy Administrator
|  | Construction Management Bureau |  |  |  |  | Construction Management Bureau | [18 empty] | Development and Construction Area
Report Date: |  |  | 2014-04-30
Report Last Revision Date: |  |  | 2014-05-10
Notes/Notas:
CMB Monthly Report is prepared for the use of Construction and Development Area. The Associate Administrator will approve any use of this report outside this area and must have his signature to be valid.
Informe preparado para uso del Área de Desarrollo y Construcción de Proyectos. El Administrador Asociado aprobará cualquier uso de este Informe fuera del Área y debe tener su firma para ser válido.
Information is provided by PRPHA Project Monitors, and is subject to change.
La Información es suministrada con los datos que proveen los Monitores de Proyectos, por lo que está sujeta a cambios.
Final Acceptance Report contains all Projects. This report is not worked by fiscal or natural year, it is a report that contains cumulative information and not all projects present monthly changes.
El Informe de "Final Acceptance" contiene todos los Proyectos. No se trabaja por Año Natural o Año Fiscal; es un reporte que contiene información acumulativa y no en todos los Proyectos se presentan cambios mensuales.
NOTIFICACIÓN DE CONFIDENCIALIDAD: Este Informe y cualquier archivo transmitido en ella pueden contener información confidencial, privilegiada y/o privada bajo las leyes aplicables. Se utiliza solamente para el uso o entidad a que se dirige. Si usted no es el destinatario intencional, se le notifica que cualquier uso, diseminación o copia de esta Informe se prohíbe estrictamente. Si usted recibe esta Informe por error, notificar al remitente inmediatamente y destruir el material en su totalidad.
CONFIDENTIALITY NOTICE: This report and any files transmitted with it may contain information that is confidential, privileged and exempt from disclosure under applicable law. It is intended solely for the use of the individual or entity to which it is addressed. If you are not the intended recipient, you are hereby notify that any use, dissemination or copying of this report is strictly prohibited. If you have received this communication by error, immediately contact the sender and destroy the material in its entirety, whether in electronic of hard copy format.
Formulas:
U=T+N-1 = [T]+[N]-1
V=T+P-1 = [T]+[P=N+O]-1
W = +[T]
Note on AC15: lvlynn: Discrepancia: $98,932 Inf. Monitor
Note on H48: lvlynn: Contratista Default Target Engineering
Note on W77: lvlynn: 9-junio-09 Final
Note on W81: lvlynn:
Note on AC96: OC 1 @ 13
Note on Z97: lvlynn: CFP-Línea de Crédito

## ACTIVE PROJECTS MONTHLY REPORT
A | B | C | D | E | F | G | H | I | J | K | L=J+K | M | N | O | P=N+O | Q=O/N | R=DATE-T | S=R/P | T | U=T+N-1 | V=T+P-1 | W | X | Y | Z | AA | AB | AC | AD=AB+AC | AE=AC/AB | AF | AG | AH=AF+AG | AI=AH/AD | AJ=(W-T)/I | AK |  | AK | AL
RQ | Municipality | Name of the Project | PHAPR Monitor | Management Agent | Construction Manager/PM | Designer (A/E) | Contractor | Units |  |  |  |  | Times | [5 empty] | Dates | [5 empty] | Funds | [9 empty] | Certified Days/Unit | % Progress | Monthly Employment | Executive Summary | Status
[8 empty] | Total Dwelling Units | Previous Completed Dwelling Units | Completed Dwelling Units for this Period | Total Completed Dwelling Units | Dwelling Units Forecast for next Month | Contruction Period (Cal. Days) | Time Extension (Cal. Days) | Revised Construction Period (Cal. Days) | % Extended Time | Elapsed Time (Cal. Days) | Elapsed Time (%) | Construction Start Date | Original Completion Date | Revised Construction Completion Date | Substantial Completion Date | Final Acceptance Date | Registered at Controller Contract Termination Date | Funds Proceeds | Funds Obligation Date | Original Construction Contract Amount | Approved Change Orders Amount ($) | Revised Construction Contract Amount | % Of Change Orders | Previous Certified Amount | Certified this Period | Total Certified Amount | Certified Amount (%)
3025 | Carolina | Felipe Sánchez Osorio (Demolition) | Luis Rodríguez | N/A | Municipio de Carolina | State Engineering | Municipio de Carolina | 32 | 26 | 0 | 26 | 0 | 120 | 0 | 120 | 0% | 259 | 215.8% | 2013-08-14 | 2013-12-11 | 2013-12-11 | 0 | 0 | 0 | 0 | 0 | 336510 | 0 | 336510 | 0% | 27516.72 | 122054.24 | 149570.96 | 44.45% |  | 0% | 0 | ♦ Project Situation according to the CPM Uptaded: Phase I was completed on November 27, 2013. ♦ Reasons of the Delay (if applies) N/A ♦ Change Order in PRPHA pending for approval: N/A ♦ Extraordinary Situations with Relocation (if applies)- N/A ♦ Situations with Governmental Agencies (if applies): N/A ♦ Others situations that are affecting the project (if Applies): N/A | Active
5127 | Arecibo | La Meseta | Pedro Vega | Housing Promoters, Inc. | AVP | ERA | Maglez Engineering & Contractors, Corp. | 0 | 0 | 0 | 0 | 0 | 365 | 0 | 365 | 0% | 394 | 107.9% | 2013-04-01 | 2014-03-31 | 2014-03-31 | 0 | 0 | 2014-03-31 | CFP | 0 | 1602797 | 0 | 1602797 | 0% | 979943.16 | 71165.27 | 1051108.43 | 65.58% |  | 0% | 0 | • Project Situation: Some submmittal requirement from designer are delaying the Contractor's time to make purchase orders or solve construction problems as design error for primary system upgrade. • Project Status: Last CPM Updated february 28,2014, refected a reduction of project delay from 49 days behind schedule. There is a CO #1 with 14 calendars days pending for PRPHA approval. New letter of intents are in negotiation that can reflect additional extension claim. • Change Orders: CO #1 $41,193.88 where send to PRPHA. • Last Certification: #11 february 28, 2014 • Relocation issues: There is not Relocation issues. • Goverment Agencies issues: AEE are requiring change to approved design that represent additional cost to project. • Other Situation issues: There is not AAA endorsement. this month the designer submmit the endorsement amedment. | Active
4011 | Mayaguez | Rafael Hernandez (El Kennedy) | Noefebdo Ramírez | JA Machuca | Klassik Builders | Hernán Jr. Machado Ingenieros Consultores | F & R Construction | 190 | 26 | 0 | 26 | 24 | 1094 | 153 | 1247 | 13.99% | 926 | 74.26% | 2011-10-17 | 2014-10-14 | 2015-03-16 | 0 | 0 | 2016-02-07 | CFP | 0 | 21797000 | 446287.81 | 22243287.81 | 2.047% | 13868385.06 | 204312.21 | 14072697.27 | 63.27% |  | 0% | 0 | • Project situation according to the CPM updated: According to the last CPM updated, the project finish date is September 3, 2015. The contract revisedconstruction completion date is March 16,2015. That represent 171 days of delay. When thechange order # 9 be approvedthe completion date move to May 30, 2015. the Change Order # 10 included 10 aditional days for weather conditions. Then represent 58 days of delay. • Reasons of the Delay: One reasons is the delay for termination and delivery of modernized units by the Contractors. The lead and asbestos abatement started on February 3,2014 to enclosure the building # 4. The buildingcome to be ready to start the works on March 21,2014, No contruction works can't do it into the buildings. Those impact the crithical path which is total responsability of the contractor. In special the building # 18, which in the next building in the modernization sequence and are stopped for 108 days. • Change Order in PRPHA pending for approval:. The CO # 9 (193,914.32 and include 75 calendar days extension) and change order # 10 (of $562,564.73 and include 10 calendar days extension) • Payments Certifications Status: The Contractor has pending to submit to PRPHA the Certifications for partial payment of # 30 (February 2014 period) and # 31 (March 2014 period) • Extraordinary Situations with Relocation - N/A • Situations with Governmental Agencies: The tapping conection for the potable water services, under the PR #2 state road was not do it in this period. This tapping is a change order in a process of negotiation. The AAA final endosement depend of finish this connection works. The Puerto Rico Power Authority present a new request to install other facilities for existingsanitary pump station. That works were not contemplted in the design. • Others situations that are affecting the project: The installationof the restrainers in the 36 inches ductile iron forced line was not completed in this period. A 70% of the total pipe line need to be reinstalling. A wprkplan was by KBI to the Contractor to define this work to be done during summer school vacation as requested. | Active
3105 | San Juan | Ext. Manuel A. Pérez | Arturo Acevedo | MAS Corp. | Klassik Builders | DDHK | LPC&D | 324 | 188 | 12 | 200 | 12 | 1098 | 433 | 1531 | 39.44% | 1385 | 90.46% | 2010-07-15 | 2013-07-16 | 2014-09-22 | 0 | 0 | 2015-08-06 | HOPE IV | 0 | 24800000 | 1110120.04 | 25910120.04 | 4.476% | 19847694.84 | 161086 | 20008780.84 | 77.22% |  | 0% | 0 | • Project situation according to the CPM updated • Reasons of the Delay (if applies) • Payments Certifications Status- Lastcertification rendered for payment is certification # 42, for the period of January 2014. • Change Orders: • Extraordinary Situations with Relocation (if applies)-N/A • Situations with Governmental Agencies (if applies)-N/A • Others situations that are affecting the project (if applies)-N/A • Withheld: | Active
5034 | San Juan | Alturas de Cupey | José M. Paris | SP Management Corp. | Klassik Builders | CSA | F&R Construction | 96 | 48 | 16 | 64 | 0 | 732 | 256 | 988 | 34.97% | 1057 | 107% | 2011-06-08 | 2013-06-08 | 2014-02-19 | 0 | 0 | 2015-06-20 | CFP | 0 | 7936000 | 1003018.78 | 8939018.78 | 12.64% | 7832237.98 | 470242.15 | 8302480.13 | 92.88% |  | 0% | 0 | • Project situation according to the CPM updated: According to the last CPM updated on June 2013, the project is 72 calendar days ahead schedule with a possible termination date on December 19, 2013. • Reasons of the Delay (if applies) • Bad execution by the Contractor (if applies)- N/A • Change Orders pending for approval - N/A • Others (if applies) - a) Weather and site conditions (Soil Moisture) • Change Order in PRPHA pending for approval: N/A • Latest Certification: The last certification for payment submitted by the Contractor correspond to the period of July 26, 2013 thru August 25, 2013 (Certification #27 for the amount of $470,242.15 • Extraordinary Situations with Relocation (if applies) - N/A • Situations with Governmental Agencies (if applies) - N/A • Others situations that are affecting the project (if applies) - N/A | Active
5068 | San Juan | Las Amapolas (Demolition) | Noefebdo Ramírez | SP Management Corp. | AVP | Integra | Anibal Díaz Construction, Inc. | 204 | 138 | 50 | 188 | 16 | 365 | 0 | 365 | 0% | 176 | 48.22% | 2013-11-05 | 2014-11-04 | 2014-11-04 | 0 | 0 | 2015-10-30 | CFP | 0 | 948000 | 0 | 948000 | 0% | 231193.27 | 0 | 231193.27 | 24.39% |  | 0% | 0 | • Project situation according to CPM (updated): According to the CPM, the project is on schedule. • Reasons of Delay: none • Change Orders in PRPHA pending for Approval: none • Payments CertificationS Status: The contractor has pending to submit to PRPHA the certificactions for the partial Payments # 3 (February 2014) and #4 (March 2014 period) • Extraordinary situations with Relocation: N/A • Situations with Governmental Agencies: none • Other situations that are affecting the project: No report in this moment. | Active
5028 | Yauco | Ana Catalina Rodríguez Vélez (Santa Catalina) | Arturo Acevedo | JA Machuca | AVP | URS Caribe LLC | La Mar Construction Corporation | 200 | 154 | 0 | 154 | 8 | 1098 | 339 | 1437 | 30.87% | 1525 | 106.1% | 2010-02-25 | 2013-02-26 | 2014-01-31 | 0 | 0 | 2014-11-26 | ARRA/Mixed | 0 | 17447000 | 1678841 | 19125841 | 9.623% | 17208971.22 | 242602.15 | 17451573.37 | 91.25% |  | 0% | 0 | • Project situation according to CPM (updated): • Reasons of Delay: • Change Orders in PRPHA pending for Approval: • latest Certification: Last certification rendered for payment is certification # 49 (February 2014) • Extraordinary situations with Relocation: N/A • Situations with Governmental Agencies: N/A • Other situations that are affecting the project: N/A | Active
5011 | San Juan | Jardines del Paraíso | José Negrón | Cost Control Company, Inc. | BMA | Andrés Hernández & Asoc. | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 41759 | #DIV/0! | 0 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | 0% | 0 | Proyecto en Re-Subasta. Subasta declarada Desierta. No se ha Comenzado el proyecto. | Stoped
3049 | Lajas | Las Américas | Noefebdo Ramírez | Inn Capital Housing Division Joint Venture | none | URS Caribe, LLP | none | 80 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | #DIV/0! | 41759 | #DIV/0! | 0 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | 0% | 0 | Design completed. Pending for will be assigned construction funds by PHA. | Stoped
3100 | Aguadilla | Agustín Stahl I | Arturo Acevedo | American Management Corp. | CCC-JV | René Acosta Arquitectos | Karimar Construction, Inc. | 180 | 180 | 0 | 180 | 0 | 915 | 192 | 1107 | 20.98% | 1100 | 100% | 2010-03-23 | 2012-09-22 | 2013-04-02 | 2013-03-27 | 0 | 0 | ARRA/CFP | 0 | 13875675 | 597322.95 | 14472997.95 | 4.305% | 13367679 | 0 | 13367679 | 92.36% | 6.1111 | 0% | 0 | Project started on march 23, 2010. substantial completion was awarded on March 27 2013 Last certification rendered for payment is certification # 38, for the period of March 1 to 30, 2013. | Substantial Completion
5201 | Cayey | Alturas de Montellano | Jorge Mercado | Municipio | LMC | Arq. José Luzunaris | RC Group S.E. | 80 | 50 | 0 | 50 | 0 | 730 | 846 | 1576 | 115.9% | 1970 | 100% | 2001-09-04 | 2003-09-03 | 2005-12-27 | 2007-01-26 | 0 | 0 | CFP | 2001-11-21 | 4790000 | 2327268.37 | 7117268.37 | 48.59% | 7036300.8 | 0 | 7036300.8 | 98.86% | 24.625 | 0% | 0 | Nunca se aprobaron las ordenes de cambio #17 y #18 porque el contratista no sometió los documentos solicitados por el Área de Adquisición y Contratación. Nunca se le otorgó el "Final Acceptance". El caso esta siendo atendido en la División Legal de la Admnisitración de Vivienda Pública. Queda un balance de $80,967.57 en espera se resuelva la controversia. | Substantial Completion
3089 | Juana Díaz | Villa del Parque (Take over agreement) | Rubén Cotto | J.A. Machuca | MD | GMG Eng. Consultants | (USF & G) | 100 | 100 | 0 | 100 | 0 | 547 | 746 | 1293 | 136.4% | 552 | 100% | 2000-12-18 | 2002-06-17 | 2004-07-02 | 2002-06-23 | 0 | 0 | CFP | 2000-09-30 | 3105100 | 239005.38 | 3344105.38 | 7.697% | 3171314 | 0 | 3171314 | 94.83% | 5.52 | 0% | 0 | El "final acceptance" le fue entregado a la Administracion del proyecto , JA Machuca, no obstante los mismos no lo han firmado ya que la Aseguradora no ha sometido aun los documentos de garantía de techo. Se le indicó vervalmente al Ing. Carrasquillo, representante de la Aseguradora. | Substantial Completion
3093 | Juncos | Narciso Varona Fase II | José González | MJ Consulting | AVP | DG3A Design Group, PSC | F & R Construction Group, Inc. | 172 | 172 | 0 | 172 | 0 | 1220 | 235 | 1455 | 19.26% | 1385 | 100% | 2010-02-24 | 2013-06-27 | 2014-02-17 | 2013-12-10 | 0 | 0 | Arra/Mixed | 0 | 13189000 | 822958.39 | 14011958.39 | 6.24% | 13762592.18 | 0 | 13762592.18 | 98.22% | 8.0523 | 0% | 0 | Project is almost completed. | Substantial Completion
5053 | Mayagüez | Ramírez de Arellano | Pedro Vega | JA Machuca | LMC | GMG Engineering | Comas & Comas Contractors, Corp | 80 | 80 | 0 | 80 | 0 | 720 | 661 | 1381 | 91.81% | 1375 | 100% | 2009-07-13 | 2011-07-02 | 2013-04-23 | 2013-04-18 | 0 | 0 | ARRA/CFP | 0 | 4040000 | 2215708.24 | 6255708.24 | 54.84% | 6011262.53 | 0 | 6011262.53 | 96.09% | 17.1875 | 0% | 0 | Final Completion and Close Out era specting for: 1) PRPHA approval CO#9 and CO#10; 2)Contractor correction of payroll defiecience | Substantial Completion
3058 | Moca | José N. Gándara | Noefebdo Ramírez | NFC | CMS | Ray Engineers PSC | Moss Construction | 74 | 74 | 0 | 74 | 0 | 896 | 73 | 969 | 8.147% | 940 | 100% | 1999-11-08 | 2002-04-21 | 2002-07-03 | 2002-06-05 | 0 | 0 | CFP-02 | 2000-01-13 | 4671000 | 238289 | 4909289 | 5.101% | 4805897.22 | 0 | 4805897.22 | 97.89% | 12.7027 | 0% | 0 | The close out was not completed because the Contractor not submit to PRPHA the final documents required by the Construction and Management Bureau and the Legal Division of the PRPHA. The solution of this case was referred to Legal Division of the PRPHA. | Substantial Completion
5088 | Ponce | Lirios del Sur | Arturo Acevedo | MJ Consulting | CMS | CSA | Caribe General Constructors | 400 | 400 | 0 | 400 | 0 | 791 | 487 | 1278 | 61.57% | 1267 | 100% | 2009-03-02 | 2011-05-01 | 2012-08-30 | 2012-08-20 | 0 | 0 | CFP | 0 | 16598000 | 2352431.7 | 18950431.7 | 14.17% | 17140589.22 | 0 | 17140589.22 | 90.45% | 3.1675 | 0% | 0 | Project started in march 2009, The contrator finished the instalation of the luminaries on the fence of the west side of the project. Last certification rendered for payment is certification # 35, which is the 50% of retainage. | Substantial Completion
5056 | Guaynabo | Loa Alamos | José González | Municipio de Guaynabo | Klassik | Hernández-Bauzá | Homeca Recycling | 376 | 376 | 0 | 376 | 0 | 549 | 0 | 549 | 0% | 547 | 100% | 2012-09-17 | 2014-03-19 | 2014-03-19 | 2014-03-18 | 0 | 0 | CFP | 0 | 2339000 | -40565.21 | 2298434.79 | -1.734% | 2149223.01 | 0 | 2149223.01 | 93.51% | 1.4548 | 0% | 0 | Project is almost completed. | Substantial Completion
5166 | San Juan | Brisas de Cupey | José M. Paris | SP Management Corp. | CCC-JV | Fracinetti Arquitectos | Pitirre Copnstruction | 184 | 184 | 0 | 184 | 0 | 993 | 127 | 1120 | 12.79% | 1251 | 100% | 2010-02-26 | 2012-11-14 | 2013-03-21 | 2013-07-31 | 0 | 0 | ARRA/CFP | 0 | 15326960 | 1013140.06 | 16340100.06 | 6.61% | 16340100.06 | 0 | 16340100.06 | 100% | 6.7989 | 0% | 0 | The Program Manager is preparing the change order # 10, this CO has time extension by wheater condition and delay in the delivery of the building # 12 to the Contractor. The six building completed and we are waiting for legal RW documents, | Substantial Completion
3070 | Trujillo Alto | Pedro Regalado Díaz | José González | Inn Capital Housing Division Joint Venture | MD | Ray Engineers PSC | José L. Colón | 10 | 10 | 0 | 10 | 0 | 273 | 226 | 499 | 82.78% | 498 | 100% | 2008-04-14 | 2009-01-11 | 2009-08-25 | 2009-08-25 | 0 | 0 | CFP | 0 | 1991000 | 435116 | 2426116 | 21.85% | 2304810.1 | 0 | 2304810.1 | 95% | 49.8 | 0% | 0 | ♦ Repair of Units and Administration Building - The Management Agent has prepared a report about the scope of work and cost to repair units that will be delivered to the residents. Extraordinary Maintenance Office (PHAPR) is working with this item. ♦ Existing post removal - This work will be performed once the AEE connects the project and the Cable TV Company removes its wiring. ♦ Claim of the Contractor Jose Luis Colon - it was assigned to PGES to work with it. | Substantial Completion
3030 | Adjuntas | Villa Valle Verde | Pedro Vega | J.A. Machuca | URS | Jorge L. Roberts, PSC | Venegas Construction | 150 | 150 | 0 | 150 | 0 | 913 | 144 | 1057 | 15.77% | 1743 | 100% | 2001-01-15 | 2003-07-16 | 2003-12-07 | 2005-10-24 | 2007-02-06 | 0 | 0 | 0 | 11829000 | 337235 | 12166235 | 2.851% | 12103923 | 0 | 12103923 | 99.49% | 11.62 | 100% | 0 | These Close out is in process by PGES. | Final Acceptance
3034 | Aguada | Francisco Egipciaco | Noefebdo Ramírez | NFC | CMS | Arq. José Luzunaris | NLL Construction | 100 | 100 | 0 | 100 | 0 | 887 | 0 | 887 | 0% | 819 | 100% | 2000-03-23 | 2002-08-26 | 2002-08-26 | 2002-06-20 | 2002-10-04 | 0 | 0 | 0 | 8107810 | 207539 | 8315349 | 2.56% | 8315349 | 0 | 8315349 | 100% | 8.19 | 100% | 0 | Project Closed | Final Acceptance
5252 | Aguada | Los Robles | Noefebdo Ramírez | NFC | CMS | Joglar & Architects | 422 Corporation | 62 | 62 | 0 | 62 | 0 | 669 | 0 | 669 | 0% | 692 | 100% | 2001-01-18 | 2002-11-17 | 2002-11-17 | 2002-12-11 | 2003-10-02 | 0 | 0 | 0 | 2640000 | -11465 | 2628535 | -0.4343% | 2628535 | 0 | 2628535 | 100% | 11.1613 | 100% | 0 | Project Closed | Final Acceptance
5158 | Aguadilla | La Montaña | Frank Nieves | American Management | URS | Unipro | Caribe Tecno Habitat | 220 | 220 | 0 | 220 | 0 | 895 | 458 | 1353 | 51.17% | 1341 | 100% | 2003-07-28 | 2006-01-07 | 2007-04-10 | 2007-03-30 | 2007-03-30 | 0 | CFP | 0 | 16148000 | 1232941.34 | 17380941.34 | 7.635% | 16890921 | 0 | 16890921 | 97.18% | 6.0955 | 100% | 0 | Project Closed | Final Acceptance
3035 | Aguas Buenas | Vista Alegre | Rubén Cotto | MJ Consulting | URS Caribe | Carlos E. Betancourt | Constructores Gilmar | 74 | 74 | 0 | 74 | 0 | 912 | 752 | 1664 | 82.46% | 1645 | 100% | 2005-06-06 | 2007-12-04 | 2009-12-25 | 2009-12-07 | 2010-09-10 | 0 | Tax Credit 908-2008 | 0 | 6690000 | 2657915 | 9347915 | 39.73% | 8143277.42 | 0 | 8143277.42 | 87.11% | 22.2297 | 100% | 0 | Project Closed | Final Acceptance
3082 | Arecibo | Ramón Marín Solá (Fase II) | Arturo Acevedo | MAS Corporation | CMS | Andrés Hernández | Nogama Construction | 96 | 96 | 0 | 96 | 0 | 612 | 44 | 656 | 7.19% | 626 | 100% | 2000-05-15 | 2002-01-16 | 2002-03-01 | 2002-01-31 | 2002-03-15 | 0 | 0 | 0 | 7837000 | 0 | 7837000 | 0% | 7837000 | 0 | 7837000 | 100% | 6.5208 | 100% | 0 | Project Closed | Final Acceptance
3097 | Arecibo | Trina Padilla de Sanz | Frank Nieves | Cost Control Company, Inc. | ISS Corp | Ray Engineers PSC | Nogama Construction | 240 | 240 | 0 | 240 | 0 | 1278 | 97 | 1375 | 7.59% | 1464 | 100% | 2006-01-09 | 2009-07-09 | 2009-10-14 | 2010-01-12 | 2010-08-16 | 0 | Tax Credit | 0 | 23814529 | 1556413.89 | 25370942.89 | 6.536% | 25198434.68 | 0 | 25198434.68 | 99.32% | 6.1 | 100% | 0 | Project Closed | Final Acceptance
5127 | Arecibo | La Meseta | Pedro Vega | Cost Control Company, Inc. | URS Caribe | Enrique Ruiz & Asoc. | Venegas Construction | 300 | 300 | 0 | 300 | 0 | 1098 | 871 | 1969 | 79.33% | 1947 | 100% | 2005-05-31 | 2008-06-01 | 2010-10-20 | 2010-09-29 | 2011-01-24 | 0 | Tax Credit | 0 | 24161000 | 1903823.57 | 26064823.57 | 7.88% | 26064823.57 | 0 | 26064823.57 | 100% | 6.49 | 100% | 0 | Project Closed. | Final Acceptance
3099 | Arecibo | Antonio Márquez Arbona | Frank Nieves | American Management | Klassik Builders | Enrique Ruiz & Asoc. | Karimar Construction, Inc. | 104 | 104 | 0 | 104 | 0 | 730 | 183 | 913 | 25.07% | 912 | 100% | 2010-03-25 | 2012-03-23 | 2012-09-22 | 2012-09-22 | 2013-04-01 | 0 | ARRA/CFP | 0 | 9085636 | 263361.39 | 9348997.39 | 2.899% | 9223663.18 | 0 | 9223663.18 | 98.66% | 8.7692 | 100% | 0 | In Closing Process. | Final Acceptance
3021 | Arroyo | Isidro Cora | Rubén Cotto | MJ Consulting | MD | GMG Eng. Consultants | Venegas Construction | 150 | 150 | 0 | 150 | 0 | 1095 | 302 | 1397 | 27.58% | 1396 | 100% | 1999-09-27 | 2002-09-25 | 2003-07-24 | 2003-07-24 | 2004-09-30 | 0 | 0 | 0 | 10247000 | 437000 | 10684000 | 4.265% | 10654500 | 0 | 10654500 | 99.72% | 9.3067 | 100% | 0 | The close out documents are under correction process by the Program Manager and General Contractor. | Final Acceptance
3036 | Barceloneta | Antonio Dávila Freytes | José Negrón | MAS Corporation | LMC | Andrés Hernández & Asoc. | Caribe Tecno | 100 | 100 | 0 | 100 | 0 | 904 | 413 | 1317 | 45.69% | 1316 | 100% | 1999-10-15 | 2002-04-05 | 2003-05-23 | 2003-05-23 | 2003-06-30 | 0 | 0 | 0 | 6970000 | 1305876.67 | 8275876.67 | 18.74% | 8275877 | 0 | 8275877 | 100% | 13.16 | 100% | 0 | Project Closed | Final Acceptance
3037 | Barranquitas | Villa Universitaria | Jorge Mercado | MJ Consulting | AVP | GMG Eng. Consultants | Royal & Sun Alliance | 100 | 100 | 0 | 100 | 0 | 540 | 913 | 1453 | 169.1% | 1678 | 100% | 1997-11-25 | 1999-05-18 | 2001-11-16 | 2002-06-30 | 2002-11-12 | 0 | 0 | 0 | 5299000 | 804839 | 6103839 | 15.19% | 6103839 | 0 | 6103839 | 100% | 16.78 | 100% | 0 | Project Closed | Final Acceptance
5093 | Bayamón | Brisas de Bayamón | Arturo Acevedo | Cost Control Company, Inc. | URS Caribe | Edison Avilés Deliz | Omega Engineering | 300 | 300 | 0 | 300 | 0 | 1400 | 1372 | 2772 | 98% | 2518 | 100% | 2002-01-09 | 2005-11-08 | 2009-08-11 | 2008-12-01 | 2010-03-22 | 0 | Tax Credit | 0 | 23965851 | 5030471 | 28996322 | 20.99% | 27007484 | 0 | 27007484 | 93.14% | 8.3933 | 100% | 0 | Project Closed | Final Acceptance
5151 | Bayamón | Sierra Linda | Arturo Acevedo | Martinal Property | URS | Gautier & De Torres | JR Builders | 200 | 200 | 0 | 200 | 0 | 1015 | 1071 | 2086 | 105.5% | 2136 | 100% | 2002-04-15 | 2005-01-23 | 2007-12-30 | 2008-02-19 | 2008-08-08 | 0 | CFP-02 | 0 | 13395440 | 1036113 | 14431553 | 7.735% | 14344606 | 0 | 14344606 | 99.4% | 10.68 | 100% | 0 | Project Closed | Final Acceptance
5096 | Bayamón | La Alhambra | Luis Rodríguez | Cost Control Company, Inc. | LMC | Jorge del Río Arquitectos | Del Valle Group | 96 | 96 | 0 | 96 | 0 | 730 | 236 | 966 | 32.33% | 793 | 100% | 2009-07-28 | 2011-07-27 | 2012-03-19 | 2011-09-29 | 2012-05-17 | 0 | ARRA-CFP | 0 | 9555000 | 752914.59 | 10307914.59 | 7.88% | 10307914.59 | 0 | 10307914.59 | 100% | 8.2604 | 100% | 0 | Project Closed | Final Acceptance
5094 | Bayamón | Las Gardenias | Jorge Mercado | Housing Promoters | AVP/Prann | Gautier & Benítez | Del Valle Group | 164 | 164 | 0 | 164 | 0 | 671 | 302 | 973 | 45.01% | 1033 | 100% | 1997-05-29 | 1999-03-30 | 2000-01-26 | 2000-03-27 | 2000-06-08 | 0 | 0 | 0 | 7117000 | 152286.5 | 7269286.5 | 2.14% | 7234564.4 | 0 | 7234564.4 | 99.52% | 6.2988 | 100% | 0 | Project Closed | Final Acceptance
5138 | Caguas | Villa del Rey (With Take Over Agreement) | Fco. Palacios | MJ Consulting | AVP / Vivonis & Villegas | Guillermety, Ortiz & Asoc. | American Intl. | 100 | 100 | 0 | 100 | 0 | 620 | 165 | 785 | 26.61% | 903 | 100% | 2000-08-04 | 2002-04-15 | 2002-09-27 | 2003-01-24 | 2003-01-24 | 0 | 0 | 0 | 2110081 | 192030 | 2302111 | 9.101% | 2302111 | 0 | 2302111 | 100% | 9.03 | 100% | 0 | Project Closed | Final Acceptance
5066 | Caguas | Turabo Heights | Luis Rodríguez | MJ Consulting | LMC | Andrés Hernández & Asoc. | Del Valle Group | 254 | 254 | 0 | 254 | 0 | 1300 | 471 | 1771 | 36.23% | 1641 | 100% | 2006-01-16 | 2009-08-07 | 2010-11-21 | 2010-07-15 | 2010-09-30 | 0 | Tax Credit | 0 | 25534940 | 2776195 | 28311135 | 10.87% | 28311135.04 | 0 | 28311135.04 | 100% | 6.4606 | 100% | 0 | Project Closed | Final Acceptance
3038 | Camuy | M. Román Adames | Arturo Acevedo | NFC | CMS | Gutierez & Gutierrez | Pintores Metropolitanos | 64 | 64 | 0 | 64 | 0 | 396 | 491 | 887 | 124% | 1101 | 100% | 1997-05-19 | 1998-06-18 | 1999-10-22 | 2000-05-24 | 2001-03-19 | 0 | 0 | 0 | 3600000 | 403566 | 4003566 | 11.21% | 4003566 | 0 | 4003566 | 100% | 17.2031 | 100% | 0 | Project Closed | Final Acceptance
3053 | Canóvanas | Jesús T. Piñero | Katherine Vázquez | Peregrine Group Inc. | Klassik Builders | Ray Engineers, PSC | LPC&D | 124 | 124 | 0 | 124 | 0 | 913 | 237 | 1150 | 25.96% | 1149 | 100% | 2009-07-15 | 2012-01-13 | 2012-09-06 | 2012-09-06 | 2013-06-30 | 0 | ARRA/CFP | 0 | 16575250 | 2355453 | 18930703 | 14.21% | 18827830.65 | 0 | 18827830.65 | 99.46% | 9.2661 | 100% | 0 | The following items are pending: comments from payroll non-compliance issues, to submit certification # 38. | Final Acceptance
5082 | Carolina | Alturas de Country Club | José González | PROMMA | URS | Jorge del Rio | North Construction | 72 | 72 | 0 | 72 | 0 | 548 | 373 | 921 | 68.07% | 893 | 100% | 2004-09-27 | 2006-03-28 | 2007-04-05 | 2007-03-09 | 2009-04-24 | 0 | CFP | 0 | 5977756.15 | 1066756.51 | 7044512.66 | 17.85% | 7044512.67 | 0 | 7044512.67 | 100% | 12.4028 | 100% | 0 | Project Closed | Final Acceptance
5057 | Carolina | Los Mirtos | José González | Cost Control | CCC-JV | Hernández - Bauzá | Del Valle group | 144 | 144 | 0 | 144 | 0 | 545 | 121 | 666 | 22.2% | 690 | 100% | 2010-11-08 | 2012-05-05 | 2012-09-03 | 2012-09-28 | 2013-07-17 | 0 | Tax Credit | 0 | 14841000 | 272983 | 15113983 | 1.839% | 14923649 | 0 | 14923649 | 98.74% | 4.7917 | 100% | 0 | Project Closed | Final Acceptance
5076 | Carolina | Catañito Gardens | Luis Rodríguez | Inn Capital Housing Division Joint Venture | MD | URS Caribe | RBC Construction | 124 | 124 | 0 | 124 | 0 | 730 | 937 | 1667 | 128.4% | 0 | 100% | 2006-02-08 | 2008-02-07 | 2010-09-01 | 2006-02-08 | 2011-03-28 | 0 | Tax Credit 908-2008 | 0 | 13938100 | 819027.62 | 14757127.62 | 5.876% | 14757127.62 | 0 | 14757127.62 | 100% | 0 | 100% | 0 | Project Closed | Final Acceptance
5102 | Carolina | El Coral | José A. González | Cost Control Company, Inc. | URS Caribe | Francinetti Arquitectos | Orion Contractors | 100 | 100 | 0 | 100 | 0 | 913 | 1268 | 2181 | 138.9% | 2180 | 100% | 2006-01-09 | 2008-07-09 | 2011-12-29 | 2011-12-29 | 2012-06-29 | 0 | Tax Credit | 0 | 9718830 | 1196730.19 | 10915560.19 | 12.31% | 10915560.19 | 0 | 10915560.19 | 100% | 21.8 | 100% | 0 | Project Closed | Final Acceptance
5101 | Carolina | La Esmeralda | Luis Rodríguez | Inn Capital Housing Division Joint Venture | BMA | Carlos E. Betancourt | Construction Zone Corp. | 84 | 84 | 0 | 84 | 0 | 549 | 65 | 614 | 11.84% | 612 | 100% | 2008-12-22 | 2010-06-23 | 2010-08-27 | 2010-08-26 | 2010-12-10 | 0 | Tax Credit | 0 | 4462898 | 32305.97 | 4495203.97 | 0.7239% | 4495203.77 | 0 | 4495203.77 | 100% | 7.2857 | 100% | 0 | Project Closed | Final Acceptance
5075 | Carolina | Lagos de Blasina | José A. González | Cost Control Company, Inc. | CMS | Guillermety, Ortiz & Asoc. (DG3A Design Group, PSC is actually supervising the works) | Mejia Construction | 240 | 240 | 0 | 240 | 0 | 800 | 289 | 1089 | 36.12% | 1077 | 100% | 2009-06-08 | 2011-08-16 | 2012-05-31 | 2012-05-20 | 2012-09-20 | 0 | Tax Credit | 0 | 15411000 | 809595.16 | 16220595.16 | 5.253% | 16220595.16 | 0 | 16220595.16 | 100% | 4.4875 | 100% | 0 | Project Closed | Final Acceptance
5212 | Carolina | Roberto Clemente | Luz Acevedo | SEG | CMS | Jorge del Río | North Connstruction | 126 | 126 | 0 | 126 | 0 | 730 | 242 | 972 | 33.15% | 1038 | 100% | 2004-08-09 | 2006-08-08 | 2007-04-07 | 2007-06-13 | 2008-02-22 | 0 | 0 | 0 | 11135000 | 586931 | 11721931 | 5.271% | 11610417 | 0 | 11610417 | 99.05% | 8.2381 | 100% | 0 | Project Closed | Final Acceptance
3102 | Cataño | Juana Matos I (Fase I) | Luz Acevedo | A & M | AVP / Erwin Rodriguez | Roca & Associates | Quintero Const. | 212 | 212 | 0 | 212 | 0 | 892 | 744 | 1636 | 83.41% | 1628 | 100% | 1997-05-29 | 1999-11-06 | 2001-11-19 | 2001-11-12 | 2002-07-22 | 0 | 0 | 0 | 11640000 | 424857 | 12064857 | 3.65% | 11679790.2 | 0 | 11679790.2 | 96.81% | 7.6792 | 100% | 0 | Project Closed | Final Acceptance
3102 | Cataño | Juana Matos I (Fase II) | Pedro Vega | A & M | BMA | Roca & Associates | Rodríguez & del Valle | 188 | 188 | 0 | 188 | 0 | 1150 | 141 | 1291 | 12.26% | 1179 | 100% | 2002-09-30 | 2005-11-22 | 2006-04-12 | 2005-12-22 | 2006-01-12 | 0 | 0 | 0 | 14243000 | 831198 | 15074198 | 5.836% | 15074198 | 0 | 15074198 | 100% | 6.2713 | 100% | 0 | Project Closed | Final Acceptance
5037 | Cataño | Jardines de Cataño | Pedro Vega | Martinal Property | CMS | Interplan | Francisco Levy Hijo Inc. | 180 | 180 | 0 | 180 | 0 | 810 | 369 | 1179 | 45.56% | 1175 | 100% | 2004-03-22 | 2006-06-09 | 2007-06-13 | 2007-06-10 | 2007-06-14 | 0 | CFP | 0 | 14181600 | 1145235.46 | 15326835.46 | 8.076% | 15326835.44 | 0 | 15326835.44 | 100% | 6.5278 | 100% | 0 | Project Closed | Final Acceptance
3083 | Cayey | Luis Muñoz Morales | Luz Acevedo | MJ Consulting | AVP | Istra Hernández | I Melendez | 280 | 280 | 0 | 280 | 0 | 913 | 416 | 1329 | 45.56% | 1342 | 100% | 1997-08-01 | 2000-01-30 | 2001-03-21 | 2001-04-04 | 2001-09-19 | 0 | 0 | 0 | 12895800 | 452279 | 13348079 | 3.507% | 13348079 | 0 | 13348079 | 100% | 4.7929 | 100% | 0 | Project Close | Final Acceptance
5127 | Cayey | Jardines de Montellanos | Rubén Cotto | Cost Control | CCC-JV | Hernández - Bauzá | Constructora I. Meléndez | 130 | 130 | 0 | 130 | 0 | 836 | 307 | 1143 | 36.72% | 1142 | 100% | 2009-09-30 | 2012-01-13 | 2012-11-15 | 2012-11-15 | 0 | 0 | Tax Credit | 0 | 17226575.94 | 2771225.7 | 19997801.64 | 16.09% | 19987858.29 | 0 | 19987858.29 | 99.95% | 8.7846 | 100% | 0 | Project Closed | Final Acceptance
5157 | Cayey | Brisas de Cayey | Rubén Cotto | MJ Consulting | MD | Ray Engineers PSC | Three O. Construction | 210 | 210 | 0 | 210 | 0 | 1491 | 1200 | 2691 | 80.48% | 1887 | 100% | 2005-01-12 | 2009-02-10 | 2012-05-25 | 2010-03-14 | 2010-04-06 | 0 | Tax Credit | 0 | 24696653 | 5611698 | 30308351 | 22.72% | 30308351 | 0 | 30308351 | 100% | 8.9857 | 100% | 0 | Project Closed | Final Acceptance
3040 | Ciales | Fernando Sierra Berdecía | José Negrón | MAS Corporation | LMC | Luis Flores & Asociados | Constructores Gilmar | 100 | 100 | 0 | 100 | 0 | 780 | 165 | 945 | 21.15% | 983 | 100% | 2001-08-21 | 2003-10-09 | 2004-03-22 | 2004-04-30 | 2006-05-16 | 0 | 0 | 0 | 9285527 | 414901 | 9700428 | 4.468% | 9700428 | 0 | 9700428 | 100% | 9.83 | 100% | 0 | Project Closed | Final Acceptance
3041 | Cidra | Práxedes Santiago | Rubén Cotto | MJ Consulting | URS | Carlos E. Betancourt | DGM Engineering | 124 | 124 | 0 | 124 | 0 | 912 | 901 | 1813 | 98.79% | 2235 | 100% | 2005-04-28 | 2007-10-26 | 2010-04-14 | 2011-06-11 | 2012-03-09 | 0 | Tax Credit | 0 | 11616773 | 3604885 | 15221658 | 31.03% | 14100168 | 0 | 14100168 | 92.63% | 18.0242 | 100% | 0 | Project Closed | Final Acceptance
3043 | Dorado | El Dorado | Frank Nieves | Cost Control Company, Inc. | BMA | Guillermety, Ortiz & Asoc. | Torres & Colón, Inc | 37 | 37 | 0 | 37 | 0 | 430 | 180 | 610 | 41.86% | 666 | 100% | 2007-06-04 | 2008-08-06 | 2009-02-02 | 2009-03-31 | 2009-04-14 | 0 | Tax Credit | 0 | 3991977 | 753900 | 4745877 | 18.89% | 4745877 | 0 | 4745877 | 100% | 18 | 100% | 0 | Project Closed | Final Acceptance
3095 | Fajardo | Pedro Rosario Nieves | José M. Paris Escalera | Inn Capital Housing Division Joint Venture | CMS | Carlos E. Betancourt | Nogama Construction | 168 | 168 | 0 | 168 | 0 | 915 | 27.5 | 942.5 | 3.005% | 904 | 100% | 2008-12-22 | 2011-06-24 | 2011-07-21 12:00 | 2011-06-14 | 2011-09-06 | 0 | Tax Credit | 0 | 16474000 | -148386.07 | 16325613.93 | -0.9007% | 16325613.93 | 0 | 16325613.93 | 100% | 5.381 | 100% | 0 | Project Closed | Final Acceptance
5021 | Fajardo | Puerto Real | Germán Acevedo | A & M | URS | René Vélez Marichal | Quality Const. | 100 | 100 | 0 | 100 | 0 | 945 | 282 | 1227 | 29.84% | 1124 | 100% | 2001-01-22 | 2003-08-24 | 2004-06-01 | 2004-02-20 | 2004-04-20 | 0 | 0 | 0 | 8220000 | 910990 | 9130990 | 11.08% | 9130990 | 0 | 9130990 | 100% | 11.24 | 100% | 0 | Project Closed | Final Acceptance
5204 | Fajardo | Valle Puerto Real | Germán Acevedo | A & M | URS | Enrique Ruiz & Assoc. | Quality Const. | 75 | 75 | 0 | 75 | 0 | 945 | 181 | 1126 | 19.15% | 1129 | 100% | 2001-01-02 | 2003-08-04 | 2004-02-01 | 2004-02-05 | 2004-05-14 | 0 | 0 | 0 | 6316000 | 725553 | 7041553 | 11.49% | 7041553 | 0 | 7041553 | 100% | 15.0533 | 100% | 0 | Project Closed | Final Acceptance
5176 | Fajardo | Santiago Veve Calzada | Robert H. Cole | A & M | BMA | Ramón W. Costacamps | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 730 | 214 | 944 | 29.32% | 906 | 100% | 2004-06-21 | 2006-06-20 | 2007-01-20 | 2006-12-14 | 2007-01-18 | 0 | 0 | 0 | 8559000 | 558385.32 | 9117385.32 | 6.524% | 9117385.32 | 0 | 9117385.32 | 100% | 9.06 | 100% | 0 | Project Closed | Final Acceptance
5183 | Guánica | Jardines de Guánica | Noefebdo Ramírez | JA Machuca | CCC-JV | Donato Design Development | RAMA Construction | 70 | 70 | 0 | 70 | 0 | 732 | 89 | 821 | 12.16% | 794 | 100% | 2009-11-23 | 2011-11-24 | 2012-02-21 | 2012-01-26 | 2012-01-31 | 0 | ARRA/CFP | 0 | 5499000 | 487497.62 | 5986497.62 | 8.865% | 5986498 | 0 | 5986498 | 100% | 11.3429 | 100% | 0 | Project Closed | Final Acceptance
3084 | Guánica | Luis Muñoz Rivera | Noefebdo Ramírez | Cost Control Company, Inc. | CCC-JV | Behar & Ybarra Associates, PSC | F & R Construction Group, Inc. | 124 | 124 | 0 | 124 | 0 | 485 | 423 | 908 | 87.22% | 970 | 100% | 2009-12-14 | 2011-04-12 | 2012-06-08 | 2012-08-10 | 2013-04-18 | 0 | Tax Credit | 0 | 9009000 | 589263.71 | 9598263.71 | 6.541% | 9590758.22 | 0 | 9590758.22 | 99.92% | 7.8226 | 100% | 0 | Project Closed | Final Acceptance
3085 | Guayama | Luis Palés Matos | Rubén Cotto | MJ Consulting | MD (Grupo C) | Guillermety, Ortiz & Asoc. | Héctor M. Valera Inc. | 298 | 298 | 0 | 298 | 0 | 1130 | 0 | 1130 | 0% | 1375 | 100% | 2002-03-25 | 2005-04-27 | 2005-04-27 | 2005-12-29 | 2006-01-03 | 0 | 0 | 0 | 22466000 | 0 | 22466000 | 0% | 22466000 | 0 | 22466000 | 100% | 4.6141 | 100% | 0 | Project Closed | Final Acceptance
5048 | Guayama | San Antonio Carioca | Jorge Mercado | MJ Consulting | MD (Grupo C) | DDHK | Constructora I. Melendez | 200 | 200 | 0 | 200 | 0 | 900 | 568 | 1468 | 63.11% | 1537 | 100% | 2004-03-15 | 2006-08-31 | 2008-03-21 | 2008-05-30 | 2008-07-30 | 0 | Tax Credit | 0 | 18456662 | 1765148 | 20221810 | 9.564% | 20221810 | 0 | 20221810 | 100% | 7.685 | 100% | 0 | Project Closed | Final Acceptance
5131 | Humacao | Jardines de Oriente | José A. González | Cost Control | CCC-JV | GMG Engineering Conslutants PSC | Ossam Construction | 88 | 88 | 0 | 88 | 0 | 365 | 242 | 607 | 66.3% | 937 | 100% | 2010-05-31 | 2011-05-30 | 2012-01-27 | 2012-12-23 | 2012-07-20 | 0 | Tax Credit | 0 | 5939925 | 394882.55 | 6334807.55 | 6.648% | 6334807.55 | 0 | 6334807.55 | 100% | 10.6477 | 100% | 0 | Project Closed | Final Acceptance
5020 | Humacao | Pedro J. Palou | Fco. Palacios | MJ Consulting | URS | R & del Valle | R & del Valle | 150 | 150 | 0 | 150 | 0 | 1095 | 180 | 1275 | 16.44% | 1145 | 100% | 1999-09-27 | 2002-09-25 | 2003-03-24 | 2002-11-15 | 2002-12-20 | 0 | 0 | 0 | 10968000 | 86049 | 11054049 | 0.7845% | 11054049 | 0 | 11054049 | 100% | 7.6333 | 100% | 0 | Project closed. | Final Acceptance
3094 | Humacao | Padre Rivera (Fase I) | Germán Acevedo | MJ Consulting | BMA | Yañez, Mayol & Asoc. | J R Builders | 128 | 128 | 0 | 128 | 0 | 840 | 731 | 1571 | 87.02% | 1548 | 100% | 1997-10-20 | 2000-02-06 | 2002-02-06 | 2002-01-15 | 2002-02-01 | 0 | 0 | 0 | 6625000 | 386337.2 | 7011337.2 | 5.832% | 7011337 | 0 | 7011337 | 100% | 12.0938 | 100% | 0 | Project Closed | Final Acceptance
3094 | Humacao | Padre Rivera (Fase II) | Jorge Mercado | MJ Consulting | BMA | Yañez & Mayol | Jafer Construction | 132 | 132 | 0 | 132 | 0 | 790 | 299 | 1089 | 37.85% | 861 | 100% | 2004-11-10 | 2007-01-08 | 2007-11-03 | 2007-03-21 | 2008-03-12 | 0 | 0 | 0 | 10199820 | 1471265 | 11671085 | 14.42% | 11237717 | 0 | 11237717 | 96.29% | 6.5227 | 100% | 0 | Project Closed | Final Acceptance
3048 | Jayuya | La Montaña | Pedro Vega | MAS Corporation | URS | OPQ-Pablo Quiñonez | Orama Const. | 100 | 100 | 0 | 100 | 0 | 780 | 128 | 908 | 16.41% | 1026 | 100% | 2000-10-23 | 2002-12-11 | 2003-04-18 | 2003-08-15 | 2004-04-26 | 0 | 0 | 0 | 8790000 | 208826 | 8998826 | 2.376% | 8998826 | 0 | 8998826 | 100% | 10.26 | 100% | 0 | Project Closed | Final Acceptance
5064 | Juncos | Colinas de Magnolia | Iván Blanco | MJ Consulting | BMA | Edison Avilés Deliz | Quality Construction | 148 | 148 | 0 | 148 | 0 | 840 | 614 | 1454 | 73.1% | 1201 | 100% | 2004-11-08 | 2007-02-25 | 2008-10-31 | 2008-02-22 | 2008-04-04 | 0 | CFP | 0 | 13860000 | 854562 | 14714562 | 6.166% | 14438155 | 0 | 14438155 | 98.12% | 8.1149 | 100% | 0 | Project Closed | Final Acceptance
3093 | Juncos | Narciso Varona I | Rubén Cotto | MJ Consulting | ISS | DG3A | Torres & Colón, Inc | 88 | 88 | 0 | 88 | 0 | 600 | 199 | 799 | 33.17% | 798 | 100% | 2009-05-29 | 2011-01-18 | 2011-08-05 | 2011-08-05 | 0 | 0 | ARRA/CFP | 0 | 9879114 | 196304 | 10075418 | 1.987% | 10058405.83 | 0 | 10058405.83 | 99.83% | 9.0682 | 100% | 0 | Project Closed | Final Acceptance
5226 | Las Marías | Jardines de las Marías | Arturo Acevedo | NFC | CMS | José L. Irizarry & Assoc. | Lebrón & Assoc. | 55 | 55 | 0 | 55 | 0 | 730 | 32 | 762 | 4.384% | 766 | 100% | 2001-02-27 | 2003-02-26 | 2003-03-30 | 2003-04-04 | 2003-10-03 | 0 | 0 | 0 | 4156000 | 71269 | 4227269 | 1.715% | 4227269 | 0 | 4227269 | 100% | 13.9273 | 100% | 0 | Project Closed | Final Acceptance
5090 | Las Piedras | Jardines de Judely | Iván Blanco | MJ Consulting | URS | René Acosta Ingenieros | Gilmar Roofing & Painting | 32 | 32 | 0 | 32 | 0 | 365 | 118 | 483 | 32.33% | 555 | 100% | 2005-04-04 | 2006-04-03 | 2006-07-30 | 2006-10-11 | 2006-11-02 | 0 | Tax Credit | 0 | 3481720 | 109596.22 | 3591316.22 | 3.148% | 3573356 | 0 | 3573356 | 99.5% | 17.3438 | 100% | 0 | Project Closed | Final Acceptance
5132 | Loíza | Yuquiyú | Luz Acevedo | A & M | BMA | Roca, González Villamil | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 945 | 60 | 1005 | 6.349% | 754 | 100% | 2001-01-22 | 2003-08-24 | 2003-10-23 | 2003-02-15 | 2003-03-21 | 0 | 0 | 0 | 8644000 | 611853 | 9255853 | 7.078% | 9255853.0708 | 0 | 9255853.0708 | 100% | 7.54 | 100% | 0 | Project Closed | Final Acceptance
5186 | Luquillo | Yuquiyú II | Luz Acevedo | Inn Capital Housing Division Joint Venture | BMA | Enrique Ruiz & Asoc. | Unique Builders | 70 | 70 | 0 | 70 | 0 | 730 | 299 | 1029 | 40.96% | 1092 | 100% | 2006-02-15 | 2008-02-14 | 2008-12-09 | 2009-02-11 | 2009-06-09 | 0 | Tax Credit | 0 | 6964727 | 157419 | 7122146 | 2.26% | 6424134.91 | 0 | 6424134.91 | 90.2% | 15.6 | 100% | 0 | Project Closed | Final Acceptance
3056 | Maricao | Juan Ferrer | Noefebdo Ramírez | J. A. Machuca | NFC | René Batista & Assoc. | Comas & Comas | 30 | 30 | 0 | 30 | 0 | 420 | 251 | 671 | 59.76% | 610 | 100% | 2000-08-02 | 2001-09-25 | 2002-06-03 | 2002-04-04 | 2002-04-30 | 0 | 0 | 0 | 2210000 | 178940 | 2388940 | 8.097% | 2388940 | 0 | 2388940 | 100% | 20.3333 | 100% | 0 | Project Closed | Final Acceptance
3057 | Maunabo | Carmen Vda. Martorell (take over agreement) | Rubén Cotto | AVP | AVP | Rene Batista | American Intl. | 50 | 50 | 0 | 50 | 0 | 375 | 327 | 702 | 87.2% | 703 | 100% | 2000-08-18 | 2001-08-27 | 2002-07-20 | 2002-07-22 | 2005-06-02 | 0 | 0 | 0 | 1308221 | 116706 | 1424927 | 8.921% | 1424927 | 0 | 1424927 | 100% | 14.06 | 100% | 0 | Project Closed | Final Acceptance
5126 | Maunabo | Villa Navarro | Rubén Cotto | MJ Consulting | MD | José L. Irizarry & Assoc. | Inversiones OLPERI | 101 | 101 | 0 | 101 | 0 | 907 | 335 | 1242 | 36.93% | 1241 | 100% | 2000-01-24 | 2002-07-18 | 2003-06-18 | 2003-06-18 | 2003-06-18 | 0 | 0 | 0 | 6745000 | 238239 | 6983239 | 3.532% | 6983239 | 0 | 6983239 | 100% | 12.2871 | 100% | 0 | Project Closed | Final Acceptance
5012 | Mayagüez | Ext. Sábalos Gardens | Noefebdo Ramírez | Inn Capital Housing Division Joint Venture | URS Caribe / AVP | Joint Venture | Venegas Construction | 300 | 300 | 0 | 300 | 0 | 1281 | 690 | 1971 | 53.86% | 1963 | 100% | 2005-05-16 | 2008-11-16 | 2010-10-07 | 2010-09-30 | 2011-04-29 | 0 | Tax Credit 908-2008 | 0 | 28259000 | 14189.7 | 28273189.7 | 0.05021% | 29677970 | 0 | 29677970 | 105% | 6.5433 | 100% | 0 | Project Closed | Final Acceptance
4004 | Mayagüez | Sábalos Gdns. | Arturo Acevedo | Zeta | CMS | Héctor Rodríguez Amezquita | Caribe Tecno | 140 | 140 | 0 | 140 | 0 | 881 | 24 | 905 | 2.724% | 900 | 100% | 1999-11-15 | 2002-04-13 | 2002-05-07 | 2002-05-03 | 2002-11-06 | 0 | 0 | 0 | 11790000 | -294361.74 | 11495638.26 | -2.497% | 11495638 | 0 | 11495638 | 100% | 6.4286 | 100% | 0 | Project Closed | Final Acceptance
4006 | Mayagüez | Cuesta las Piedras | Arturo Acevedo | Zeta | CMS | García Cabot | RC Enginering | 142 | 142 | 0 | 142 | 0 | 1093 | 0 | 1093 | 0% | 907 | 100% | 2000-02-10 | 2003-02-06 | 2003-02-06 | 2002-08-05 | 2002-11-21 | 0 | 0 | 0 | 10673000 | 158657 | 10831657 | 1.487% | 10831657 | 0 | 10831657 | 100% | 6.3873 | 100% | 0 | Se aprobó el "close out". Contratista no cobró el total del contrato debido a ajustes deductivos recomendados por el "Program Manager"C.M. Services. | Final Acceptance
4008 | Mayagüez | Yagüez | Arturo Acevedo | ZETA | CMS | GDA Ing. Consultores | NLL Construction | 200 | 200 | 0 | 200 | 0 | 1399 | 0 | 1399 | 0% | 1177 | 100% | 2000-05-22 | 2004-03-20 | 2004-03-20 | 2003-08-12 | 2003-10-06 | 0 | 0 | 0 | 16799671 | -872594 | 15927077 | -5.194% | 15927077 | 0 | 15927077 | 100% | 5.885 | 100% | 0 | Project Closed | Final Acceptance
4005 | Mayagüez | Marini Farm | Frank Nieves | Zeta | BMA | CSA Architects | Empresas Toledo | 100 | 100 | 0 | 100 | 0 | 218 | 50 | 268 | 22.94% | 247 | 100% | 2004-05-12 | 2004-12-15 | 2005-02-03 | 2005-01-14 | 2005-09-07 | 0 | 0 | 0 | 845900 | 30508 | 876408 | 3.607% | 876408 | 0 | 876408 | 100% | 2.47 | 100% | 0 | Project Closed | Final Acceptance
5005 | Mayagüez | Mar y Sol | Noefebdo Ramírez | Zeta | CMS | Arq. Amadeo Pino | RC Enginering | 124 | 124 | 0 | 124 | 0 | 1055 | 14 | 1069 | 1.327% | 1068 | 100% | 2001-01-22 | 2003-12-12 | 2003-12-26 | 2003-12-26 | 2004-05-26 | 0 | 0 | 0 | 10513000 | 269417 | 10782417 | 2.563% | 10782417 | 0 | 10782417 | 100% | 8.6129 | 100% | 0 | Project Closed | Final Acceptance
5133 | Naguabo | Villas del Río | Félix Ortiz | MJ Consulting | MD | N/A | DGM Engineering | 100 | 100 | 0 | 100 | 0 | 730 | 906 | 1636 | 124.1% | 1640 | 100% | 2006-02-15 | 2008-02-14 | 2010-08-08 | 2010-08-13 | 2011-06-27 | 0 | Tax Credit | 0 | 11008930 | 1560851 | 12569781 | 14.18% | 12120952 | 0 | 12120952 | 96.43% | 16.4 | 100% | 0 | Project Closed | Final Acceptance
3063 | Peñuela | Los Flamboyanes | Noefebdo Ramírez | J.A. Machuca | MD | Fuertes, La Font & Asoc. | St. Paul Surety | 24 | 24 | 0 | 24 | 0 | 345 | 502 | 847 | 145.5% | 845 | 100% | 2003-04-15 | 2004-03-24 | 2005-08-08 | 2005-08-07 | 2005-09-26 | 0 | 0 | 0 | 1235996 | 568973 | 1804969 | 46.03% | 1804969 | 0 | 1804969 | 100% | 35.2083 | 100% | 0 | Project Closed | Final Acceptance
1014 | Ponce | Aristides Chavier | Noefebdo Ramírez | MJ Consulting | CCC Joint Venture | Unipro | Del Valle Group | 480 | 480 | 0 | 480 | 0 | 1464 | 552 | 2016 | 37.7% | 2003 | 100% | 2005-08-01 | 2009-08-03 | 2011-02-06 | 2011-01-25 | 2011-08-16 | 0 | Tax Credit 908-2008 | 0 | 43792000 | 2045988.7 | 45837988.7 | 4.672% | 45837989 | 0 | 45837989 | 100% | 4.1729 | 100% | 0 | Project Closed | Final Acceptance
5088 | Ponce | Lirios del Sur | Arturo Acevedo | J.A. Machuca | CMS | CSA Architects | Omega Engineering | 238 | 238 | 0 | 238 | 0 | 730 | 340 | 1070 | 46.58% | 1083 | 100% | 2003-02-12 | 2005-02-10 | 2006-01-16 | 2006-01-30 | 2006-04-12 | 0 | 0 | 0 | 18140000 | 570661 | 18710661 | 3.146% | 18710661 | 0 | 18710661 | 100% | 4.5504 | 100% | 0 | Project Closed | Final Acceptance
1001 | Ponce | Ponce de León ( Take Over Agreement) Fase I | José González | J. A. Machuca | MD | Interplan | American Intl. | 168 | 168 | 0 | 168 | 0 | 732 | 171 | 903 | 23.36% | 862 | 100% | 2000-08-28 | 2002-08-29 | 2003-02-16 | 2003-01-07 | 2003-01-30 | 0 | 0 | 0 | 10990000 | 512271 | 11502271 | 4.661% | 11447321.14 | 0 | 11447321.14 | 99.52% | 5.131 | 100% | 0 | Project Closed | Final Acceptance
1001 | Ponce | Ponce de León (Fase II) | Noefebdo Ramírez | MJ Consulting | BMA | Interplan | Constructora I. Meléndez | 132 | 132 | 0 | 132 | 0 | 730 | 748 | 1478 | 102.5% | 1442 | 100% | 2005-01-10 | 2007-01-09 | 2009-01-26 | 2008-12-22 | 2009-03-31 | 0 | Tax Credit 908-2008 | 0 | 13680284 | 787807 | 14468091 | 5.759% | 14448030 | 0 | 14448030 | 99.86% | 10.9242 | 100% | 0 | Project Closed | Final Acceptance
1002 | Ponce | Santiago Iglesias (Fase I) | Noefebdo Ramírez | Zeta | CMS | CSA | Ferrovial & Agroman | 160 | 160 | 0 | 160 | 0 | 487 | 505 | 992 | 103.7% | 1791 | 100% | 1997-10-28 | 1999-02-26 | 2000-07-15 | 2002-09-23 | 2002-11-02 | 0 | 0 | 0 | 9445984 | 580020 | 10026004 | 6.14% | 9993950 | 0 | 9993950 | 99.68% | 11.1937 | 100% | 0 | Project Closed | Final Acceptance
1016 | Ponce | Rafael López Nussa | Noefebdo Ramírez | MJ Consulting | BMA | URS Caribe | Del Valle Group | 404 | 404 | 0 | 404 | 0 | 1464 | 369 | 1833 | 25.2% | 1832 | 100% | 2004-10-25 | 2008-10-27 | 2009-10-31 | 2009-10-31 | 2010-06-16 | 0 | Tax Credit 908-2008 | 0 | 38744000 | 738951.13 | 39482951.13 | 1.907% | 39482951.13 | 0 | 39482951.13 | 100% | 4.5347 | 100% | 0 | Project Closed | Final Acceptance
1003 | Ponce | Caribe | Rubén Cotto | J.A. Machuca | MD | Lombardo Pérez | Caribe General Constructors | 116 | 116 | 0 | 116 | 0 | 720 | 358.4 | 1078.4 | 49.78% | 1192 | 100% | 2002-12-01 | 2004-11-19 | 2005-11-12 09:36 | 2006-03-07 | 2006-06-07 | 0 | 0 | 0 | 11468000 | 1539402.23 | 13007402.23 | 13.42% | 13007402 | 0 | 13007402 | 100% | 10.2759 | 100% | 0 | Project Closed | Final Acceptance
5022 | Ponce | La Ceiba | Rubén Cotto | MJ Consulting | BMA | Ray Engineers PSC | Jafer Construction | 300 | 300 | 0 | 300 | 0 | 1281 | 283 | 1564 | 22.09% | 1514 | 100% | 2004-10-11 | 2008-04-13 | 2009-01-21 | 2008-12-03 | 2009-01-30 | 0 | Tax Credit | 0 | 29600820 | 1001464.91 | 30602284.91 | 3.383% | 30602284.91 | 0 | 30602284.91 | 100% | 5.0467 | 100% | 0 | Project Closed | Final Acceptance
5095 | Ponce | Las Terrazas | Rubén Cotto | AVP | ISS Corp. | Méndez, Brunner, Badillo & Associates | Homeca Recycling Center Co., Inc. | 100 | 100 | 0 | 100 | 0 | 365 | 0 | 365 | 0% | 344 | 100% | 2009-07-28 | 2010-07-27 | 2010-07-27 | 2010-07-07 | 2010-07-27 | 0 | Mixed Fund | 0 | 1085000 | 0 | 1085000 | 0% | 918124.83 | 0 | 918124.83 | 84.62% | 3.44 | 100% | 0 | Se entregaron los documentos de cierre, pero aun le falta por cobrar al contratista la Cert # 8 - Parcial (10/Agosto/10) $ 36,954.06 y Cert.#10 - Retenido Final (22/Oct/10) $108,500.00, para un Totasl de $145,454.06, mas reclamacion de intereses por pago tardio. Alega el contratista que le han informado de finanzas que los fondos estan congelados, pero no le han explicado razon. | Final Acceptance
1002 | Ponce | Santiago Iglesias (Fase II) | Noefebdo Ramírez | Individual Management | Klassik Builders | CSA | Jafer Construction | 120 | 120 | 0 | 120 | 0 | 790 | 66 | 856 | 8.354% | 855 | 100% | 2009-06-15 | 2011-08-13 | 2011-10-18 | 2011-10-18 | 2012-01-26 | 0 | ARRA | 0 | 14498820 | 637269.47 | 15136089.47 | 4.395% | 15136089.47 | 0 | 15136089.47 | 100% | 7.125 | 100% | 0 | Project Closed | Final Acceptance
3066 | Río Grande | José H. Ramírez | Luz Acevedo | A & M | AVP / ORAM | Raúl Feliciano & Asoc. | J R Builders | 80 | 80 | 0 | 80 | 0 | 540 | 317 | 857 | 58.7% | 853 | 100% | 2000-03-29 | 2001-09-19 | 2002-08-02 | 2002-07-30 | 2002-11-15 | 0 | 0 | 0 | 3404949 | 226802 | 3631751 | 6.661% | 3631751 | 0 | 3631751 | 100% | 10.6625 | 100% | 0 | Project Closed | Final Acceptance
5145 | San Germán | Manuel F. Rossy | Frank Nieves | Municipio de San Germán | MD | Unipro | Cap Con Inc. | 101 | 101 | 0 | 101 | 0 | 732 | 84 | 816 | 11.48% | 815 | 100% | 2009-06-22 | 2011-06-23 | 2011-09-15 | 2011-09-15 | 2011-12-31 | 0 | CFP/ARRA | 0 | 10316000 | 610969.8 | 10926969.8 | 5.923% | 10908277 | 0 | 10908277 | 99.83% | 8.0693 | 100% | 0 | Project Closed | Final Acceptance
5035 | San Juan | Villa Esperanza | Luz Acevedo | 0 | LMC | Guillermety, Ortiz & Asoc. | Del Valle Group | 300 | 300 | 0 | 300 | 0 | 1130 | 233 | 1363 | 20.62% | 1323 | 100% | 2003-06-18 | 2006-07-21 | 2007-03-11 | 2007-01-31 | 2007-03-30 | 0 | CFP | 0 | 19819000 | 1078350.46 | 20897350.46 | 5.441% | 20897350.46 | 0 | 20897350.46 | 100% | 4.41 | 100% | 0 | Project Closed | Final Acceptance
5077 | San Juan | La Rosa | Jorge Mercado | AUTO ADM. | LMC | García Joglar & Arq. | DGM Engineers | 52 | 52 | 0 | 52 | 0 | 730 | 270 | 1000 | 36.99% | 984 | 100% | 2000-10-02 | 2002-10-01 | 2003-06-28 | 2003-06-13 | 2004-07-19 | 0 | 0 | 0 | 4491000 | 510039 | 5001039 | 11.36% | 5001039 | 0 | 5001039 | 100% | 18.9231 | 100% | 0 | Project Closed | Final Acceptance
5026 | San Juan | Los Lirios | Frank Nieves | A & M | CCC Joint Venture | DG3A | Builders Associates, LLC | 150 | 150 | 0 | 150 | 0 | 854 | 275 | 1129 | 32.2% | 1142 | 100% | 2009-11-12 | 2012-03-14 | 2012-12-14 | 2012-12-28 | 2013-04-19 | 0 | ARRA/CFP | 0 | 15075000 | 523404.07 | 15598404.07 | 3.472% | 15598404.07 | 0 | 15598404.07 | 100% | 7.6133 | 100% | 0 | The Contractor submitted a claim for extended overhead by amount of $989,402.32 | Final Acceptance
5099 | San Juan | El Prado | José González | Cost Control | BMA | Ray Architects | Del Valle Group | 220 | 220 | 0 | 220 | 0 | 1260 | 78 | 1338 | 6.19% | 1202 | 100% | 2000-09-15 | 2004-02-26 | 2004-05-14 | 2003-12-31 | 2004-01-28 | 0 | CFP | 0 | 15715000 | 1037001 | 16752001 | 6.599% | 16752001 | 0 | 16752001 | 100% | 5.4636 | 100% | 0 | Project Closed | Final Acceptance
5192 | San Juan | Antigua Via | José González | MAS Corporation | BMA | Rodríguez & del Valle (Design & Build) | Rodríguez & del Valle | 200 | 200 | 0 | 200 | 0 | 882 | 147 | 1029 | 16.67% | 1338 | 100% | 2000-01-10 | 2002-06-09 | 2002-11-03 | 2003-09-09 | 2003-09-09 | 0 | CFP | 0 | 13397000 | 211211 | 13608211 | 1.577% | 13608211 | 0 | 13608211 | 100% | 6.69 | 100% | 0 | Project Closed | Final Acceptance
2010 | San Juan | Vista Hermosa II (Fase II) | José Negrón | MAS Corporation | AVP / Jorge L. Robert | Guillermety, Ortiz & Asoc. | Urban Builders | 476 | 476 | 0 | 476 | 0 | 1216 | 590 | 1806 | 48.52% | 1442 | 100% | 1997-04-07 | 2000-08-04 | 2002-03-17 | 2001-03-19 | 2001-12-13 | 0 | 0 | 0 | 17900000 | 1037096.5 | 18937096.5 | 5.794% | 18371767.14 | 0 | 18371767.14 | 97.01% | 3.0294 | 100% | 0 | Project Closed | Final Acceptance
5031 | San Juan | Jardines de Campo Rico | José Negrón | Cost Control | CMS | DG3A | North Connstruction | 196 | 196 | 0 | 196 | 0 | 750 | 263 | 1013 | 35.07% | 1012 | 100% | 2006-01-30 | 2008-02-18 | 2008-11-07 | 2008-11-07 | 2008-12-04 | 0 | Tax Credit | 0 | 19483000 | 17564 | 19500564 | 0.09015% | 19500564 | 0 | 19500564 | 100% | 5.1633 | 100% | 0 | Project Closed | Final Acceptance
5143 | San Juan | Monte Park | José Negrón | Housing Promoters | AVP / SAGA | Molinary | Fernández & Gutiérrez | 224 | 224 | 0 | 224 | 0 | 874 | 345 | 1219 | 39.47% | 1517 | 100% | 1996-11-01 | 1999-03-24 | 2000-03-03 | 2000-12-27 | 2001-03-09 | 0 | 0 | 0 | 10585212 | 350973 | 10936185 | 3.316% | 10936185 | 0 | 10936185 | 100% | 6.7723 | 100% | 0 | Project Closed | Final Acceptance
5017 | San Juan | San Martín | Luis Rodríguez | Housing Promoters | LMC | Enrique Ruiz & Assoc. | Del Valle Group | 300 | 300 | 0 | 300 | 0 | 1095 | 353 | 1448 | 32.24% | 1631 | 100% | 2003-05-14 | 2006-05-12 | 2007-04-30 | 2007-10-31 | 2008-01-30 | 0 | 0 | 0 | 19703000 | 845652.15 | 20548652.15 | 4.292% | 20180652.15 | 0 | 20180652.15 | 98.21% | 5.4367 | 100% | 0 | Project Closed | Final Acceptance
5023 | San Juan | San Fernando | Luis Rodríguez | Cost Control Company, Inc. | LMC | DDHK | Del Valle Group | 334 | 334 | 0 | 334 | 0 | 1190 | 807 | 1997 | 67.82% | 1965 | 100% | 2004-12-10 | 2008-03-13 | 2010-05-29 | 2010-04-28 | 2010-10-15 | 0 | Tax Credit | 0 | 32133000 | 1051432.05 | 33184432.05 | 3.272% | 33163350.99 | 0 | 33163350.99 | 99.94% | 5.8832 | 100% | 0 | Project Closed | Final Acceptance
5135 | San Juan | Las Dalias | Luis Rodríguez | Housing Promoters | CMS | CSA Architects | Del Valle Group | 240 | 240 | 0 | 240 | 0 | 1195 | 271 | 1466 | 22.68% | 1458 | 100% | 2004-02-25 | 2007-06-03 | 2008-02-29 | 2008-02-22 | 2008-04-22 | 0 | Tax Credit 908-2008 | 0 | 22437872.18 | 818872.18 | 23256744.36 | 3.65% | 23256744.36 | 0 | 23256744.36 | 100% | 6.075 | 100% | 0 | Project Closed | Final Acceptance
5161 | San Juan | El Manatial | Luis Rodríguez | MAS Corporation | CMS | Behar-Ybarra | Del Valle Group | 200 | 200 | 0 | 200 | 0 | 890 | 345 | 1235 | 38.76% | 1234 | 100% | 2004-01-26 | 2006-07-03 | 2007-06-13 | 2007-06-13 | 2008-05-19 | 0 | 0 | 0 | 12929000 | 1024355.41 | 13953355.41 | 7.923% | 13953355.41 | 0 | 13953355.41 | 100% | 6.17 | 100% | 0 | Project Closed | Final Acceptance
5080 | San Juan | Jardines de Cupey | Félix Ortiz | Cost Control Company, Inc. | URS Caribe | Gautier & de Torres | Ferrovial Agroman | 308 | 308 | 0 | 308 | 0 | 1095 | 628 | 1723 | 57.35% | 1660 | 100% | 2006-02-15 | 2009-02-13 | 2010-11-03 | 2010-09-02 | 2011-08-22 | 0 | Tax Credit | 0 | 33630461 | 1042731.4 | 34673192.4 | 3.101% | 34673192.4 | 0 | 34673192.4 | 100% | 5.3896 | 100% | 0 | Project Closed | Final Acceptance
5040 | San Juan | Jardines de Sellés Fase I (Take over agreement) | Luz Acevedo | 0 | BMA | URS Dames & Moore | Urban Builders (St. Paul Surety) | 184 | 184 | 0 | 184 | 0 | 90 | 0 | 90 | 0% | 114 | 100% | 2003-08-20 | 2003-11-17 | 2003-11-17 | 2003-12-12 | 2004-02-17 | 0 | CFP | 0 | 9975000 | 231719 | 10206719 | 2.323% | 10206719 | 0 | 10206719 | 100% | 0.61957 | 100% | 0 | Project Closed | Final Acceptance
5040 | San Juan | Jardines de Sellés (Fase II) | Luz Acevedo | Housing Promoters | BMA | URS Caribe | Rodríguez & del Valle | 216 | 216 | 0 | 216 | 0 | 1095 | 320 | 1415 | 29.22% | 1415 | 100% | 2002-06-17 | 2005-06-15 | 2006-05-01 | 2006-05-02 | 2007-05-27 | 0 | 0 | 0 | 15268000 | 968748 | 16236748 | 6.345% | 16236748 | 0 | 16236748 | 100% | 6.5509 | 100% | 0 | Project Closed | Final Acceptance
5015-5140 | San Juan | Las Gladiolas I & II | Félix Ortiz | MAS Corp. | CCC-JV | Méndez-Brunner | Del Valle Group | 676 | 676 | 0 | 676 | 0 | 365 | 77 | 442 | 21.1% | 449 | 100% | 2011-04-11 | 2012-04-09 | 2012-06-25 | 2012-07-03 | 2013-02-08 | 0 | CFP | 0 | 2932000 | 129200.55 | 3061200.55 | 4.407% | 3061200.55 | 0 | 3061200.55 | 100% | 0.6642 | 100% | 0 | Pending Close Out | Final Acceptance
2003 | San Juan | Puerta de Tierra | Pedro Vega | Cost Control Company, Inc. | LMC | Guillermety, Ortiz & Asoc. | Homeca Recycling 2007-0498A | 148 | 148 | 0 | 148 | 0 | 150 | 300 | 450 | 200% | 543 | 100% | 2007-03-22 | 2007-08-18 | 2008-06-13 | 2008-09-15 | 0 | 0 | CFP | 0 | 678000 | 152491.82 | 830491.82 | 22.49% | 830492 | 0 | 830492 | 100% | 3.6689 | 100% | 0 | Project Closed | Final Acceptance
2003 | San Juan | New Puerta de Tierra | Pedro Vega | Cost Control Company, Inc. | LMC | Guillermety, Ortiz & Asoc. | Cué & López Construction, Inc | 85 | 85 | 0 | 85 | 0 | 900 | 20 | 920 | 2.222% | 823 | 100% | 2008-11-10 | 2011-04-28 | 2011-05-18 | 2011-02-11 | 2011-05-17 | 0 | CFP/Línea de Crédito | 0 | 16770000 | 813871.99 | 17583871.99 | 4.853% | 17583871.99 | 0 | 17583871.99 | 100% | 9.6824 | 100% | 0 | Project Closed | Final Acceptance
2004 | San Juan | San Agustín | José M. Paris Escalera | AM Contractors | Klassik Builders | Ray Engineers PSC | Cuè & López Construction, Inc | 84 | 84 | 0 | 84 | 0 | 570 | 304 | 874 | 53.33% | 869 | 100% | 2009-12-14 | 2011-07-06 | 2012-05-05 | 2012-05-01 | 2012-07-18 | 0 | ARRA | 0 | 3746000 | 1029880.39 | 4775880.39 | 27.49% | 4775880.39 | 0 | 4775880.39 | 100% | 10.3452 | 100% | 0 | Project Closed | Final Acceptance
2012 | San Juan | Villa España | Pedro Vega | Cost Control Company | LMC | Ray Engineers, PSC | Rodríguez & del Valle | 500 | 500 | 0 | 500 | 0 | 1280 | 929 | 2209 | 72.58% | 2208 | 100% | 2003-09-29 | 2007-03-31 | 2009-10-15 | 2009-10-15 | 2010-10-21 | 0 | Tax Credit | 0 | 33768000 | 1862123 | 35630123 | 5.514% | 35630123 | 0 | 35630123 | 100% | 4.416 | 100% | 0 | Project Closed | Final Acceptance
3090 | Salinas | Bella Vista | Félix Ortiz | MJ Consulting | Klassik Builders | INTEGRA | LPC&D | 100 | 100 | 0 | 100 | 0 | 730 | 160 | 890 | 21.92% | 889 | 100% | 2009-09-08 | 2011-09-07 | 2012-02-14 | 2012-02-14 | 2012-07-16 | 0 | ARRA | 0 | 10500000 | 749675.93 | 11249675.93 | 7.14% | 11249675.93 | 0 | 11249675.93 | 100% | 8.89 | 100% | 0 | 0 | Final Acceptance
5092 | San Lorenzo | La Lorenzana | Iván Blanco | MJ Consulting | URS | René Acosta Ingenieros | CD Builders | 100 | 100 | 0 | 100 | 0 | 730 | 351 | 1081 | 48.08% | 1147 | 100% | 2005-09-14 | 2007-09-13 | 2008-08-29 | 2008-11-04 | 2009-09-17 | 0 | Tax Credit | 0 | 10310000 | 828444.55 | 11138444.55 | 8.035% | 11138444.55 | 0 | 11138444.55 | 100% | 11.47 | 100% | 0 | Project Closed | Final Acceptance
3087 | San Sebastian | Andrés Méndez Liceaga | Arturo Acevedo | Inn Capital Housing Division Joint Venture | CMS | Interplan | RC Engineering | 150 | 150 | 0 | 150 | 0 | 960 | 729 | 1689 | 75.94% | 1688 | 100% | 2004-05-24 | 2007-01-08 | 2009-01-06 | 2009-01-06 | 2009-02-16 | 0 | Tax Credit | 0 | 13130000 | 401586.86 | 13531586.86 | 3.059% | 13531587 | 0 | 13531587 | 100% | 11.2533 | 100% | 0 | Project Closed | Final Acceptance
5144 | Santa Isabel | Rincón Taíno | Rubén Cotto | J. A. Machuca | BMA | Hernández - Bauzá | Constructora I. Meléndez | 100 | 100 | 0 | 100 | 0 | 810 | 499 | 1309 | 61.6% | 1087 | 100% | 2003-07-28 | 2005-10-14 | 2007-02-25 | 2006-07-19 | 2006-09-30 | 0 | 0 | 0 | 7231087 | 175900 | 7406987 | 2.433% | 6372476 | 0 | 6372476 | 86.03% | 10.87 | 100% | 0 | Las OC # 7 y 8 fueron sometidas por el CM, pero le fueron devueltas para aclaracion o correccion, ya que el NGC no esta de acuerdo con el tiempo de extension otorgado y los "supporting documents". Posteriormente el CM las entrego fuera del termino de vigencia y las mismas no se pudieron procesar. El contratista sometio demanda y se efectuo reunion entre ambas representaciones legales. Se llego a un acuerdo: AVP de pagar lo que se le adeudaba por concepto de daños liquidos y retenido, Contratista: No reclamar "extended overhead" ni la OC #8. Esto hace varios meses y AVP tiene pendiente procesar los pagos correspondientes. | Final Acceptance
5198 | Toa Alta | Jardines de San Fernando | Luis Rodríguez | Housing Promoters | MD | URS Caribe, LLP | Orion Contractors | 51 | 51 | 0 | 51 | 0 | 800 | 1627 | 2427 | 203.4% | 2502 | 100% | 2006-01-09 | 2008-03-18 | 2012-08-31 | 2012-11-15 | 2013-10-15 | 0 | BFP-2003 | 0 | 7227000 | -982226.89 | 6244773.11 | -13.59% | 6244773.11 | 0 | 6244773.11 | 100% | 49.0588 | 100% | 0 | The PRPHA and the Contractor signed a Termination by Convinience (TBC), where the contractor grants a creditfor the amount of $2,182,368.61 for the remaining work phase IV,V and VIII. The PRPHA extends the contract by 744 calendar days providing a substantial termination effective at the August 31, 2012. The contractor walves its claim for extended overhead. | Final Acceptance
3069 | Toa Baja | El Toa | Jorge Mercado | MJ Consulting | AVP | Soler Cloquel & Asoc. | Royal Ins. | 80 | 80 | 0 | 80 | 0 | 669 | 458 | 1127 | 68.46% | 1205 | 100% | 1997-06-30 | 1999-04-29 | 2000-07-30 | 2000-10-17 | 2001-05-18 | 0 | 0 | 0 | 4045086 | 299127 | 4344213 | 7.395% | 4344213 | 0 | 4344213 | 100% | 15.0625 | 100% | 0 | Project Closed | Final Acceptance
5193 | Trujillo Alto | Los Rosales | José M. Paris Escalera | Peregrine Group Inc. | Klassik Builders | URS Caribe, LLP | Cidra Excavation, SE | 74 | 74 | 0 | 74 | 0 | 730 | 138 | 868 | 18.9% | 821 | 100% | 2009-11-16 | 2011-11-15 | 2012-04-01 | 2012-02-15 | 2012-08-14 | 0 | ARRA | 0 | 7947800 | 1458351.48 | 9406151.48 | 18.35% | 9406151.48 | 0 | 9406151.48 | 100% | 11.0946 | 100% | 0 | Project Closed | Final Acceptance
3071 | Vega Alta | Fco. Vega Sánchez | José Negrón | MJ Consulting | LMC | Hernández - Bauzá | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 782 | 109 | 891 | 13.94% | 890 | 100% | 2000-10-02 | 2002-11-22 | 2003-03-11 | 2003-03-11 | 2003-04-11 | 0 | 0 | 0 | 9309000 | 70614.85 | 9379614.85 | 0.7586% | 9379616 | 0 | 9379616 | 100% | 8.9 | 100% | 0 | Project Closed | Final Acceptance
5105 | Vega Alta | Las Violetas | Luis Rodríguez | Cost Control Company, Inc. | ISS | URS Dames & Moore | Del Valle Group | 88 | 88 | 0 | 88 | 0 | 730 | 150 | 880 | 20.55% | 1000 | 100% | 2006-02-01 | 2008-01-31 | 2008-06-29 | 2008-10-28 | 2009-09-30 | 0 | Tax Credit | 0 | 9203600 | 46081.53 | 9249681.53 | 0.5007% | 9007681.53 | 0 | 9007681.53 | 97.38% | 11.3636 | 100% | 0 | Project Closed | Final Acceptance
3073 | Villalba | Efraín Suárez Negrón | Arturo Acevedo | J.A. Machuca | CMS | Yañez & Mayol | Ravaro Construction | 60 | 60 | 0 | 60 | 0 | 660 | 295 | 955 | 44.7% | 1240 | 100% | 2002-04-15 | 2004-02-03 | 2004-11-24 | 2005-09-06 | 2005-09-06 | 0 | 0 | 0 | 4033500 | 93123 | 4126623 | 2.309% | 4126623 | 0 | 4126623 | 100% | 20.6667 | 100% | 0 | Project Closed | Final Acceptance
5164 | Villalba | Maximino Miranda Jiménez | Félix Ortiz | Municipio de Villalba | Klassik Builders | LPA Group, Arq. | Constructora I. Meléndez | 100 | 100 | 0 | 100 | 0 | 732 | 180 | 912 | 24.59% | 911 | 100% | 2009-05-20 | 2011-05-21 | 2011-11-17 | 2011-11-17 | 2012-01-19 | 0 | CFP/ARRA | 0 | 12392438 | 408291.81 | 12800729.81 | 3.295% | 12800729.81 | 0 | 12800729.81 | 100% | 9.11 | 100% | 0 | Project Closed | Final Acceptance
5067 | Yauco | Ext. Santa Catalina | Rubén Cotto | Inn Capital Housing Division Joint Venture | URS | René Acosta Ingenieros | A. Rivera & Asociados | 24 | 24 | 0 | 24 | 0 | 548 | 319 | 867 | 58.21% | 814 | 100% | 2006-01-16 | 2007-07-17 | 2008-05-31 | 2008-04-09 | 2008-08-26 | 0 | CFP-2003 | 0 | 1972404 | 50556.96 | 2022960.96 | 2.563% | 2022961 | 0 | 2022961 | 100% | 33.9167 | 100% | 0 | Project Closed | Final Acceptance
| 7 | Active | [5 empty] | 1046 | 580 | 78 | 658 | 60 | [14 empty] | 74867307 | 4238267.63 | 79105574.63 |  | 59995942.25 | 1271462.02 | 61267404.27 |  |  |  | 0 |  | Active
| 2 | Stoped | [5 empty] | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | Stoped
| 10 | Substantial | [5 empty] | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 13.542 |  |  |  | Substantial Completion
| 110 | Final Acceptance | [5 empty] | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 9.8658 |  |  |  | Final Acceptance
Total | 129 | [6 empty] | 20299 | 19627 | 78 | 19705 | 60 | [14 empty] | 1493538072.27 | 97622150.87 | 1670265797.77 |  | 1558880043.8708 | 1271462.02 | 1621418910.1608 |  | 10.1721 |  | 0 |  | Total
| Revised by: |  |  |  | Approved by: | [19 empty] | Approved by:
|  | Luz M. Acevedo Pellot, PE |  |  |  |  | Germán Acevedo Marín, PE | [18 empty] | Arturo A. Garcia de la Noceda Castro, PE
|  | Project Coordinator |  |  |  |  | Director | [18 empty] | Deputy Administrator
|  | Construction Management Bureau |  |  |  |  | Construction Management Bureau | [18 empty] | Development and Construction Area
Report Date: |  |  | 2014-04-30
Report Last Revision Date: |  |  | 2014-05-10
Notes/Notas:
CMB Monthly Report is prepared for the use of Construction and Development Area. The Associate Administrator will approve any use of this report outside this area and must have his signature to be valid.
Informe preparado para uso del Área de Desarrollo y Construcción de Proyectos. El Administrador Asociado aprobará cualquier uso de este Informe fuera del Área y debe tener su firma para ser válido.
Information is provided by PRPHA Project Monitors, and is subject to change.
La Información es suministrada con los datos que proveen los Monitores de Proyectos, por lo que está sujeta a cambios.
Final Acceptance Report contains all Projects. This report is not worked by fiscal or natural year, it is a report that contains cumulative information and not all projects present monthly changes.
El Informe de "Final Acceptance" contiene todos los Proyectos. No se trabaja por Año Natural o Año Fiscal; es un reporte que contiene información acumulativa y no en todos los Proyectos se presentan cambios mensuales.
NOTIFICACIÓN DE CONFIDENCIALIDAD: Este Informe y cualquier archivo transmitido en ella pueden contener información confidencial, privilegiada y/o privada bajo las leyes aplicables. Se utiliza solamente para el uso o entidad a que se dirige. Si usted no es el destinatario intencional, se le notifica que cualquier uso, diseminación o copia de esta Informe se prohíbe estrictamente. Si usted recibe esta Informe por error, notificar al remitente inmediatamente y destruir el material en su totalidad.
CONFIDENTIALITY NOTICE: This report and any files transmitted with it may contain information that is confidential, privileged and exempt from disclosure under applicable law. It is intended solely for the use of the individual or entity to which it is addressed. If you are not the intended recipient, you are hereby notify that any use, dissemination or copying of this report is strictly prohibited. If you have received this communication by error, immediately contact the sender and destroy the material in its entirety, whether in electronic of hard copy format.
Note on AC15: lvlynn: Discrepancia: $98,932 Inf. Monitor
Note on H48: lvlynn: Contratista Default Target Engineering
Note on W77: lvlynn: 9-junio-09 Final
Note on W81: lvlynn:
Note on AC96: OC 1 @ 13
Note on Z97: lvlynn: CFP-Línea de Crédito

## STOPPED PROJECTS MONTHLY REPORT
A | B | C | D | E | F | G | H | I | J | K | L=J+K | M | N | O | P=N+O | Q=O/N | R=DATE-T | S=R/P | T | U=T+N-1 | V=T+P-1 | W | X | Y | Z | AA | AB | AC | AD=AB+AC | AE=AC/AB | AF | AG | AH=AF+AG | AI=AH/AD | AJ=(W-T)/I | AK |  | AK | AL
RQ | Municipality | Name of the Project | PHAPR Monitor | Management Agent | Construction Manager/PM | Designer (A/E) | Contractor | Units |  |  |  |  | Times | [5 empty] | Dates | [5 empty] | Funds | [9 empty] | Certified Days/Unit | % Progress | Monthly Employment | Executive Summary | Status
[8 empty] | Total Dwelling Units | Previous Completed Dwelling Units | Completed Dwelling Units for this Period | Total Completed Dwelling Units | Dwelling Units Forecast for next Month | Contruction Period (Cal. Days) | Time Extension (Cal. Days) | Revised Construction Period (Cal. Days) | % Extended Time | Elapsed Time (Cal. Days) | Elapsed Time (%) | Construction Start Date | Original Completion Date | Revised Construction Completion Date | Substantial Completion Date | Final Acceptance Date | Registered at Controller Contract Termination Date | Funds Proceeds | Funds Obligation Date | Original Construction Contract Amount | Approved Change Orders Amount ($) | Revised Construction Contract Amount | % Of Change Orders | Previous Certified Amount | Certified this Period | Total Certified Amount | Certified Amount (%)
3025 | Carolina | Felipe Sánchez Osorio (Demolition) | Luis Rodríguez | N/A | Municipio de Carolina | State Engineering | Municipio de Carolina | 32 | 26 | 0 | 26 | 0 | 120 | 0 | 120 | 0% | 259 | 215.8% | 2013-08-14 | 2013-12-11 | 2013-12-11 | 0 | 0 | 0 | 0 | 0 | 336510 | 0 | 336510 | 0% | 27516.72 | 122054.24 | 149570.96 | 44.45% |  | 0% | 0 | ♦ Project Situation according to the CPM Uptaded: Phase I was completed on November 27, 2013. ♦ Reasons of the Delay (if applies) N/A ♦ Change Order in PRPHA pending for approval: N/A ♦ Extraordinary Situations with Relocation (if applies)- N/A ♦ Situations with Governmental Agencies (if applies): N/A ♦ Others situations that are affecting the project (if Applies): N/A | Active
5127 | Arecibo | La Meseta | Pedro Vega | Housing Promoters, Inc. | AVP | ERA | Maglez Engineering & Contractors, Corp. | 0 | 0 | 0 | 0 | 0 | 365 | 0 | 365 | 0% | 394 | 107.9% | 2013-04-01 | 2014-03-31 | 2014-03-31 | 0 | 0 | 2014-03-31 | CFP | 0 | 1602797 | 0 | 1602797 | 0% | 979943.16 | 71165.27 | 1051108.43 | 65.58% |  | 0% | 0 | • Project Situation: Some submmittal requirement from designer are delaying the Contractor's time to make purchase orders or solve construction problems as design error for primary system upgrade. • Project Status: Last CPM Updated february 28,2014, refected a reduction of project delay from 49 days behind schedule. There is a CO #1 with 14 calendars days pending for PRPHA approval. New letter of intents are in negotiation that can reflect additional extension claim. • Change Orders: CO #1 $41,193.88 where send to PRPHA. • Last Certification: #11 february 28, 2014 • Relocation issues: There is not Relocation issues. • Goverment Agencies issues: AEE are requiring change to approved design that represent additional cost to project. • Other Situation issues: There is not AAA endorsement. this month the designer submmit the endorsement amedment. | Active
4011 | Mayaguez | Rafael Hernandez (El Kennedy) | Noefebdo Ramírez | JA Machuca | Klassik Builders | Hernán Jr. Machado Ingenieros Consultores | F & R Construction | 190 | 26 | 0 | 26 | 24 | 1094 | 153 | 1247 | 13.99% | 926 | 74.26% | 2011-10-17 | 2014-10-14 | 2015-03-16 | 0 | 0 | 2016-02-07 | CFP | 0 | 21797000 | 446287.81 | 22243287.81 | 2.047% | 13868385.06 | 204312.21 | 14072697.27 | 63.27% |  | 0% | 0 | • Project situation according to the CPM updated: According to the last CPM updated, the project finish date is September 3, 2015. The contract revisedconstruction completion date is March 16,2015. That represent 171 days of delay. When thechange order # 9 be approvedthe completion date move to May 30, 2015. the Change Order # 10 included 10 aditional days for weather conditions. Then represent 58 days of delay. • Reasons of the Delay: One reasons is the delay for termination and delivery of modernized units by the Contractors. The lead and asbestos abatement started on February 3,2014 to enclosure the building # 4. The buildingcome to be ready to start the works on March 21,2014, No contruction works can't do it into the buildings. Those impact the crithical path which is total responsability of the contractor. In special the building # 18, which in the next building in the modernization sequence and are stopped for 108 days. • Change Order in PRPHA pending for approval:. The CO # 9 (193,914.32 and include 75 calendar days extension) and change order # 10 (of $562,564.73 and include 10 calendar days extension) • Payments Certifications Status: The Contractor has pending to submit to PRPHA the Certifications for partial payment of # 30 (February 2014 period) and # 31 (March 2014 period) • Extraordinary Situations with Relocation - N/A • Situations with Governmental Agencies: The tapping conection for the potable water services, under the PR #2 state road was not do it in this period. This tapping is a change order in a process of negotiation. The AAA final endosement depend of finish this connection works. The Puerto Rico Power Authority present a new request to install other facilities for existingsanitary pump station. That works were not contemplted in the design. • Others situations that are affecting the project: The installationof the restrainers in the 36 inches ductile iron forced line was not completed in this period. A 70% of the total pipe line need to be reinstalling. A wprkplan was by KBI to the Contractor to define this work to be done during summer school vacation as requested. | Active
3105 | San Juan | Ext. Manuel A. Pérez | Arturo Acevedo | MAS Corp. | Klassik Builders | DDHK | LPC&D | 324 | 188 | 12 | 200 | 12 | 1098 | 433 | 1531 | 39.44% | 1385 | 90.46% | 2010-07-15 | 2013-07-16 | 2014-09-22 | 0 | 0 | 2015-08-06 | HOPE IV | 0 | 24800000 | 1110120.04 | 25910120.04 | 4.476% | 19847694.84 | 161086 | 20008780.84 | 77.22% |  | 0% | 0 | • Project situation according to the CPM updated • Reasons of the Delay (if applies) • Payments Certifications Status- Lastcertification rendered for payment is certification # 42, for the period of January 2014. • Change Orders: • Extraordinary Situations with Relocation (if applies)-N/A • Situations with Governmental Agencies (if applies)-N/A • Others situations that are affecting the project (if applies)-N/A • Withheld: | Active
5034 | San Juan | Alturas de Cupey | José M. Paris | SP Management Corp. | Klassik Builders | CSA | F&R Construction | 96 | 48 | 16 | 64 | 0 | 732 | 256 | 988 | 34.97% | 1057 | 107% | 2011-06-08 | 2013-06-08 | 2014-02-19 | 0 | 0 | 2015-06-20 | CFP | 0 | 7936000 | 1003018.78 | 8939018.78 | 12.64% | 7832237.98 | 470242.15 | 8302480.13 | 92.88% |  | 0% | 0 | • Project situation according to the CPM updated: According to the last CPM updated on June 2013, the project is 72 calendar days ahead schedule with a possible termination date on December 19, 2013. • Reasons of the Delay (if applies) • Bad execution by the Contractor (if applies)- N/A • Change Orders pending for approval - N/A • Others (if applies) - a) Weather and site conditions (Soil Moisture) • Change Order in PRPHA pending for approval: N/A • Latest Certification: The last certification for payment submitted by the Contractor correspond to the period of July 26, 2013 thru August 25, 2013 (Certification #27 for the amount of $470,242.15 • Extraordinary Situations with Relocation (if applies) - N/A • Situations with Governmental Agencies (if applies) - N/A • Others situations that are affecting the project (if applies) - N/A | Active
5068 | San Juan | Las Amapolas (Demolition) | Noefebdo Ramírez | SP Management Corp. | AVP | Integra | Anibal Díaz Construction, Inc. | 204 | 138 | 50 | 188 | 16 | 365 | 0 | 365 | 0% | 176 | 48.22% | 2013-11-05 | 2014-11-04 | 2014-11-04 | 0 | 0 | 2015-10-30 | CFP | 0 | 948000 | 0 | 948000 | 0% | 231193.27 | 0 | 231193.27 | 24.39% |  | 0% | 0 | • Project situation according to CPM (updated): According to the CPM, the project is on schedule. • Reasons of Delay: none • Change Orders in PRPHA pending for Approval: none • Payments CertificationS Status: The contractor has pending to submit to PRPHA the certificactions for the partial Payments # 3 (February 2014) and #4 (March 2014 period) • Extraordinary situations with Relocation: N/A • Situations with Governmental Agencies: none • Other situations that are affecting the project: No report in this moment. | Active
5028 | Yauco | Ana Catalina Rodríguez Vélez (Santa Catalina) | Arturo Acevedo | JA Machuca | AVP | URS Caribe LLC | La Mar Construction Corporation | 200 | 154 | 0 | 154 | 8 | 1098 | 339 | 1437 | 30.87% | 1525 | 106.1% | 2010-02-25 | 2013-02-26 | 2014-01-31 | 0 | 0 | 2014-11-26 | ARRA/Mixed | 0 | 17447000 | 1678841 | 19125841 | 9.623% | 17208971.22 | 242602.15 | 17451573.37 | 91.25% |  | 0% | 0 | • Project situation according to CPM (updated): • Reasons of Delay: • Change Orders in PRPHA pending for Approval: • latest Certification: Last certification rendered for payment is certification # 49 (February 2014) • Extraordinary situations with Relocation: N/A • Situations with Governmental Agencies: N/A • Other situations that are affecting the project: N/A | Active
5011 | San Juan | Jardines del Paraíso | José Negrón | Cost Control Company, Inc. | BMA | Andrés Hernández & Asoc. | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 41759 | #DIV/0! | 0 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | 0% | 0 | Proyecto en Re-Subasta. Subasta declarada Desierta. No se ha Comenzado el proyecto. | Stopped
3049 | Lajas | Las Américas | Noefebdo Ramírez | Inn Capital Housing Division Joint Venture | none | URS Caribe, LLP | none | 80 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | #DIV/0! | 41759 | #DIV/0! | 0 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | 0% | 0 | Design completed. Pending for will be assigned construction funds by PHA. | Stopped
3100 | Aguadilla | Agustín Stahl I | Arturo Acevedo | American Management Corp. | CCC-JV | René Acosta Arquitectos | Karimar Construction, Inc. | 180 | 180 | 0 | 180 | 0 | 915 | 192 | 1107 | 20.98% | 1100 | 100% | 2010-03-23 | 2012-09-22 | 2013-04-02 | 2013-03-27 | 0 | 0 | ARRA/CFP | 0 | 13875675 | 597322.95 | 14472997.95 | 4.305% | 13367679 | 0 | 13367679 | 92.36% | 6.1111 | 0% | 0 | Project started on march 23, 2010. substantial completion was awarded on March 27 2013 Last certification rendered for payment is certification # 38, for the period of March 1 to 30, 2013. | Substantial Completion
5201 | Cayey | Alturas de Montellano | Jorge Mercado | Municipio | LMC | Arq. José Luzunaris | RC Group S.E. | 80 | 50 | 0 | 50 | 0 | 730 | 846 | 1576 | 115.9% | 1970 | 100% | 2001-09-04 | 2003-09-03 | 2005-12-27 | 2007-01-26 | 0 | 0 | CFP | 2001-11-21 | 4790000 | 2327268.37 | 7117268.37 | 48.59% | 7036300.8 | 0 | 7036300.8 | 98.86% | 24.625 | 0% | 0 | Nunca se aprobaron las ordenes de cambio #17 y #18 porque el contratista no sometió los documentos solicitados por el Área de Adquisición y Contratación. Nunca se le otorgó el "Final Acceptance". El caso esta siendo atendido en la División Legal de la Admnisitración de Vivienda Pública. Queda un balance de $80,967.57 en espera se resuelva la controversia. | Substantial Completion
3089 | Juana Díaz | Villa del Parque (Take over agreement) | Rubén Cotto | J.A. Machuca | MD | GMG Eng. Consultants | (USF & G) | 100 | 100 | 0 | 100 | 0 | 547 | 746 | 1293 | 136.4% | 552 | 100% | 2000-12-18 | 2002-06-17 | 2004-07-02 | 2002-06-23 | 0 | 0 | CFP | 2000-09-30 | 3105100 | 239005.38 | 3344105.38 | 7.697% | 3171314 | 0 | 3171314 | 94.83% | 5.52 | 0% | 0 | El "final acceptance" le fue entregado a la Administracion del proyecto , JA Machuca, no obstante los mismos no lo han firmado ya que la Aseguradora no ha sometido aun los documentos de garantía de techo. Se le indicó vervalmente al Ing. Carrasquillo, representante de la Aseguradora. | Substantial Completion
3093 | Juncos | Narciso Varona Fase II | José González | MJ Consulting | AVP | DG3A Design Group, PSC | F & R Construction Group, Inc. | 172 | 172 | 0 | 172 | 0 | 1220 | 235 | 1455 | 19.26% | 1385 | 100% | 2010-02-24 | 2013-06-27 | 2014-02-17 | 2013-12-10 | 0 | 0 | Arra/Mixed | 0 | 13189000 | 822958.39 | 14011958.39 | 6.24% | 13762592.18 | 0 | 13762592.18 | 98.22% | 8.0523 | 0% | 0 | Project is almost completed. | Substantial Completion
5053 | Mayagüez | Ramírez de Arellano | Pedro Vega | JA Machuca | LMC | GMG Engineering | Comas & Comas Contractors, Corp | 80 | 80 | 0 | 80 | 0 | 720 | 661 | 1381 | 91.81% | 1375 | 100% | 2009-07-13 | 2011-07-02 | 2013-04-23 | 2013-04-18 | 0 | 0 | ARRA/CFP | 0 | 4040000 | 2215708.24 | 6255708.24 | 54.84% | 6011262.53 | 0 | 6011262.53 | 96.09% | 17.1875 | 0% | 0 | Final Completion and Close Out era specting for: 1) PRPHA approval CO#9 and CO#10; 2)Contractor correction of payroll defiecience | Substantial Completion
3058 | Moca | José N. Gándara | Noefebdo Ramírez | NFC | CMS | Ray Engineers PSC | Moss Construction | 74 | 74 | 0 | 74 | 0 | 896 | 73 | 969 | 8.147% | 940 | 100% | 1999-11-08 | 2002-04-21 | 2002-07-03 | 2002-06-05 | 0 | 0 | CFP-02 | 2000-01-13 | 4671000 | 238289 | 4909289 | 5.101% | 4805897.22 | 0 | 4805897.22 | 97.89% | 12.7027 | 0% | 0 | The close out was not completed because the Contractor not submit to PRPHA the final documents required by the Construction and Management Bureau and the Legal Division of the PRPHA. The solution of this case was referred to Legal Division of the PRPHA. | Substantial Completion
5088 | Ponce | Lirios del Sur | Arturo Acevedo | MJ Consulting | CMS | CSA | Caribe General Constructors | 400 | 400 | 0 | 400 | 0 | 791 | 487 | 1278 | 61.57% | 1267 | 100% | 2009-03-02 | 2011-05-01 | 2012-08-30 | 2012-08-20 | 0 | 0 | CFP | 0 | 16598000 | 2352431.7 | 18950431.7 | 14.17% | 17140589.22 | 0 | 17140589.22 | 90.45% | 3.1675 | 0% | 0 | Project started in march 2009, The contrator finished the instalation of the luminaries on the fence of the west side of the project. Last certification rendered for payment is certification # 35, which is the 50% of retainage. | Substantial Completion
5056 | Guaynabo | Loa Alamos | José González | Municipio de Guaynabo | Klassik | Hernández-Bauzá | Homeca Recycling | 376 | 376 | 0 | 376 | 0 | 549 | 0 | 549 | 0% | 547 | 100% | 2012-09-17 | 2014-03-19 | 2014-03-19 | 2014-03-18 | 0 | 0 | CFP | 0 | 2339000 | -40565.21 | 2298434.79 | -1.734% | 2149223.01 | 0 | 2149223.01 | 93.51% | 1.4548 | 0% | 0 | Project is almost completed. | Substantial Completion
5166 | San Juan | Brisas de Cupey | José M. Paris | SP Management Corp. | CCC-JV | Fracinetti Arquitectos | Pitirre Copnstruction | 184 | 184 | 0 | 184 | 0 | 993 | 127 | 1120 | 12.79% | 1251 | 100% | 2010-02-26 | 2012-11-14 | 2013-03-21 | 2013-07-31 | 0 | 0 | ARRA/CFP | 0 | 15326960 | 1013140.06 | 16340100.06 | 6.61% | 16340100.06 | 0 | 16340100.06 | 100% | 6.7989 | 0% | 0 | The Program Manager is preparing the change order # 10, this CO has time extension by wheater condition and delay in the delivery of the building # 12 to the Contractor. The six building completed and we are waiting for legal RW documents, | Substantial Completion
3070 | Trujillo Alto | Pedro Regalado Díaz | José González | Inn Capital Housing Division Joint Venture | MD | Ray Engineers PSC | José L. Colón | 10 | 10 | 0 | 10 | 0 | 273 | 226 | 499 | 82.78% | 498 | 100% | 2008-04-14 | 2009-01-11 | 2009-08-25 | 2009-08-25 | 0 | 0 | CFP | 0 | 1991000 | 435116 | 2426116 | 21.85% | 2304810.1 | 0 | 2304810.1 | 95% | 49.8 | 0% | 0 | ♦ Repair of Units and Administration Building - The Management Agent has prepared a report about the scope of work and cost to repair units that will be delivered to the residents. Extraordinary Maintenance Office (PHAPR) is working with this item. ♦ Existing post removal - This work will be performed once the AEE connects the project and the Cable TV Company removes its wiring. ♦ Claim of the Contractor Jose Luis Colon - it was assigned to PGES to work with it. | Substantial Completion
3030 | Adjuntas | Villa Valle Verde | Pedro Vega | J.A. Machuca | URS | Jorge L. Roberts, PSC | Venegas Construction | 150 | 150 | 0 | 150 | 0 | 913 | 144 | 1057 | 15.77% | 1743 | 100% | 2001-01-15 | 2003-07-16 | 2003-12-07 | 2005-10-24 | 2007-02-06 | 0 | 0 | 0 | 11829000 | 337235 | 12166235 | 2.851% | 12103923 | 0 | 12103923 | 99.49% | 11.62 | 100% | 0 | These Close out is in process by PGES. | Final Acceptance
3034 | Aguada | Francisco Egipciaco | Noefebdo Ramírez | NFC | CMS | Arq. José Luzunaris | NLL Construction | 100 | 100 | 0 | 100 | 0 | 887 | 0 | 887 | 0% | 819 | 100% | 2000-03-23 | 2002-08-26 | 2002-08-26 | 2002-06-20 | 2002-10-04 | 0 | 0 | 0 | 8107810 | 207539 | 8315349 | 2.56% | 8315349 | 0 | 8315349 | 100% | 8.19 | 100% | 0 | Project Closed | Final Acceptance
5252 | Aguada | Los Robles | Noefebdo Ramírez | NFC | CMS | Joglar & Architects | 422 Corporation | 62 | 62 | 0 | 62 | 0 | 669 | 0 | 669 | 0% | 692 | 100% | 2001-01-18 | 2002-11-17 | 2002-11-17 | 2002-12-11 | 2003-10-02 | 0 | 0 | 0 | 2640000 | -11465 | 2628535 | -0.4343% | 2628535 | 0 | 2628535 | 100% | 11.1613 | 100% | 0 | Project Closed | Final Acceptance
5158 | Aguadilla | La Montaña | Frank Nieves | American Management | URS | Unipro | Caribe Tecno Habitat | 220 | 220 | 0 | 220 | 0 | 895 | 458 | 1353 | 51.17% | 1341 | 100% | 2003-07-28 | 2006-01-07 | 2007-04-10 | 2007-03-30 | 2007-03-30 | 0 | CFP | 0 | 16148000 | 1232941.34 | 17380941.34 | 7.635% | 16890921 | 0 | 16890921 | 97.18% | 6.0955 | 100% | 0 | Project Closed | Final Acceptance
3035 | Aguas Buenas | Vista Alegre | Rubén Cotto | MJ Consulting | URS Caribe | Carlos E. Betancourt | Constructores Gilmar | 74 | 74 | 0 | 74 | 0 | 912 | 752 | 1664 | 82.46% | 1645 | 100% | 2005-06-06 | 2007-12-04 | 2009-12-25 | 2009-12-07 | 2010-09-10 | 0 | Tax Credit 908-2008 | 0 | 6690000 | 2657915 | 9347915 | 39.73% | 8143277.42 | 0 | 8143277.42 | 87.11% | 22.2297 | 100% | 0 | Project Closed | Final Acceptance
3082 | Arecibo | Ramón Marín Solá (Fase II) | Arturo Acevedo | MAS Corporation | CMS | Andrés Hernández | Nogama Construction | 96 | 96 | 0 | 96 | 0 | 612 | 44 | 656 | 7.19% | 626 | 100% | 2000-05-15 | 2002-01-16 | 2002-03-01 | 2002-01-31 | 2002-03-15 | 0 | 0 | 0 | 7837000 | 0 | 7837000 | 0% | 7837000 | 0 | 7837000 | 100% | 6.5208 | 100% | 0 | Project Closed | Final Acceptance
3097 | Arecibo | Trina Padilla de Sanz | Frank Nieves | Cost Control Company, Inc. | ISS Corp | Ray Engineers PSC | Nogama Construction | 240 | 240 | 0 | 240 | 0 | 1278 | 97 | 1375 | 7.59% | 1464 | 100% | 2006-01-09 | 2009-07-09 | 2009-10-14 | 2010-01-12 | 2010-08-16 | 0 | Tax Credit | 0 | 23814529 | 1556413.89 | 25370942.89 | 6.536% | 25198434.68 | 0 | 25198434.68 | 99.32% | 6.1 | 100% | 0 | Project Closed | Final Acceptance
5127 | Arecibo | La Meseta | Pedro Vega | Cost Control Company, Inc. | URS Caribe | Enrique Ruiz & Asoc. | Venegas Construction | 300 | 300 | 0 | 300 | 0 | 1098 | 871 | 1969 | 79.33% | 1947 | 100% | 2005-05-31 | 2008-06-01 | 2010-10-20 | 2010-09-29 | 2011-01-24 | 0 | Tax Credit | 0 | 24161000 | 1903823.57 | 26064823.57 | 7.88% | 26064823.57 | 0 | 26064823.57 | 100% | 6.49 | 100% | 0 | Project Closed. | Final Acceptance
3099 | Arecibo | Antonio Márquez Arbona | Frank Nieves | American Management | Klassik Builders | Enrique Ruiz & Asoc. | Karimar Construction, Inc. | 104 | 104 | 0 | 104 | 0 | 730 | 183 | 913 | 25.07% | 912 | 100% | 2010-03-25 | 2012-03-23 | 2012-09-22 | 2012-09-22 | 2013-04-01 | 0 | ARRA/CFP | 0 | 9085636 | 263361.39 | 9348997.39 | 2.899% | 9223663.18 | 0 | 9223663.18 | 98.66% | 8.7692 | 100% | 0 | In Closing Process. | Final Acceptance
3021 | Arroyo | Isidro Cora | Rubén Cotto | MJ Consulting | MD | GMG Eng. Consultants | Venegas Construction | 150 | 150 | 0 | 150 | 0 | 1095 | 302 | 1397 | 27.58% | 1396 | 100% | 1999-09-27 | 2002-09-25 | 2003-07-24 | 2003-07-24 | 2004-09-30 | 0 | 0 | 0 | 10247000 | 437000 | 10684000 | 4.265% | 10654500 | 0 | 10654500 | 99.72% | 9.3067 | 100% | 0 | The close out documents are under correction process by the Program Manager and General Contractor. | Final Acceptance
3036 | Barceloneta | Antonio Dávila Freytes | José Negrón | MAS Corporation | LMC | Andrés Hernández & Asoc. | Caribe Tecno | 100 | 100 | 0 | 100 | 0 | 904 | 413 | 1317 | 45.69% | 1316 | 100% | 1999-10-15 | 2002-04-05 | 2003-05-23 | 2003-05-23 | 2003-06-30 | 0 | 0 | 0 | 6970000 | 1305876.67 | 8275876.67 | 18.74% | 8275877 | 0 | 8275877 | 100% | 13.16 | 100% | 0 | Project Closed | Final Acceptance
3037 | Barranquitas | Villa Universitaria | Jorge Mercado | MJ Consulting | AVP | GMG Eng. Consultants | Royal & Sun Alliance | 100 | 100 | 0 | 100 | 0 | 540 | 913 | 1453 | 169.1% | 1678 | 100% | 1997-11-25 | 1999-05-18 | 2001-11-16 | 2002-06-30 | 2002-11-12 | 0 | 0 | 0 | 5299000 | 804839 | 6103839 | 15.19% | 6103839 | 0 | 6103839 | 100% | 16.78 | 100% | 0 | Project Closed | Final Acceptance
5093 | Bayamón | Brisas de Bayamón | Arturo Acevedo | Cost Control Company, Inc. | URS Caribe | Edison Avilés Deliz | Omega Engineering | 300 | 300 | 0 | 300 | 0 | 1400 | 1372 | 2772 | 98% | 2518 | 100% | 2002-01-09 | 2005-11-08 | 2009-08-11 | 2008-12-01 | 2010-03-22 | 0 | Tax Credit | 0 | 23965851 | 5030471 | 28996322 | 20.99% | 27007484 | 0 | 27007484 | 93.14% | 8.3933 | 100% | 0 | Project Closed | Final Acceptance
5151 | Bayamón | Sierra Linda | Arturo Acevedo | Martinal Property | URS | Gautier & De Torres | JR Builders | 200 | 200 | 0 | 200 | 0 | 1015 | 1071 | 2086 | 105.5% | 2136 | 100% | 2002-04-15 | 2005-01-23 | 2007-12-30 | 2008-02-19 | 2008-08-08 | 0 | CFP-02 | 0 | 13395440 | 1036113 | 14431553 | 7.735% | 14344606 | 0 | 14344606 | 99.4% | 10.68 | 100% | 0 | Project Closed | Final Acceptance
5096 | Bayamón | La Alhambra | Luis Rodríguez | Cost Control Company, Inc. | LMC | Jorge del Río Arquitectos | Del Valle Group | 96 | 96 | 0 | 96 | 0 | 730 | 236 | 966 | 32.33% | 793 | 100% | 2009-07-28 | 2011-07-27 | 2012-03-19 | 2011-09-29 | 2012-05-17 | 0 | ARRA-CFP | 0 | 9555000 | 752914.59 | 10307914.59 | 7.88% | 10307914.59 | 0 | 10307914.59 | 100% | 8.2604 | 100% | 0 | Project Closed | Final Acceptance
5094 | Bayamón | Las Gardenias | Jorge Mercado | Housing Promoters | AVP/Prann | Gautier & Benítez | Del Valle Group | 164 | 164 | 0 | 164 | 0 | 671 | 302 | 973 | 45.01% | 1033 | 100% | 1997-05-29 | 1999-03-30 | 2000-01-26 | 2000-03-27 | 2000-06-08 | 0 | 0 | 0 | 7117000 | 152286.5 | 7269286.5 | 2.14% | 7234564.4 | 0 | 7234564.4 | 99.52% | 6.2988 | 100% | 0 | Project Closed | Final Acceptance
5138 | Caguas | Villa del Rey (With Take Over Agreement) | Fco. Palacios | MJ Consulting | AVP / Vivonis & Villegas | Guillermety, Ortiz & Asoc. | American Intl. | 100 | 100 | 0 | 100 | 0 | 620 | 165 | 785 | 26.61% | 903 | 100% | 2000-08-04 | 2002-04-15 | 2002-09-27 | 2003-01-24 | 2003-01-24 | 0 | 0 | 0 | 2110081 | 192030 | 2302111 | 9.101% | 2302111 | 0 | 2302111 | 100% | 9.03 | 100% | 0 | Project Closed | Final Acceptance
5066 | Caguas | Turabo Heights | Luis Rodríguez | MJ Consulting | LMC | Andrés Hernández & Asoc. | Del Valle Group | 254 | 254 | 0 | 254 | 0 | 1300 | 471 | 1771 | 36.23% | 1641 | 100% | 2006-01-16 | 2009-08-07 | 2010-11-21 | 2010-07-15 | 2010-09-30 | 0 | Tax Credit | 0 | 25534940 | 2776195 | 28311135 | 10.87% | 28311135.04 | 0 | 28311135.04 | 100% | 6.4606 | 100% | 0 | Project Closed | Final Acceptance
3038 | Camuy | M. Román Adames | Arturo Acevedo | NFC | CMS | Gutierez & Gutierrez | Pintores Metropolitanos | 64 | 64 | 0 | 64 | 0 | 396 | 491 | 887 | 124% | 1101 | 100% | 1997-05-19 | 1998-06-18 | 1999-10-22 | 2000-05-24 | 2001-03-19 | 0 | 0 | 0 | 3600000 | 403566 | 4003566 | 11.21% | 4003566 | 0 | 4003566 | 100% | 17.2031 | 100% | 0 | Project Closed | Final Acceptance
3053 | Canóvanas | Jesús T. Piñero | Katherine Vázquez | Peregrine Group Inc. | Klassik Builders | Ray Engineers, PSC | LPC&D | 124 | 124 | 0 | 124 | 0 | 913 | 237 | 1150 | 25.96% | 1149 | 100% | 2009-07-15 | 2012-01-13 | 2012-09-06 | 2012-09-06 | 2013-06-30 | 0 | ARRA/CFP | 0 | 16575250 | 2355453 | 18930703 | 14.21% | 18827830.65 | 0 | 18827830.65 | 99.46% | 9.2661 | 100% | 0 | The following items are pending: comments from payroll non-compliance issues, to submit certification # 38. | Final Acceptance
5082 | Carolina | Alturas de Country Club | José González | PROMMA | URS | Jorge del Rio | North Construction | 72 | 72 | 0 | 72 | 0 | 548 | 373 | 921 | 68.07% | 893 | 100% | 2004-09-27 | 2006-03-28 | 2007-04-05 | 2007-03-09 | 2009-04-24 | 0 | CFP | 0 | 5977756.15 | 1066756.51 | 7044512.66 | 17.85% | 7044512.67 | 0 | 7044512.67 | 100% | 12.4028 | 100% | 0 | Project Closed | Final Acceptance
5057 | Carolina | Los Mirtos | José González | Cost Control | CCC-JV | Hernández - Bauzá | Del Valle group | 144 | 144 | 0 | 144 | 0 | 545 | 121 | 666 | 22.2% | 690 | 100% | 2010-11-08 | 2012-05-05 | 2012-09-03 | 2012-09-28 | 2013-07-17 | 0 | Tax Credit | 0 | 14841000 | 272983 | 15113983 | 1.839% | 14923649 | 0 | 14923649 | 98.74% | 4.7917 | 100% | 0 | Project Closed | Final Acceptance
5076 | Carolina | Catañito Gardens | Luis Rodríguez | Inn Capital Housing Division Joint Venture | MD | URS Caribe | RBC Construction | 124 | 124 | 0 | 124 | 0 | 730 | 937 | 1667 | 128.4% | 0 | 100% | 2006-02-08 | 2008-02-07 | 2010-09-01 | 2006-02-08 | 2011-03-28 | 0 | Tax Credit 908-2008 | 0 | 13938100 | 819027.62 | 14757127.62 | 5.876% | 14757127.62 | 0 | 14757127.62 | 100% | 0 | 100% | 0 | Project Closed | Final Acceptance
5102 | Carolina | El Coral | José A. González | Cost Control Company, Inc. | URS Caribe | Francinetti Arquitectos | Orion Contractors | 100 | 100 | 0 | 100 | 0 | 913 | 1268 | 2181 | 138.9% | 2180 | 100% | 2006-01-09 | 2008-07-09 | 2011-12-29 | 2011-12-29 | 2012-06-29 | 0 | Tax Credit | 0 | 9718830 | 1196730.19 | 10915560.19 | 12.31% | 10915560.19 | 0 | 10915560.19 | 100% | 21.8 | 100% | 0 | Project Closed | Final Acceptance
5101 | Carolina | La Esmeralda | Luis Rodríguez | Inn Capital Housing Division Joint Venture | BMA | Carlos E. Betancourt | Construction Zone Corp. | 84 | 84 | 0 | 84 | 0 | 549 | 65 | 614 | 11.84% | 612 | 100% | 2008-12-22 | 2010-06-23 | 2010-08-27 | 2010-08-26 | 2010-12-10 | 0 | Tax Credit | 0 | 4462898 | 32305.97 | 4495203.97 | 0.7239% | 4495203.77 | 0 | 4495203.77 | 100% | 7.2857 | 100% | 0 | Project Closed | Final Acceptance
5075 | Carolina | Lagos de Blasina | José A. González | Cost Control Company, Inc. | CMS | Guillermety, Ortiz & Asoc. (DG3A Design Group, PSC is actually supervising the works) | Mejia Construction | 240 | 240 | 0 | 240 | 0 | 800 | 289 | 1089 | 36.12% | 1077 | 100% | 2009-06-08 | 2011-08-16 | 2012-05-31 | 2012-05-20 | 2012-09-20 | 0 | Tax Credit | 0 | 15411000 | 809595.16 | 16220595.16 | 5.253% | 16220595.16 | 0 | 16220595.16 | 100% | 4.4875 | 100% | 0 | Project Closed | Final Acceptance
5212 | Carolina | Roberto Clemente | Luz Acevedo | SEG | CMS | Jorge del Río | North Connstruction | 126 | 126 | 0 | 126 | 0 | 730 | 242 | 972 | 33.15% | 1038 | 100% | 2004-08-09 | 2006-08-08 | 2007-04-07 | 2007-06-13 | 2008-02-22 | 0 | 0 | 0 | 11135000 | 586931 | 11721931 | 5.271% | 11610417 | 0 | 11610417 | 99.05% | 8.2381 | 100% | 0 | Project Closed | Final Acceptance
3102 | Cataño | Juana Matos I (Fase I) | Luz Acevedo | A & M | AVP / Erwin Rodriguez | Roca & Associates | Quintero Const. | 212 | 212 | 0 | 212 | 0 | 892 | 744 | 1636 | 83.41% | 1628 | 100% | 1997-05-29 | 1999-11-06 | 2001-11-19 | 2001-11-12 | 2002-07-22 | 0 | 0 | 0 | 11640000 | 424857 | 12064857 | 3.65% | 11679790.2 | 0 | 11679790.2 | 96.81% | 7.6792 | 100% | 0 | Project Closed | Final Acceptance
3102 | Cataño | Juana Matos I (Fase II) | Pedro Vega | A & M | BMA | Roca & Associates | Rodríguez & del Valle | 188 | 188 | 0 | 188 | 0 | 1150 | 141 | 1291 | 12.26% | 1179 | 100% | 2002-09-30 | 2005-11-22 | 2006-04-12 | 2005-12-22 | 2006-01-12 | 0 | 0 | 0 | 14243000 | 831198 | 15074198 | 5.836% | 15074198 | 0 | 15074198 | 100% | 6.2713 | 100% | 0 | Project Closed | Final Acceptance
5037 | Cataño | Jardines de Cataño | Pedro Vega | Martinal Property | CMS | Interplan | Francisco Levy Hijo Inc. | 180 | 180 | 0 | 180 | 0 | 810 | 369 | 1179 | 45.56% | 1175 | 100% | 2004-03-22 | 2006-06-09 | 2007-06-13 | 2007-06-10 | 2007-06-14 | 0 | CFP | 0 | 14181600 | 1145235.46 | 15326835.46 | 8.076% | 15326835.44 | 0 | 15326835.44 | 100% | 6.5278 | 100% | 0 | Project Closed | Final Acceptance
3083 | Cayey | Luis Muñoz Morales | Luz Acevedo | MJ Consulting | AVP | Istra Hernández | I Melendez | 280 | 280 | 0 | 280 | 0 | 913 | 416 | 1329 | 45.56% | 1342 | 100% | 1997-08-01 | 2000-01-30 | 2001-03-21 | 2001-04-04 | 2001-09-19 | 0 | 0 | 0 | 12895800 | 452279 | 13348079 | 3.507% | 13348079 | 0 | 13348079 | 100% | 4.7929 | 100% | 0 | Project Close | Final Acceptance
5127 | Cayey | Jardines de Montellanos | Rubén Cotto | Cost Control | CCC-JV | Hernández - Bauzá | Constructora I. Meléndez | 130 | 130 | 0 | 130 | 0 | 836 | 307 | 1143 | 36.72% | 1142 | 100% | 2009-09-30 | 2012-01-13 | 2012-11-15 | 2012-11-15 | 0 | 0 | Tax Credit | 0 | 17226575.94 | 2771225.7 | 19997801.64 | 16.09% | 19987858.29 | 0 | 19987858.29 | 99.95% | 8.7846 | 100% | 0 | Project Closed | Final Acceptance
5157 | Cayey | Brisas de Cayey | Rubén Cotto | MJ Consulting | MD | Ray Engineers PSC | Three O. Construction | 210 | 210 | 0 | 210 | 0 | 1491 | 1200 | 2691 | 80.48% | 1887 | 100% | 2005-01-12 | 2009-02-10 | 2012-05-25 | 2010-03-14 | 2010-04-06 | 0 | Tax Credit | 0 | 24696653 | 5611698 | 30308351 | 22.72% | 30308351 | 0 | 30308351 | 100% | 8.9857 | 100% | 0 | Project Closed | Final Acceptance
3040 | Ciales | Fernando Sierra Berdecía | José Negrón | MAS Corporation | LMC | Luis Flores & Asociados | Constructores Gilmar | 100 | 100 | 0 | 100 | 0 | 780 | 165 | 945 | 21.15% | 983 | 100% | 2001-08-21 | 2003-10-09 | 2004-03-22 | 2004-04-30 | 2006-05-16 | 0 | 0 | 0 | 9285527 | 414901 | 9700428 | 4.468% | 9700428 | 0 | 9700428 | 100% | 9.83 | 100% | 0 | Project Closed | Final Acceptance
3041 | Cidra | Práxedes Santiago | Rubén Cotto | MJ Consulting | URS | Carlos E. Betancourt | DGM Engineering | 124 | 124 | 0 | 124 | 0 | 912 | 901 | 1813 | 98.79% | 2235 | 100% | 2005-04-28 | 2007-10-26 | 2010-04-14 | 2011-06-11 | 2012-03-09 | 0 | Tax Credit | 0 | 11616773 | 3604885 | 15221658 | 31.03% | 14100168 | 0 | 14100168 | 92.63% | 18.0242 | 100% | 0 | Project Closed | Final Acceptance
3043 | Dorado | El Dorado | Frank Nieves | Cost Control Company, Inc. | BMA | Guillermety, Ortiz & Asoc. | Torres & Colón, Inc | 37 | 37 | 0 | 37 | 0 | 430 | 180 | 610 | 41.86% | 666 | 100% | 2007-06-04 | 2008-08-06 | 2009-02-02 | 2009-03-31 | 2009-04-14 | 0 | Tax Credit | 0 | 3991977 | 753900 | 4745877 | 18.89% | 4745877 | 0 | 4745877 | 100% | 18 | 100% | 0 | Project Closed | Final Acceptance
3095 | Fajardo | Pedro Rosario Nieves | José M. Paris Escalera | Inn Capital Housing Division Joint Venture | CMS | Carlos E. Betancourt | Nogama Construction | 168 | 168 | 0 | 168 | 0 | 915 | 27.5 | 942.5 | 3.005% | 904 | 100% | 2008-12-22 | 2011-06-24 | 2011-07-21 12:00 | 2011-06-14 | 2011-09-06 | 0 | Tax Credit | 0 | 16474000 | -148386.07 | 16325613.93 | -0.9007% | 16325613.93 | 0 | 16325613.93 | 100% | 5.381 | 100% | 0 | Project Closed | Final Acceptance
5021 | Fajardo | Puerto Real | Germán Acevedo | A & M | URS | René Vélez Marichal | Quality Const. | 100 | 100 | 0 | 100 | 0 | 945 | 282 | 1227 | 29.84% | 1124 | 100% | 2001-01-22 | 2003-08-24 | 2004-06-01 | 2004-02-20 | 2004-04-20 | 0 | 0 | 0 | 8220000 | 910990 | 9130990 | 11.08% | 9130990 | 0 | 9130990 | 100% | 11.24 | 100% | 0 | Project Closed | Final Acceptance
5204 | Fajardo | Valle Puerto Real | Germán Acevedo | A & M | URS | Enrique Ruiz & Assoc. | Quality Const. | 75 | 75 | 0 | 75 | 0 | 945 | 181 | 1126 | 19.15% | 1129 | 100% | 2001-01-02 | 2003-08-04 | 2004-02-01 | 2004-02-05 | 2004-05-14 | 0 | 0 | 0 | 6316000 | 725553 | 7041553 | 11.49% | 7041553 | 0 | 7041553 | 100% | 15.0533 | 100% | 0 | Project Closed | Final Acceptance
5176 | Fajardo | Santiago Veve Calzada | Robert H. Cole | A & M | BMA | Ramón W. Costacamps | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 730 | 214 | 944 | 29.32% | 906 | 100% | 2004-06-21 | 2006-06-20 | 2007-01-20 | 2006-12-14 | 2007-01-18 | 0 | 0 | 0 | 8559000 | 558385.32 | 9117385.32 | 6.524% | 9117385.32 | 0 | 9117385.32 | 100% | 9.06 | 100% | 0 | Project Closed | Final Acceptance
5183 | Guánica | Jardines de Guánica | Noefebdo Ramírez | JA Machuca | CCC-JV | Donato Design Development | RAMA Construction | 70 | 70 | 0 | 70 | 0 | 732 | 89 | 821 | 12.16% | 794 | 100% | 2009-11-23 | 2011-11-24 | 2012-02-21 | 2012-01-26 | 2012-01-31 | 0 | ARRA/CFP | 0 | 5499000 | 487497.62 | 5986497.62 | 8.865% | 5986498 | 0 | 5986498 | 100% | 11.3429 | 100% | 0 | Project Closed | Final Acceptance
3084 | Guánica | Luis Muñoz Rivera | Noefebdo Ramírez | Cost Control Company, Inc. | CCC-JV | Behar & Ybarra Associates, PSC | F & R Construction Group, Inc. | 124 | 124 | 0 | 124 | 0 | 485 | 423 | 908 | 87.22% | 970 | 100% | 2009-12-14 | 2011-04-12 | 2012-06-08 | 2012-08-10 | 2013-04-18 | 0 | Tax Credit | 0 | 9009000 | 589263.71 | 9598263.71 | 6.541% | 9590758.22 | 0 | 9590758.22 | 99.92% | 7.8226 | 100% | 0 | Project Closed | Final Acceptance
3085 | Guayama | Luis Palés Matos | Rubén Cotto | MJ Consulting | MD (Grupo C) | Guillermety, Ortiz & Asoc. | Héctor M. Valera Inc. | 298 | 298 | 0 | 298 | 0 | 1130 | 0 | 1130 | 0% | 1375 | 100% | 2002-03-25 | 2005-04-27 | 2005-04-27 | 2005-12-29 | 2006-01-03 | 0 | 0 | 0 | 22466000 | 0 | 22466000 | 0% | 22466000 | 0 | 22466000 | 100% | 4.6141 | 100% | 0 | Project Closed | Final Acceptance
5048 | Guayama | San Antonio Carioca | Jorge Mercado | MJ Consulting | MD (Grupo C) | DDHK | Constructora I. Melendez | 200 | 200 | 0 | 200 | 0 | 900 | 568 | 1468 | 63.11% | 1537 | 100% | 2004-03-15 | 2006-08-31 | 2008-03-21 | 2008-05-30 | 2008-07-30 | 0 | Tax Credit | 0 | 18456662 | 1765148 | 20221810 | 9.564% | 20221810 | 0 | 20221810 | 100% | 7.685 | 100% | 0 | Project Closed | Final Acceptance
5131 | Humacao | Jardines de Oriente | José A. González | Cost Control | CCC-JV | GMG Engineering Conslutants PSC | Ossam Construction | 88 | 88 | 0 | 88 | 0 | 365 | 242 | 607 | 66.3% | 937 | 100% | 2010-05-31 | 2011-05-30 | 2012-01-27 | 2012-12-23 | 2012-07-20 | 0 | Tax Credit | 0 | 5939925 | 394882.55 | 6334807.55 | 6.648% | 6334807.55 | 0 | 6334807.55 | 100% | 10.6477 | 100% | 0 | Project Closed | Final Acceptance
5020 | Humacao | Pedro J. Palou | Fco. Palacios | MJ Consulting | URS | R & del Valle | R & del Valle | 150 | 150 | 0 | 150 | 0 | 1095 | 180 | 1275 | 16.44% | 1145 | 100% | 1999-09-27 | 2002-09-25 | 2003-03-24 | 2002-11-15 | 2002-12-20 | 0 | 0 | 0 | 10968000 | 86049 | 11054049 | 0.7845% | 11054049 | 0 | 11054049 | 100% | 7.6333 | 100% | 0 | Project closed. | Final Acceptance
3094 | Humacao | Padre Rivera (Fase I) | Germán Acevedo | MJ Consulting | BMA | Yañez, Mayol & Asoc. | J R Builders | 128 | 128 | 0 | 128 | 0 | 840 | 731 | 1571 | 87.02% | 1548 | 100% | 1997-10-20 | 2000-02-06 | 2002-02-06 | 2002-01-15 | 2002-02-01 | 0 | 0 | 0 | 6625000 | 386337.2 | 7011337.2 | 5.832% | 7011337 | 0 | 7011337 | 100% | 12.0938 | 100% | 0 | Project Closed | Final Acceptance
3094 | Humacao | Padre Rivera (Fase II) | Jorge Mercado | MJ Consulting | BMA | Yañez & Mayol | Jafer Construction | 132 | 132 | 0 | 132 | 0 | 790 | 299 | 1089 | 37.85% | 861 | 100% | 2004-11-10 | 2007-01-08 | 2007-11-03 | 2007-03-21 | 2008-03-12 | 0 | 0 | 0 | 10199820 | 1471265 | 11671085 | 14.42% | 11237717 | 0 | 11237717 | 96.29% | 6.5227 | 100% | 0 | Project Closed | Final Acceptance
3048 | Jayuya | La Montaña | Pedro Vega | MAS Corporation | URS | OPQ-Pablo Quiñonez | Orama Const. | 100 | 100 | 0 | 100 | 0 | 780 | 128 | 908 | 16.41% | 1026 | 100% | 2000-10-23 | 2002-12-11 | 2003-04-18 | 2003-08-15 | 2004-04-26 | 0 | 0 | 0 | 8790000 | 208826 | 8998826 | 2.376% | 8998826 | 0 | 8998826 | 100% | 10.26 | 100% | 0 | Project Closed | Final Acceptance
5064 | Juncos | Colinas de Magnolia | Iván Blanco | MJ Consulting | BMA | Edison Avilés Deliz | Quality Construction | 148 | 148 | 0 | 148 | 0 | 840 | 614 | 1454 | 73.1% | 1201 | 100% | 2004-11-08 | 2007-02-25 | 2008-10-31 | 2008-02-22 | 2008-04-04 | 0 | CFP | 0 | 13860000 | 854562 | 14714562 | 6.166% | 14438155 | 0 | 14438155 | 98.12% | 8.1149 | 100% | 0 | Project Closed | Final Acceptance
3093 | Juncos | Narciso Varona I | Rubén Cotto | MJ Consulting | ISS | DG3A | Torres & Colón, Inc | 88 | 88 | 0 | 88 | 0 | 600 | 199 | 799 | 33.17% | 798 | 100% | 2009-05-29 | 2011-01-18 | 2011-08-05 | 2011-08-05 | 0 | 0 | ARRA/CFP | 0 | 9879114 | 196304 | 10075418 | 1.987% | 10058405.83 | 0 | 10058405.83 | 99.83% | 9.0682 | 100% | 0 | Project Closed | Final Acceptance
5226 | Las Marías | Jardines de las Marías | Arturo Acevedo | NFC | CMS | José L. Irizarry & Assoc. | Lebrón & Assoc. | 55 | 55 | 0 | 55 | 0 | 730 | 32 | 762 | 4.384% | 766 | 100% | 2001-02-27 | 2003-02-26 | 2003-03-30 | 2003-04-04 | 2003-10-03 | 0 | 0 | 0 | 4156000 | 71269 | 4227269 | 1.715% | 4227269 | 0 | 4227269 | 100% | 13.9273 | 100% | 0 | Project Closed | Final Acceptance
5090 | Las Piedras | Jardines de Judely | Iván Blanco | MJ Consulting | URS | René Acosta Ingenieros | Gilmar Roofing & Painting | 32 | 32 | 0 | 32 | 0 | 365 | 118 | 483 | 32.33% | 555 | 100% | 2005-04-04 | 2006-04-03 | 2006-07-30 | 2006-10-11 | 2006-11-02 | 0 | Tax Credit | 0 | 3481720 | 109596.22 | 3591316.22 | 3.148% | 3573356 | 0 | 3573356 | 99.5% | 17.3438 | 100% | 0 | Project Closed | Final Acceptance
5132 | Loíza | Yuquiyú | Luz Acevedo | A & M | BMA | Roca, González Villamil | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 945 | 60 | 1005 | 6.349% | 754 | 100% | 2001-01-22 | 2003-08-24 | 2003-10-23 | 2003-02-15 | 2003-03-21 | 0 | 0 | 0 | 8644000 | 611853 | 9255853 | 7.078% | 9255853.0708 | 0 | 9255853.0708 | 100% | 7.54 | 100% | 0 | Project Closed | Final Acceptance
5186 | Luquillo | Yuquiyú II | Luz Acevedo | Inn Capital Housing Division Joint Venture | BMA | Enrique Ruiz & Asoc. | Unique Builders | 70 | 70 | 0 | 70 | 0 | 730 | 299 | 1029 | 40.96% | 1092 | 100% | 2006-02-15 | 2008-02-14 | 2008-12-09 | 2009-02-11 | 2009-06-09 | 0 | Tax Credit | 0 | 6964727 | 157419 | 7122146 | 2.26% | 6424134.91 | 0 | 6424134.91 | 90.2% | 15.6 | 100% | 0 | Project Closed | Final Acceptance
3056 | Maricao | Juan Ferrer | Noefebdo Ramírez | J. A. Machuca | NFC | René Batista & Assoc. | Comas & Comas | 30 | 30 | 0 | 30 | 0 | 420 | 251 | 671 | 59.76% | 610 | 100% | 2000-08-02 | 2001-09-25 | 2002-06-03 | 2002-04-04 | 2002-04-30 | 0 | 0 | 0 | 2210000 | 178940 | 2388940 | 8.097% | 2388940 | 0 | 2388940 | 100% | 20.3333 | 100% | 0 | Project Closed | Final Acceptance
3057 | Maunabo | Carmen Vda. Martorell (take over agreement) | Rubén Cotto | AVP | AVP | Rene Batista | American Intl. | 50 | 50 | 0 | 50 | 0 | 375 | 327 | 702 | 87.2% | 703 | 100% | 2000-08-18 | 2001-08-27 | 2002-07-20 | 2002-07-22 | 2005-06-02 | 0 | 0 | 0 | 1308221 | 116706 | 1424927 | 8.921% | 1424927 | 0 | 1424927 | 100% | 14.06 | 100% | 0 | Project Closed | Final Acceptance
5126 | Maunabo | Villa Navarro | Rubén Cotto | MJ Consulting | MD | José L. Irizarry & Assoc. | Inversiones OLPERI | 101 | 101 | 0 | 101 | 0 | 907 | 335 | 1242 | 36.93% | 1241 | 100% | 2000-01-24 | 2002-07-18 | 2003-06-18 | 2003-06-18 | 2003-06-18 | 0 | 0 | 0 | 6745000 | 238239 | 6983239 | 3.532% | 6983239 | 0 | 6983239 | 100% | 12.2871 | 100% | 0 | Project Closed | Final Acceptance
5012 | Mayagüez | Ext. Sábalos Gardens | Noefebdo Ramírez | Inn Capital Housing Division Joint Venture | URS Caribe / AVP | Joint Venture | Venegas Construction | 300 | 300 | 0 | 300 | 0 | 1281 | 690 | 1971 | 53.86% | 1963 | 100% | 2005-05-16 | 2008-11-16 | 2010-10-07 | 2010-09-30 | 2011-04-29 | 0 | Tax Credit 908-2008 | 0 | 28259000 | 14189.7 | 28273189.7 | 0.05021% | 29677970 | 0 | 29677970 | 105% | 6.5433 | 100% | 0 | Project Closed | Final Acceptance
4004 | Mayagüez | Sábalos Gdns. | Arturo Acevedo | Zeta | CMS | Héctor Rodríguez Amezquita | Caribe Tecno | 140 | 140 | 0 | 140 | 0 | 881 | 24 | 905 | 2.724% | 900 | 100% | 1999-11-15 | 2002-04-13 | 2002-05-07 | 2002-05-03 | 2002-11-06 | 0 | 0 | 0 | 11790000 | -294361.74 | 11495638.26 | -2.497% | 11495638 | 0 | 11495638 | 100% | 6.4286 | 100% | 0 | Project Closed | Final Acceptance
4006 | Mayagüez | Cuesta las Piedras | Arturo Acevedo | Zeta | CMS | García Cabot | RC Enginering | 142 | 142 | 0 | 142 | 0 | 1093 | 0 | 1093 | 0% | 907 | 100% | 2000-02-10 | 2003-02-06 | 2003-02-06 | 2002-08-05 | 2002-11-21 | 0 | 0 | 0 | 10673000 | 158657 | 10831657 | 1.487% | 10831657 | 0 | 10831657 | 100% | 6.3873 | 100% | 0 | Se aprobó el "close out". Contratista no cobró el total del contrato debido a ajustes deductivos recomendados por el "Program Manager"C.M. Services. | Final Acceptance
4008 | Mayagüez | Yagüez | Arturo Acevedo | ZETA | CMS | GDA Ing. Consultores | NLL Construction | 200 | 200 | 0 | 200 | 0 | 1399 | 0 | 1399 | 0% | 1177 | 100% | 2000-05-22 | 2004-03-20 | 2004-03-20 | 2003-08-12 | 2003-10-06 | 0 | 0 | 0 | 16799671 | -872594 | 15927077 | -5.194% | 15927077 | 0 | 15927077 | 100% | 5.885 | 100% | 0 | Project Closed | Final Acceptance
4005 | Mayagüez | Marini Farm | Frank Nieves | Zeta | BMA | CSA Architects | Empresas Toledo | 100 | 100 | 0 | 100 | 0 | 218 | 50 | 268 | 22.94% | 247 | 100% | 2004-05-12 | 2004-12-15 | 2005-02-03 | 2005-01-14 | 2005-09-07 | 0 | 0 | 0 | 845900 | 30508 | 876408 | 3.607% | 876408 | 0 | 876408 | 100% | 2.47 | 100% | 0 | Project Closed | Final Acceptance
5005 | Mayagüez | Mar y Sol | Noefebdo Ramírez | Zeta | CMS | Arq. Amadeo Pino | RC Enginering | 124 | 124 | 0 | 124 | 0 | 1055 | 14 | 1069 | 1.327% | 1068 | 100% | 2001-01-22 | 2003-12-12 | 2003-12-26 | 2003-12-26 | 2004-05-26 | 0 | 0 | 0 | 10513000 | 269417 | 10782417 | 2.563% | 10782417 | 0 | 10782417 | 100% | 8.6129 | 100% | 0 | Project Closed | Final Acceptance
5133 | Naguabo | Villas del Río | Félix Ortiz | MJ Consulting | MD | N/A | DGM Engineering | 100 | 100 | 0 | 100 | 0 | 730 | 906 | 1636 | 124.1% | 1640 | 100% | 2006-02-15 | 2008-02-14 | 2010-08-08 | 2010-08-13 | 2011-06-27 | 0 | Tax Credit | 0 | 11008930 | 1560851 | 12569781 | 14.18% | 12120952 | 0 | 12120952 | 96.43% | 16.4 | 100% | 0 | Project Closed | Final Acceptance
3063 | Peñuela | Los Flamboyanes | Noefebdo Ramírez | J.A. Machuca | MD | Fuertes, La Font & Asoc. | St. Paul Surety | 24 | 24 | 0 | 24 | 0 | 345 | 502 | 847 | 145.5% | 845 | 100% | 2003-04-15 | 2004-03-24 | 2005-08-08 | 2005-08-07 | 2005-09-26 | 0 | 0 | 0 | 1235996 | 568973 | 1804969 | 46.03% | 1804969 | 0 | 1804969 | 100% | 35.2083 | 100% | 0 | Project Closed | Final Acceptance
1014 | Ponce | Aristides Chavier | Noefebdo Ramírez | MJ Consulting | CCC Joint Venture | Unipro | Del Valle Group | 480 | 480 | 0 | 480 | 0 | 1464 | 552 | 2016 | 37.7% | 2003 | 100% | 2005-08-01 | 2009-08-03 | 2011-02-06 | 2011-01-25 | 2011-08-16 | 0 | Tax Credit 908-2008 | 0 | 43792000 | 2045988.7 | 45837988.7 | 4.672% | 45837989 | 0 | 45837989 | 100% | 4.1729 | 100% | 0 | Project Closed | Final Acceptance
5088 | Ponce | Lirios del Sur | Arturo Acevedo | J.A. Machuca | CMS | CSA Architects | Omega Engineering | 238 | 238 | 0 | 238 | 0 | 730 | 340 | 1070 | 46.58% | 1083 | 100% | 2003-02-12 | 2005-02-10 | 2006-01-16 | 2006-01-30 | 2006-04-12 | 0 | 0 | 0 | 18140000 | 570661 | 18710661 | 3.146% | 18710661 | 0 | 18710661 | 100% | 4.5504 | 100% | 0 | Project Closed | Final Acceptance
1001 | Ponce | Ponce de León ( Take Over Agreement) Fase I | José González | J. A. Machuca | MD | Interplan | American Intl. | 168 | 168 | 0 | 168 | 0 | 732 | 171 | 903 | 23.36% | 862 | 100% | 2000-08-28 | 2002-08-29 | 2003-02-16 | 2003-01-07 | 2003-01-30 | 0 | 0 | 0 | 10990000 | 512271 | 11502271 | 4.661% | 11447321.14 | 0 | 11447321.14 | 99.52% | 5.131 | 100% | 0 | Project Closed | Final Acceptance
1001 | Ponce | Ponce de León (Fase II) | Noefebdo Ramírez | MJ Consulting | BMA | Interplan | Constructora I. Meléndez | 132 | 132 | 0 | 132 | 0 | 730 | 748 | 1478 | 102.5% | 1442 | 100% | 2005-01-10 | 2007-01-09 | 2009-01-26 | 2008-12-22 | 2009-03-31 | 0 | Tax Credit 908-2008 | 0 | 13680284 | 787807 | 14468091 | 5.759% | 14448030 | 0 | 14448030 | 99.86% | 10.9242 | 100% | 0 | Project Closed | Final Acceptance
1002 | Ponce | Santiago Iglesias (Fase I) | Noefebdo Ramírez | Zeta | CMS | CSA | Ferrovial & Agroman | 160 | 160 | 0 | 160 | 0 | 487 | 505 | 992 | 103.7% | 1791 | 100% | 1997-10-28 | 1999-02-26 | 2000-07-15 | 2002-09-23 | 2002-11-02 | 0 | 0 | 0 | 9445984 | 580020 | 10026004 | 6.14% | 9993950 | 0 | 9993950 | 99.68% | 11.1937 | 100% | 0 | Project Closed | Final Acceptance
1016 | Ponce | Rafael López Nussa | Noefebdo Ramírez | MJ Consulting | BMA | URS Caribe | Del Valle Group | 404 | 404 | 0 | 404 | 0 | 1464 | 369 | 1833 | 25.2% | 1832 | 100% | 2004-10-25 | 2008-10-27 | 2009-10-31 | 2009-10-31 | 2010-06-16 | 0 | Tax Credit 908-2008 | 0 | 38744000 | 738951.13 | 39482951.13 | 1.907% | 39482951.13 | 0 | 39482951.13 | 100% | 4.5347 | 100% | 0 | Project Closed | Final Acceptance
1003 | Ponce | Caribe | Rubén Cotto | J.A. Machuca | MD | Lombardo Pérez | Caribe General Constructors | 116 | 116 | 0 | 116 | 0 | 720 | 358.4 | 1078.4 | 49.78% | 1192 | 100% | 2002-12-01 | 2004-11-19 | 2005-11-12 09:36 | 2006-03-07 | 2006-06-07 | 0 | 0 | 0 | 11468000 | 1539402.23 | 13007402.23 | 13.42% | 13007402 | 0 | 13007402 | 100% | 10.2759 | 100% | 0 | Project Closed | Final Acceptance
5022 | Ponce | La Ceiba | Rubén Cotto | MJ Consulting | BMA | Ray Engineers PSC | Jafer Construction | 300 | 300 | 0 | 300 | 0 | 1281 | 283 | 1564 | 22.09% | 1514 | 100% | 2004-10-11 | 2008-04-13 | 2009-01-21 | 2008-12-03 | 2009-01-30 | 0 | Tax Credit | 0 | 29600820 | 1001464.91 | 30602284.91 | 3.383% | 30602284.91 | 0 | 30602284.91 | 100% | 5.0467 | 100% | 0 | Project Closed | Final Acceptance
5095 | Ponce | Las Terrazas | Rubén Cotto | AVP | ISS Corp. | Méndez, Brunner, Badillo & Associates | Homeca Recycling Center Co., Inc. | 100 | 100 | 0 | 100 | 0 | 365 | 0 | 365 | 0% | 344 | 100% | 2009-07-28 | 2010-07-27 | 2010-07-27 | 2010-07-07 | 2010-07-27 | 0 | Mixed Fund | 0 | 1085000 | 0 | 1085000 | 0% | 918124.83 | 0 | 918124.83 | 84.62% | 3.44 | 100% | 0 | Se entregaron los documentos de cierre, pero aun le falta por cobrar al contratista la Cert # 8 - Parcial (10/Agosto/10) $ 36,954.06 y Cert.#10 - Retenido Final (22/Oct/10) $108,500.00, para un Totasl de $145,454.06, mas reclamacion de intereses por pago tardio. Alega el contratista que le han informado de finanzas que los fondos estan congelados, pero no le han explicado razon. | Final Acceptance
1002 | Ponce | Santiago Iglesias (Fase II) | Noefebdo Ramírez | Individual Management | Klassik Builders | CSA | Jafer Construction | 120 | 120 | 0 | 120 | 0 | 790 | 66 | 856 | 8.354% | 855 | 100% | 2009-06-15 | 2011-08-13 | 2011-10-18 | 2011-10-18 | 2012-01-26 | 0 | ARRA | 0 | 14498820 | 637269.47 | 15136089.47 | 4.395% | 15136089.47 | 0 | 15136089.47 | 100% | 7.125 | 100% | 0 | Project Closed | Final Acceptance
3066 | Río Grande | José H. Ramírez | Luz Acevedo | A & M | AVP / ORAM | Raúl Feliciano & Asoc. | J R Builders | 80 | 80 | 0 | 80 | 0 | 540 | 317 | 857 | 58.7% | 853 | 100% | 2000-03-29 | 2001-09-19 | 2002-08-02 | 2002-07-30 | 2002-11-15 | 0 | 0 | 0 | 3404949 | 226802 | 3631751 | 6.661% | 3631751 | 0 | 3631751 | 100% | 10.6625 | 100% | 0 | Project Closed | Final Acceptance
5145 | San Germán | Manuel F. Rossy | Frank Nieves | Municipio de San Germán | MD | Unipro | Cap Con Inc. | 101 | 101 | 0 | 101 | 0 | 732 | 84 | 816 | 11.48% | 815 | 100% | 2009-06-22 | 2011-06-23 | 2011-09-15 | 2011-09-15 | 2011-12-31 | 0 | CFP/ARRA | 0 | 10316000 | 610969.8 | 10926969.8 | 5.923% | 10908277 | 0 | 10908277 | 99.83% | 8.0693 | 100% | 0 | Project Closed | Final Acceptance
5035 | San Juan | Villa Esperanza | Luz Acevedo | 0 | LMC | Guillermety, Ortiz & Asoc. | Del Valle Group | 300 | 300 | 0 | 300 | 0 | 1130 | 233 | 1363 | 20.62% | 1323 | 100% | 2003-06-18 | 2006-07-21 | 2007-03-11 | 2007-01-31 | 2007-03-30 | 0 | CFP | 0 | 19819000 | 1078350.46 | 20897350.46 | 5.441% | 20897350.46 | 0 | 20897350.46 | 100% | 4.41 | 100% | 0 | Project Closed | Final Acceptance
5077 | San Juan | La Rosa | Jorge Mercado | AUTO ADM. | LMC | García Joglar & Arq. | DGM Engineers | 52 | 52 | 0 | 52 | 0 | 730 | 270 | 1000 | 36.99% | 984 | 100% | 2000-10-02 | 2002-10-01 | 2003-06-28 | 2003-06-13 | 2004-07-19 | 0 | 0 | 0 | 4491000 | 510039 | 5001039 | 11.36% | 5001039 | 0 | 5001039 | 100% | 18.9231 | 100% | 0 | Project Closed | Final Acceptance
5026 | San Juan | Los Lirios | Frank Nieves | A & M | CCC Joint Venture | DG3A | Builders Associates, LLC | 150 | 150 | 0 | 150 | 0 | 854 | 275 | 1129 | 32.2% | 1142 | 100% | 2009-11-12 | 2012-03-14 | 2012-12-14 | 2012-12-28 | 2013-04-19 | 0 | ARRA/CFP | 0 | 15075000 | 523404.07 | 15598404.07 | 3.472% | 15598404.07 | 0 | 15598404.07 | 100% | 7.6133 | 100% | 0 | The Contractor submitted a claim for extended overhead by amount of $989,402.32 | Final Acceptance
5099 | San Juan | El Prado | José González | Cost Control | BMA | Ray Architects | Del Valle Group | 220 | 220 | 0 | 220 | 0 | 1260 | 78 | 1338 | 6.19% | 1202 | 100% | 2000-09-15 | 2004-02-26 | 2004-05-14 | 2003-12-31 | 2004-01-28 | 0 | CFP | 0 | 15715000 | 1037001 | 16752001 | 6.599% | 16752001 | 0 | 16752001 | 100% | 5.4636 | 100% | 0 | Project Closed | Final Acceptance
5192 | San Juan | Antigua Via | José González | MAS Corporation | BMA | Rodríguez & del Valle (Design & Build) | Rodríguez & del Valle | 200 | 200 | 0 | 200 | 0 | 882 | 147 | 1029 | 16.67% | 1338 | 100% | 2000-01-10 | 2002-06-09 | 2002-11-03 | 2003-09-09 | 2003-09-09 | 0 | CFP | 0 | 13397000 | 211211 | 13608211 | 1.577% | 13608211 | 0 | 13608211 | 100% | 6.69 | 100% | 0 | Project Closed | Final Acceptance
2010 | San Juan | Vista Hermosa II (Fase II) | José Negrón | MAS Corporation | AVP / Jorge L. Robert | Guillermety, Ortiz & Asoc. | Urban Builders | 476 | 476 | 0 | 476 | 0 | 1216 | 590 | 1806 | 48.52% | 1442 | 100% | 1997-04-07 | 2000-08-04 | 2002-03-17 | 2001-03-19 | 2001-12-13 | 0 | 0 | 0 | 17900000 | 1037096.5 | 18937096.5 | 5.794% | 18371767.14 | 0 | 18371767.14 | 97.01% | 3.0294 | 100% | 0 | Project Closed | Final Acceptance
5031 | San Juan | Jardines de Campo Rico | José Negrón | Cost Control | CMS | DG3A | North Connstruction | 196 | 196 | 0 | 196 | 0 | 750 | 263 | 1013 | 35.07% | 1012 | 100% | 2006-01-30 | 2008-02-18 | 2008-11-07 | 2008-11-07 | 2008-12-04 | 0 | Tax Credit | 0 | 19483000 | 17564 | 19500564 | 0.09015% | 19500564 | 0 | 19500564 | 100% | 5.1633 | 100% | 0 | Project Closed | Final Acceptance
5143 | San Juan | Monte Park | José Negrón | Housing Promoters | AVP / SAGA | Molinary | Fernández & Gutiérrez | 224 | 224 | 0 | 224 | 0 | 874 | 345 | 1219 | 39.47% | 1517 | 100% | 1996-11-01 | 1999-03-24 | 2000-03-03 | 2000-12-27 | 2001-03-09 | 0 | 0 | 0 | 10585212 | 350973 | 10936185 | 3.316% | 10936185 | 0 | 10936185 | 100% | 6.7723 | 100% | 0 | Project Closed | Final Acceptance
5017 | San Juan | San Martín | Luis Rodríguez | Housing Promoters | LMC | Enrique Ruiz & Assoc. | Del Valle Group | 300 | 300 | 0 | 300 | 0 | 1095 | 353 | 1448 | 32.24% | 1631 | 100% | 2003-05-14 | 2006-05-12 | 2007-04-30 | 2007-10-31 | 2008-01-30 | 0 | 0 | 0 | 19703000 | 845652.15 | 20548652.15 | 4.292% | 20180652.15 | 0 | 20180652.15 | 98.21% | 5.4367 | 100% | 0 | Project Closed | Final Acceptance
5023 | San Juan | San Fernando | Luis Rodríguez | Cost Control Company, Inc. | LMC | DDHK | Del Valle Group | 334 | 334 | 0 | 334 | 0 | 1190 | 807 | 1997 | 67.82% | 1965 | 100% | 2004-12-10 | 2008-03-13 | 2010-05-29 | 2010-04-28 | 2010-10-15 | 0 | Tax Credit | 0 | 32133000 | 1051432.05 | 33184432.05 | 3.272% | 33163350.99 | 0 | 33163350.99 | 99.94% | 5.8832 | 100% | 0 | Project Closed | Final Acceptance
5135 | San Juan | Las Dalias | Luis Rodríguez | Housing Promoters | CMS | CSA Architects | Del Valle Group | 240 | 240 | 0 | 240 | 0 | 1195 | 271 | 1466 | 22.68% | 1458 | 100% | 2004-02-25 | 2007-06-03 | 2008-02-29 | 2008-02-22 | 2008-04-22 | 0 | Tax Credit 908-2008 | 0 | 22437872.18 | 818872.18 | 23256744.36 | 3.65% | 23256744.36 | 0 | 23256744.36 | 100% | 6.075 | 100% | 0 | Project Closed | Final Acceptance
5161 | San Juan | El Manatial | Luis Rodríguez | MAS Corporation | CMS | Behar-Ybarra | Del Valle Group | 200 | 200 | 0 | 200 | 0 | 890 | 345 | 1235 | 38.76% | 1234 | 100% | 2004-01-26 | 2006-07-03 | 2007-06-13 | 2007-06-13 | 2008-05-19 | 0 | 0 | 0 | 12929000 | 1024355.41 | 13953355.41 | 7.923% | 13953355.41 | 0 | 13953355.41 | 100% | 6.17 | 100% | 0 | Project Closed | Final Acceptance
5080 | San Juan | Jardines de Cupey | Félix Ortiz | Cost Control Company, Inc. | URS Caribe | Gautier & de Torres | Ferrovial Agroman | 308 | 308 | 0 | 308 | 0 | 1095 | 628 | 1723 | 57.35% | 1660 | 100% | 2006-02-15 | 2009-02-13 | 2010-11-03 | 2010-09-02 | 2011-08-22 | 0 | Tax Credit | 0 | 33630461 | 1042731.4 | 34673192.4 | 3.101% | 34673192.4 | 0 | 34673192.4 | 100% | 5.3896 | 100% | 0 | Project Closed | Final Acceptance
5040 | San Juan | Jardines de Sellés Fase I (Take over agreement) | Luz Acevedo | 0 | BMA | URS Dames & Moore | Urban Builders (St. Paul Surety) | 184 | 184 | 0 | 184 | 0 | 90 | 0 | 90 | 0% | 114 | 100% | 2003-08-20 | 2003-11-17 | 2003-11-17 | 2003-12-12 | 2004-02-17 | 0 | CFP | 0 | 9975000 | 231719 | 10206719 | 2.323% | 10206719 | 0 | 10206719 | 100% | 0.61957 | 100% | 0 | Project Closed | Final Acceptance
5040 | San Juan | Jardines de Sellés (Fase II) | Luz Acevedo | Housing Promoters | BMA | URS Caribe | Rodríguez & del Valle | 216 | 216 | 0 | 216 | 0 | 1095 | 320 | 1415 | 29.22% | 1415 | 100% | 2002-06-17 | 2005-06-15 | 2006-05-01 | 2006-05-02 | 2007-05-27 | 0 | 0 | 0 | 15268000 | 968748 | 16236748 | 6.345% | 16236748 | 0 | 16236748 | 100% | 6.5509 | 100% | 0 | Project Closed | Final Acceptance
5015-5140 | San Juan | Las Gladiolas I & II | Félix Ortiz | MAS Corp. | CCC-JV | Méndez-Brunner | Del Valle Group | 676 | 676 | 0 | 676 | 0 | 365 | 77 | 442 | 21.1% | 449 | 100% | 2011-04-11 | 2012-04-09 | 2012-06-25 | 2012-07-03 | 2013-02-08 | 0 | CFP | 0 | 2932000 | 129200.55 | 3061200.55 | 4.407% | 3061200.55 | 0 | 3061200.55 | 100% | 0.6642 | 100% | 0 | Pending Close Out | Final Acceptance
2003 | San Juan | Puerta de Tierra | Pedro Vega | Cost Control Company, Inc. | LMC | Guillermety, Ortiz & Asoc. | Homeca Recycling 2007-0498A | 148 | 148 | 0 | 148 | 0 | 150 | 300 | 450 | 200% | 543 | 100% | 2007-03-22 | 2007-08-18 | 2008-06-13 | 2008-09-15 | 0 | 0 | CFP | 0 | 678000 | 152491.82 | 830491.82 | 22.49% | 830492 | 0 | 830492 | 100% | 3.6689 | 100% | 0 | Project Closed | Final Acceptance
2003 | San Juan | New Puerta de Tierra | Pedro Vega | Cost Control Company, Inc. | LMC | Guillermety, Ortiz & Asoc. | Cué & López Construction, Inc | 85 | 85 | 0 | 85 | 0 | 900 | 20 | 920 | 2.222% | 823 | 100% | 2008-11-10 | 2011-04-28 | 2011-05-18 | 2011-02-11 | 2011-05-17 | 0 | CFP/Línea de Crédito | 0 | 16770000 | 813871.99 | 17583871.99 | 4.853% | 17583871.99 | 0 | 17583871.99 | 100% | 9.6824 | 100% | 0 | Project Closed | Final Acceptance
2004 | San Juan | San Agustín | José M. Paris Escalera | AM Contractors | Klassik Builders | Ray Engineers PSC | Cuè & López Construction, Inc | 84 | 84 | 0 | 84 | 0 | 570 | 304 | 874 | 53.33% | 869 | 100% | 2009-12-14 | 2011-07-06 | 2012-05-05 | 2012-05-01 | 2012-07-18 | 0 | ARRA | 0 | 3746000 | 1029880.39 | 4775880.39 | 27.49% | 4775880.39 | 0 | 4775880.39 | 100% | 10.3452 | 100% | 0 | Project Closed | Final Acceptance
2012 | San Juan | Villa España | Pedro Vega | Cost Control Company | LMC | Ray Engineers, PSC | Rodríguez & del Valle | 500 | 500 | 0 | 500 | 0 | 1280 | 929 | 2209 | 72.58% | 2208 | 100% | 2003-09-29 | 2007-03-31 | 2009-10-15 | 2009-10-15 | 2010-10-21 | 0 | Tax Credit | 0 | 33768000 | 1862123 | 35630123 | 5.514% | 35630123 | 0 | 35630123 | 100% | 4.416 | 100% | 0 | Project Closed | Final Acceptance
3090 | Salinas | Bella Vista | Félix Ortiz | MJ Consulting | Klassik Builders | INTEGRA | LPC&D | 100 | 100 | 0 | 100 | 0 | 730 | 160 | 890 | 21.92% | 889 | 100% | 2009-09-08 | 2011-09-07 | 2012-02-14 | 2012-02-14 | 2012-07-16 | 0 | ARRA | 0 | 10500000 | 749675.93 | 11249675.93 | 7.14% | 11249675.93 | 0 | 11249675.93 | 100% | 8.89 | 100% | 0 | 0 | Final Acceptance
5092 | San Lorenzo | La Lorenzana | Iván Blanco | MJ Consulting | URS | René Acosta Ingenieros | CD Builders | 100 | 100 | 0 | 100 | 0 | 730 | 351 | 1081 | 48.08% | 1147 | 100% | 2005-09-14 | 2007-09-13 | 2008-08-29 | 2008-11-04 | 2009-09-17 | 0 | Tax Credit | 0 | 10310000 | 828444.55 | 11138444.55 | 8.035% | 11138444.55 | 0 | 11138444.55 | 100% | 11.47 | 100% | 0 | Project Closed | Final Acceptance
3087 | San Sebastian | Andrés Méndez Liceaga | Arturo Acevedo | Inn Capital Housing Division Joint Venture | CMS | Interplan | RC Engineering | 150 | 150 | 0 | 150 | 0 | 960 | 729 | 1689 | 75.94% | 1688 | 100% | 2004-05-24 | 2007-01-08 | 2009-01-06 | 2009-01-06 | 2009-02-16 | 0 | Tax Credit | 0 | 13130000 | 401586.86 | 13531586.86 | 3.059% | 13531587 | 0 | 13531587 | 100% | 11.2533 | 100% | 0 | Project Closed | Final Acceptance
5144 | Santa Isabel | Rincón Taíno | Rubén Cotto | J. A. Machuca | BMA | Hernández - Bauzá | Constructora I. Meléndez | 100 | 100 | 0 | 100 | 0 | 810 | 499 | 1309 | 61.6% | 1087 | 100% | 2003-07-28 | 2005-10-14 | 2007-02-25 | 2006-07-19 | 2006-09-30 | 0 | 0 | 0 | 7231087 | 175900 | 7406987 | 2.433% | 6372476 | 0 | 6372476 | 86.03% | 10.87 | 100% | 0 | Las OC # 7 y 8 fueron sometidas por el CM, pero le fueron devueltas para aclaracion o correccion, ya que el NGC no esta de acuerdo con el tiempo de extension otorgado y los "supporting documents". Posteriormente el CM las entrego fuera del termino de vigencia y las mismas no se pudieron procesar. El contratista sometio demanda y se efectuo reunion entre ambas representaciones legales. Se llego a un acuerdo: AVP de pagar lo que se le adeudaba por concepto de daños liquidos y retenido, Contratista: No reclamar "extended overhead" ni la OC #8. Esto hace varios meses y AVP tiene pendiente procesar los pagos correspondientes. | Final Acceptance
5198 | Toa Alta | Jardines de San Fernando | Luis Rodríguez | Housing Promoters | MD | URS Caribe, LLP | Orion Contractors | 51 | 51 | 0 | 51 | 0 | 800 | 1627 | 2427 | 203.4% | 2502 | 100% | 2006-01-09 | 2008-03-18 | 2012-08-31 | 2012-11-15 | 2013-10-15 | 0 | BFP-2003 | 0 | 7227000 | -982226.89 | 6244773.11 | -13.59% | 6244773.11 | 0 | 6244773.11 | 100% | 49.0588 | 100% | 0 | The PRPHA and the Contractor signed a Termination by Convinience (TBC), where the contractor grants a creditfor the amount of $2,182,368.61 for the remaining work phase IV,V and VIII. The PRPHA extends the contract by 744 calendar days providing a substantial termination effective at the August 31, 2012. The contractor walves its claim for extended overhead. | Final Acceptance
3069 | Toa Baja | El Toa | Jorge Mercado | MJ Consulting | AVP | Soler Cloquel & Asoc. | Royal Ins. | 80 | 80 | 0 | 80 | 0 | 669 | 458 | 1127 | 68.46% | 1205 | 100% | 1997-06-30 | 1999-04-29 | 2000-07-30 | 2000-10-17 | 2001-05-18 | 0 | 0 | 0 | 4045086 | 299127 | 4344213 | 7.395% | 4344213 | 0 | 4344213 | 100% | 15.0625 | 100% | 0 | Project Closed | Final Acceptance
5193 | Trujillo Alto | Los Rosales | José M. Paris Escalera | Peregrine Group Inc. | Klassik Builders | URS Caribe, LLP | Cidra Excavation, SE | 74 | 74 | 0 | 74 | 0 | 730 | 138 | 868 | 18.9% | 821 | 100% | 2009-11-16 | 2011-11-15 | 2012-04-01 | 2012-02-15 | 2012-08-14 | 0 | ARRA | 0 | 7947800 | 1458351.48 | 9406151.48 | 18.35% | 9406151.48 | 0 | 9406151.48 | 100% | 11.0946 | 100% | 0 | Project Closed | Final Acceptance
3071 | Vega Alta | Fco. Vega Sánchez | José Negrón | MJ Consulting | LMC | Hernández - Bauzá | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 782 | 109 | 891 | 13.94% | 890 | 100% | 2000-10-02 | 2002-11-22 | 2003-03-11 | 2003-03-11 | 2003-04-11 | 0 | 0 | 0 | 9309000 | 70614.85 | 9379614.85 | 0.7586% | 9379616 | 0 | 9379616 | 100% | 8.9 | 100% | 0 | Project Closed | Final Acceptance
5105 | Vega Alta | Las Violetas | Luis Rodríguez | Cost Control Company, Inc. | ISS | URS Dames & Moore | Del Valle Group | 88 | 88 | 0 | 88 | 0 | 730 | 150 | 880 | 20.55% | 1000 | 100% | 2006-02-01 | 2008-01-31 | 2008-06-29 | 2008-10-28 | 2009-09-30 | 0 | Tax Credit | 0 | 9203600 | 46081.53 | 9249681.53 | 0.5007% | 9007681.53 | 0 | 9007681.53 | 97.38% | 11.3636 | 100% | 0 | Project Closed | Final Acceptance
3073 | Villalba | Efraín Suárez Negrón | Arturo Acevedo | J.A. Machuca | CMS | Yañez & Mayol | Ravaro Construction | 60 | 60 | 0 | 60 | 0 | 660 | 295 | 955 | 44.7% | 1240 | 100% | 2002-04-15 | 2004-02-03 | 2004-11-24 | 2005-09-06 | 2005-09-06 | 0 | 0 | 0 | 4033500 | 93123 | 4126623 | 2.309% | 4126623 | 0 | 4126623 | 100% | 20.6667 | 100% | 0 | Project Closed | Final Acceptance
5164 | Villalba | Maximino Miranda Jiménez | Félix Ortiz | Municipio de Villalba | Klassik Builders | LPA Group, Arq. | Constructora I. Meléndez | 100 | 100 | 0 | 100 | 0 | 732 | 180 | 912 | 24.59% | 911 | 100% | 2009-05-20 | 2011-05-21 | 2011-11-17 | 2011-11-17 | 2012-01-19 | 0 | CFP/ARRA | 0 | 12392438 | 408291.81 | 12800729.81 | 3.295% | 12800729.81 | 0 | 12800729.81 | 100% | 9.11 | 100% | 0 | Project Closed | Final Acceptance
5067 | Yauco | Ext. Santa Catalina | Rubén Cotto | Inn Capital Housing Division Joint Venture | URS | René Acosta Ingenieros | A. Rivera & Asociados | 24 | 24 | 0 | 24 | 0 | 548 | 319 | 867 | 58.21% | 814 | 100% | 2006-01-16 | 2007-07-17 | 2008-05-31 | 2008-04-09 | 2008-08-26 | 0 | CFP-2003 | 0 | 1972404 | 50556.96 | 2022960.96 | 2.563% | 2022961 | 0 | 2022961 | 100% | 33.9167 | 100% | 0 | Project Closed | Final Acceptance
| 7 | Active | [5 empty] | 192 | 16 | 0 | 16 | 0 | [14 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | Active
| 2 | Stopped | [5 empty] | 192 | 16 | 0 | 16 | 0 | [14 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | Stopped
| 10 | Substantial | [5 empty] | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 13.542 |  |  |  | Substantial Completion
| 110 | Final Acceptance | [5 empty] | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 9.8658 |  |  |  | Final Acceptance
Total | 129 | [6 empty] | 20299 | 19627 | 78 | 19705 | 60 | [14 empty] | 1493538072.27 | 97622150.87 | 1591160223.14 |  | 1558880043.8708 | 1271462.02 | 1560151505.8908 |  | 10.1721 |  | 0 |  | Total
| Revised by: |  |  |  | Approved by: | [19 empty] | Approved by:
|  | Luz M. Acevedo Pellot, PE |  |  |  |  | Germán Acevedo Marín, PE | [18 empty] | Arturo A. Garcia de la Noceda Castro, PE
|  | Project Coordinator |  |  |  |  | Director | [18 empty] | Deputy Administrator
|  | Construction Management Bureau |  |  |  |  | Construction Management Bureau | [18 empty] | Development and Construction Area
Report Date: |  |  | 2014-04-30
Report Last Revision Date: |  |  | 2014-05-10
Notes/Notas:
CMB Monthly Report is prepared for the use of Construction and Development Area. The Associate Administrator will approve any use of this report outside this area and must have his signature to be valid.
Informe preparado para uso del Área de Desarrollo y Construcción de Proyectos. El Administrador Asociado aprobará cualquier uso de este Informe fuera del Área y debe tener su firma para ser válido.
Information is provided by PRPHA Project Monitors, and is subject to change.
La Información es suministrada con los datos que proveen los Monitores de Proyectos, por lo que está sujeta a cambios.
Final Acceptance Report contains all Projects. This report is not worked by fiscal or natural year, it is a report that contains cumulative information and not all projects present monthly changes.
El Informe de "Final Acceptance" contiene todos los Proyectos. No se trabaja por Año Natural o Año Fiscal; es un reporte que contiene información acumulativa y no en todos los Proyectos se presentan cambios mensuales.
NOTIFICACIÓN DE CONFIDENCIALIDAD: Este Informe y cualquier archivo transmitido en ella pueden contener información confidencial, privilegiada y/o privada bajo las leyes aplicables. Se utiliza solamente para el uso o entidad a que se dirige. Si usted no es el destinatario intencional, se le notifica que cualquier uso, diseminación o copia de esta Informe se prohíbe estrictamente. Si usted recibe esta Informe por error, notificar al remitente inmediatamente y destruir el material en su totalidad.
CONFIDENTIALITY NOTICE: This report and any files transmitted with it may contain information that is confidential, privileged and exempt from disclosure under applicable law. It is intended solely for the use of the individual or entity to which it is addressed. If you are not the intended recipient, you are hereby notify that any use, dissemination or copying of this report is strictly prohibited. If you have received this communication by error, immediately contact the sender and destroy the material in its entirety, whether in electronic of hard copy format.
Note on AC15: lvlynn: Discrepancia: $98,932 Inf. Monitor
Note on H48: lvlynn: Contratista Default Target Engineering
Note on W77: lvlynn: 9-junio-09 Final
Note on W81: lvlynn:
Note on AC96: OC 1 @ 13
Note on Z97: lvlynn: CFP-Línea de Crédito

## SUSTANTIAL PROJECTS MONTLY REPO
A | B | C | D | E | F | G | H | I | J | K | L=J+K | M | N | O | P=N+O | Q=O/N | R=DATE-T | S=R/P | T | U=T+N-1 | V=T+P-1 | W | X | Y | Z | AA | AB | AC | AD=AB+AC | AE=AC/AB | AF | AG | AH=AF+AG | AI=AH/AD | AJ=(W-T)/I | AK |  | AK | AL
RQ | Municipality | Name of the Project | PHAPR Monitor | Management Agent | Construction Manager/PM | Designer (A/E) | Contractor | Units |  |  |  |  | Times | [5 empty] | Dates | [5 empty] | Funds | [9 empty] | Certified Days/Unit | % Progress | Monthly Employment | Executive Summary | Status
[8 empty] | Total Dwelling Units | Previous Completed Dwelling Units | Completed Dwelling Units for this Period | Total Completed Dwelling Units | Dwelling Units Forecast for next Month | Contruction Period (Cal. Days) | Time Extension (Cal. Days) | Revised Construction Period (Cal. Days) | % Extended Time | Elapsed Time (Cal. Days) | Elapsed Time (%) | Construction Start Date | Original Completion Date | Revised Construction Completion Date | Substantial Completion Date | Final Acceptance Date | Registered at Controller Contract Termination Date | Funds Proceeds | Funds Obligation Date | Original Construction Contract Amount | Approved Change Orders Amount ($) | Revised Construction Contract Amount | % Of Change Orders | Previous Certified Amount | Certified this Period | Total Certified Amount | Certified Amount (%)
3025 | Carolina | Felipe Sánchez Osorio (Demolition) | Luis Rodríguez | N/A | Municipio de Carolina | State Engineering | Municipio de Carolina | 32 | 26 | 0 | 26 | 0 | 120 | 0 | 120 | 0% | 259 | 215.8% | 2013-08-14 | 2013-12-11 | 2013-12-11 | 0 | 0 | 0 | 0 | 0 | 336510 | 0 | 336510 | 0% | 27516.72 | 122054.24 | 149570.96 | 44.45% |  | 0% | 0 | ♦ Project Situation according to the CPM Uptaded: Phase I was completed on November 27, 2013. ♦ Reasons of the Delay (if applies) N/A ♦ Change Order in PRPHA pending for approval: N/A ♦ Extraordinary Situations with Relocation (if applies)- N/A ♦ Situations with Governmental Agencies (if applies): N/A ♦ Others situations that are affecting the project (if Applies): N/A | Active
5127 | Arecibo | La Meseta | Pedro Vega | Housing Promoters, Inc. | AVP | ERA | Maglez Engineering & Contractors, Corp. | 0 | 0 | 0 | 0 | 0 | 365 | 0 | 365 | 0% | 394 | 107.9% | 2013-04-01 | 2014-03-31 | 2014-03-31 | 0 | 0 | 2014-03-31 | CFP | 0 | 1602797 | 0 | 1602797 | 0% | 979943.16 | 71165.27 | 1051108.43 | 65.58% |  | 0% | 0 | • Project Situation: Some submmittal requirement from designer are delaying the Contractor's time to make purchase orders or solve construction problems as design error for primary system upgrade. • Project Status: Last CPM Updated february 28,2014, refected a reduction of project delay from 49 days behind schedule. There is a CO #1 with 14 calendars days pending for PRPHA approval. New letter of intents are in negotiation that can reflect additional extension claim. • Change Orders: CO #1 $41,193.88 where send to PRPHA. • Last Certification: #11 february 28, 2014 • Relocation issues: There is not Relocation issues. • Goverment Agencies issues: AEE are requiring change to approved design that represent additional cost to project. • Other Situation issues: There is not AAA endorsement. this month the designer submmit the endorsement amedment. | Active
4011 | Mayaguez | Rafael Hernandez (El Kennedy) | Noefebdo Ramírez | JA Machuca | Klassik Builders | Hernán Jr. Machado Ingenieros Consultores | F & R Construction | 190 | 26 | 0 | 26 | 24 | 1094 | 153 | 1247 | 13.99% | 926 | 74.26% | 2011-10-17 | 2014-10-14 | 2015-03-16 | 0 | 0 | 2016-02-07 | CFP | 0 | 21797000 | 446287.81 | 22243287.81 | 2.047% | 13868385.06 | 204312.21 | 14072697.27 | 63.27% |  | 0% | 0 | • Project situation according to the CPM updated: According to the last CPM updated, the project finish date is September 3, 2015. The contract revisedconstruction completion date is March 16,2015. That represent 171 days of delay. When thechange order # 9 be approvedthe completion date move to May 30, 2015. the Change Order # 10 included 10 aditional days for weather conditions. Then represent 58 days of delay. • Reasons of the Delay: One reasons is the delay for termination and delivery of modernized units by the Contractors. The lead and asbestos abatement started on February 3,2014 to enclosure the building # 4. The buildingcome to be ready to start the works on March 21,2014, No contruction works can't do it into the buildings. Those impact the crithical path which is total responsability of the contractor. In special the building # 18, which in the next building in the modernization sequence and are stopped for 108 days. • Change Order in PRPHA pending for approval:. The CO # 9 (193,914.32 and include 75 calendar days extension) and change order # 10 (of $562,564.73 and include 10 calendar days extension) • Payments Certifications Status: The Contractor has pending to submit to PRPHA the Certifications for partial payment of # 30 (February 2014 period) and # 31 (March 2014 period) • Extraordinary Situations with Relocation - N/A • Situations with Governmental Agencies: The tapping conection for the potable water services, under the PR #2 state road was not do it in this period. This tapping is a change order in a process of negotiation. The AAA final endosement depend of finish this connection works. The Puerto Rico Power Authority present a new request to install other facilities for existingsanitary pump station. That works were not contemplted in the design. • Others situations that are affecting the project: The installationof the restrainers in the 36 inches ductile iron forced line was not completed in this period. A 70% of the total pipe line need to be reinstalling. A wprkplan was by KBI to the Contractor to define this work to be done during summer school vacation as requested. | Active
3105 | San Juan | Ext. Manuel A. Pérez | Arturo Acevedo | MAS Corp. | Klassik Builders | DDHK | LPC&D | 324 | 188 | 12 | 200 | 12 | 1098 | 433 | 1531 | 39.44% | 1385 | 90.46% | 2010-07-15 | 2013-07-16 | 2014-09-22 | 0 | 0 | 2015-08-06 | HOPE IV | 0 | 24800000 | 1110120.04 | 25910120.04 | 4.476% | 19847694.84 | 161086 | 20008780.84 | 77.22% |  | 0% | 0 | • Project situation according to the CPM updated • Reasons of the Delay (if applies) • Payments Certifications Status- Lastcertification rendered for payment is certification # 42, for the period of January 2014. • Change Orders: • Extraordinary Situations with Relocation (if applies)-N/A • Situations with Governmental Agencies (if applies)-N/A • Others situations that are affecting the project (if applies)-N/A • Withheld: | Active
5034 | San Juan | Alturas de Cupey | José M. Paris | SP Management Corp. | Klassik Builders | CSA | F&R Construction | 96 | 48 | 16 | 64 | 0 | 732 | 256 | 988 | 34.97% | 1057 | 107% | 2011-06-08 | 2013-06-08 | 2014-02-19 | 0 | 0 | 2015-06-20 | CFP | 0 | 7936000 | 1003018.78 | 8939018.78 | 12.64% | 7832237.98 | 470242.15 | 8302480.13 | 92.88% |  | 0% | 0 | • Project situation according to the CPM updated: According to the last CPM updated on June 2013, the project is 72 calendar days ahead schedule with a possible termination date on December 19, 2013. • Reasons of the Delay (if applies) • Bad execution by the Contractor (if applies)- N/A • Change Orders pending for approval - N/A • Others (if applies) - a) Weather and site conditions (Soil Moisture) • Change Order in PRPHA pending for approval: N/A • Latest Certification: The last certification for payment submitted by the Contractor correspond to the period of July 26, 2013 thru August 25, 2013 (Certification #27 for the amount of $470,242.15 • Extraordinary Situations with Relocation (if applies) - N/A • Situations with Governmental Agencies (if applies) - N/A • Others situations that are affecting the project (if applies) - N/A | Active
5068 | San Juan | Las Amapolas (Demolition) | Noefebdo Ramírez | SP Management Corp. | AVP | Integra | Anibal Díaz Construction, Inc. | 204 | 138 | 50 | 188 | 16 | 365 | 0 | 365 | 0% | 176 | 48.22% | 2013-11-05 | 2014-11-04 | 2014-11-04 | 0 | 0 | 2015-10-30 | CFP | 0 | 948000 | 0 | 948000 | 0% | 231193.27 | 0 | 231193.27 | 24.39% |  | 0% | 0 | • Project situation according to CPM (updated): According to the CPM, the project is on schedule. • Reasons of Delay: none • Change Orders in PRPHA pending for Approval: none • Payments CertificationS Status: The contractor has pending to submit to PRPHA the certificactions for the partial Payments # 3 (February 2014) and #4 (March 2014 period) • Extraordinary situations with Relocation: N/A • Situations with Governmental Agencies: none • Other situations that are affecting the project: No report in this moment. | Active
5028 | Yauco | Ana Catalina Rodríguez Vélez (Santa Catalina) | Arturo Acevedo | JA Machuca | AVP | URS Caribe LLC | La Mar Construction Corporation | 200 | 154 | 0 | 154 | 8 | 1098 | 339 | 1437 | 30.87% | 1525 | 106.1% | 2010-02-25 | 2013-02-26 | 2014-01-31 | 0 | 0 | 2014-11-26 | ARRA/Mixed | 0 | 17447000 | 1678841 | 19125841 | 9.623% | 17208971.22 | 242602.15 | 17451573.37 | 91.25% |  | 0% | 0 | • Project situation according to CPM (updated): • Reasons of Delay: • Change Orders in PRPHA pending for Approval: • latest Certification: Last certification rendered for payment is certification # 49 (February 2014) • Extraordinary situations with Relocation: N/A • Situations with Governmental Agencies: N/A • Other situations that are affecting the project: N/A | Active
5011 | San Juan | Jardines del Paraíso | José Negrón | Cost Control Company, Inc. | BMA | Andrés Hernández & Asoc. | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 41759 | #DIV/0! | 0 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | 0% | 0 | Proyecto en Re-Subasta. Subasta declarada Desierta. No se ha Comenzado el proyecto. | Stoped
3049 | Lajas | Las Américas | Noefebdo Ramírez | Inn Capital Housing Division Joint Venture | none | URS Caribe, LLP | none | 80 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | #DIV/0! | 41759 | #DIV/0! | 0 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | 0% | 0 | Design completed. Pending for will be assigned construction funds by PHA. | Stoped
3100 | Aguadilla | Agustín Stahl I | Arturo Acevedo | American Management Corp. | CCC-JV | René Acosta Arquitectos | Karimar Construction, Inc. | 180 | 180 | 0 | 180 | 0 | 915 | 192 | 1107 | 20.98% | 1100 | 100% | 2010-03-23 | 2012-09-22 | 2013-04-02 | 2013-03-27 | 0 | 0 | ARRA/CFP | 0 | 13875675 | 597322.95 | 14472997.95 | 4.305% | 13367679 | 0 | 13367679 | 92.36% | 6.1111 | 0% | 0 | Project started on march 23, 2010. substantial completion was awarded on March 27 2013 Last certification rendered for payment is certification # 38, for the period of March 1 to 30, 2013. | Substantial Completion
5201 | Cayey | Alturas de Montellano | Jorge Mercado | Municipio | LMC | Arq. José Luzunaris | RC Group S.E. | 80 | 50 | 0 | 50 | 0 | 730 | 846 | 1576 | 115.9% | 1970 | 100% | 2001-09-04 | 2003-09-03 | 2005-12-27 | 2007-01-26 | 0 | 0 | CFP | 2001-11-21 | 4790000 | 2327268.37 | 7117268.37 | 48.59% | 7036300.8 | 0 | 7036300.8 | 98.86% | 24.625 | 0% | 0 | Nunca se aprobaron las ordenes de cambio #17 y #18 porque el contratista no sometió los documentos solicitados por el Área de Adquisición y Contratación. Nunca se le otorgó el "Final Acceptance". El caso esta siendo atendido en la División Legal de la Admnisitración de Vivienda Pública. Queda un balance de $80,967.57 en espera se resuelva la controversia. | Substantial Completion
3089 | Juana Díaz | Villa del Parque (Take over agreement) | Rubén Cotto | J.A. Machuca | MD | GMG Eng. Consultants | (USF & G) | 100 | 100 | 0 | 100 | 0 | 547 | 746 | 1293 | 136.4% | 552 | 100% | 2000-12-18 | 2002-06-17 | 2004-07-02 | 2002-06-23 | 0 | 0 | CFP | 2000-09-30 | 3105100 | 239005.38 | 3344105.38 | 7.697% | 3171314 | 0 | 3171314 | 94.83% | 5.52 | 0% | 0 | El "final acceptance" le fue entregado a la Administracion del proyecto , JA Machuca, no obstante los mismos no lo han firmado ya que la Aseguradora no ha sometido aun los documentos de garantía de techo. Se le indicó vervalmente al Ing. Carrasquillo, representante de la Aseguradora. | Substantial Completion
3093 | Juncos | Narciso Varona Fase II | José González | MJ Consulting | AVP | DG3A Design Group, PSC | F & R Construction Group, Inc. | 172 | 172 | 0 | 172 | 0 | 1220 | 235 | 1455 | 19.26% | 1385 | 100% | 2010-02-24 | 2013-06-27 | 2014-02-17 | 2013-12-10 | 0 | 0 | Arra/Mixed | 0 | 13189000 | 822958.39 | 14011958.39 | 6.24% | 13762592.18 | 0 | 13762592.18 | 98.22% | 8.0523 | 0% | 0 | Project is almost completed. | Substantial Completion
5053 | Mayagüez | Ramírez de Arellano | Pedro Vega | JA Machuca | LMC | GMG Engineering | Comas & Comas Contractors, Corp | 80 | 80 | 0 | 80 | 0 | 720 | 661 | 1381 | 91.81% | 1375 | 100% | 2009-07-13 | 2011-07-02 | 2013-04-23 | 2013-04-18 | 0 | 0 | ARRA/CFP | 0 | 4040000 | 2215708.24 | 6255708.24 | 54.84% | 6011262.53 | 0 | 6011262.53 | 96.09% | 17.1875 | 0% | 0 | Final Completion and Close Out era specting for: 1) PRPHA approval CO#9 and CO#10; 2)Contractor correction of payroll defiecience | Substantial Completion
3058 | Moca | José N. Gándara | Noefebdo Ramírez | NFC | CMS | Ray Engineers PSC | Moss Construction | 74 | 74 | 0 | 74 | 0 | 896 | 73 | 969 | 8.147% | 940 | 100% | 1999-11-08 | 2002-04-21 | 2002-07-03 | 2002-06-05 | 0 | 0 | CFP-02 | 2000-01-13 | 4671000 | 238289 | 4909289 | 5.101% | 4805897.22 | 0 | 4805897.22 | 97.89% | 12.7027 | 0% | 0 | The close out was not completed because the Contractor not submit to PRPHA the final documents required by the Construction and Management Bureau and the Legal Division of the PRPHA. The solution of this case was referred to Legal Division of the PRPHA. | Substantial Completion
5088 | Ponce | Lirios del Sur | Arturo Acevedo | MJ Consulting | CMS | CSA | Caribe General Constructors | 400 | 400 | 0 | 400 | 0 | 791 | 487 | 1278 | 61.57% | 1267 | 100% | 2009-03-02 | 2011-05-01 | 2012-08-30 | 2012-08-20 | 0 | 0 | CFP | 0 | 16598000 | 2352431.7 | 18950431.7 | 14.17% | 17140589.22 | 0 | 17140589.22 | 90.45% | 3.1675 | 0% | 0 | Project started in march 2009, The contrator finished the instalation of the luminaries on the fence of the west side of the project. Last certification rendered for payment is certification # 35, which is the 50% of retainage. | Substantial Completion
5056 | Guaynabo | Loa Alamos | José González | Municipio de Guaynabo | Klassik | Hernández-Bauzá | Homeca Recycling | 376 | 376 | 0 | 376 | 0 | 549 | 0 | 549 | 0% | 547 | 100% | 2012-09-17 | 2014-03-19 | 2014-03-19 | 2014-03-18 | 0 | 0 | CFP | 0 | 2339000 | -40565.21 | 2298434.79 | -1.734% | 2149223.01 | 0 | 2149223.01 | 93.51% | 1.4548 | 0% | 0 | Project is almost completed. | Substantial Completion
5166 | San Juan | Brisas de Cupey | José M. Paris | SP Management Corp. | CCC-JV | Fracinetti Arquitectos | Pitirre Copnstruction | 184 | 184 | 0 | 184 | 0 | 993 | 127 | 1120 | 12.79% | 1251 | 100% | 2010-02-26 | 2012-11-14 | 2013-03-21 | 2013-07-31 | 0 | 0 | ARRA/CFP | 0 | 15326960 | 1013140.06 | 16340100.06 | 6.61% | 16340100.06 | 0 | 16340100.06 | 100% | 6.7989 | 0% | 0 | The Program Manager is preparing the change order # 10, this CO has time extension by wheater condition and delay in the delivery of the building # 12 to the Contractor. The six building completed and we are waiting for legal RW documents, | Substantial Completion
3070 | Trujillo Alto | Pedro Regalado Díaz | José González | Inn Capital Housing Division Joint Venture | MD | Ray Engineers PSC | José L. Colón | 10 | 10 | 0 | 10 | 0 | 273 | 226 | 499 | 82.78% | 498 | 100% | 2008-04-14 | 2009-01-11 | 2009-08-25 | 2009-08-25 | 0 | 0 | CFP | 0 | 1991000 | 435116 | 2426116 | 21.85% | 2304810.1 | 0 | 2304810.1 | 95% | 49.8 | 0% | 0 | ♦ Repair of Units and Administration Building - The Management Agent has prepared a report about the scope of work and cost to repair units that will be delivered to the residents. Extraordinary Maintenance Office (PHAPR) is working with this item. ♦ Existing post removal - This work will be performed once the AEE connects the project and the Cable TV Company removes its wiring. ♦ Claim of the Contractor Jose Luis Colon - it was assigned to PGES to work with it. | Substantial Completion
3030 | Adjuntas | Villa Valle Verde | Pedro Vega | J.A. Machuca | URS | Jorge L. Roberts, PSC | Venegas Construction | 150 | 150 | 0 | 150 | 0 | 913 | 144 | 1057 | 15.77% | 1743 | 100% | 2001-01-15 | 2003-07-16 | 2003-12-07 | 2005-10-24 | 2007-02-06 | 0 | 0 | 0 | 11829000 | 337235 | 12166235 | 2.851% | 12103923 | 0 | 12103923 | 99.49% | 11.62 | 100% | 0 | These Close out is in process by PGES. | Final Acceptance
3034 | Aguada | Francisco Egipciaco | Noefebdo Ramírez | NFC | CMS | Arq. José Luzunaris | NLL Construction | 100 | 100 | 0 | 100 | 0 | 887 | 0 | 887 | 0% | 819 | 100% | 2000-03-23 | 2002-08-26 | 2002-08-26 | 2002-06-20 | 2002-10-04 | 0 | 0 | 0 | 8107810 | 207539 | 8315349 | 2.56% | 8315349 | 0 | 8315349 | 100% | 8.19 | 100% | 0 | Project Closed | Final Acceptance
5252 | Aguada | Los Robles | Noefebdo Ramírez | NFC | CMS | Joglar & Architects | 422 Corporation | 62 | 62 | 0 | 62 | 0 | 669 | 0 | 669 | 0% | 692 | 100% | 2001-01-18 | 2002-11-17 | 2002-11-17 | 2002-12-11 | 2003-10-02 | 0 | 0 | 0 | 2640000 | -11465 | 2628535 | -0.4343% | 2628535 | 0 | 2628535 | 100% | 11.1613 | 100% | 0 | Project Closed | Final Acceptance
5158 | Aguadilla | La Montaña | Frank Nieves | American Management | URS | Unipro | Caribe Tecno Habitat | 220 | 220 | 0 | 220 | 0 | 895 | 458 | 1353 | 51.17% | 1341 | 100% | 2003-07-28 | 2006-01-07 | 2007-04-10 | 2007-03-30 | 2007-03-30 | 0 | CFP | 0 | 16148000 | 1232941.34 | 17380941.34 | 7.635% | 16890921 | 0 | 16890921 | 97.18% | 6.0955 | 100% | 0 | Project Closed | Final Acceptance
3035 | Aguas Buenas | Vista Alegre | Rubén Cotto | MJ Consulting | URS Caribe | Carlos E. Betancourt | Constructores Gilmar | 74 | 74 | 0 | 74 | 0 | 912 | 752 | 1664 | 82.46% | 1645 | 100% | 2005-06-06 | 2007-12-04 | 2009-12-25 | 2009-12-07 | 2010-09-10 | 0 | Tax Credit 908-2008 | 0 | 6690000 | 2657915 | 9347915 | 39.73% | 8143277.42 | 0 | 8143277.42 | 87.11% | 22.2297 | 100% | 0 | Project Closed | Final Acceptance
3082 | Arecibo | Ramón Marín Solá (Fase II) | Arturo Acevedo | MAS Corporation | CMS | Andrés Hernández | Nogama Construction | 96 | 96 | 0 | 96 | 0 | 612 | 44 | 656 | 7.19% | 626 | 100% | 2000-05-15 | 2002-01-16 | 2002-03-01 | 2002-01-31 | 2002-03-15 | 0 | 0 | 0 | 7837000 | 0 | 7837000 | 0% | 7837000 | 0 | 7837000 | 100% | 6.5208 | 100% | 0 | Project Closed | Final Acceptance
3097 | Arecibo | Trina Padilla de Sanz | Frank Nieves | Cost Control Company, Inc. | ISS Corp | Ray Engineers PSC | Nogama Construction | 240 | 240 | 0 | 240 | 0 | 1278 | 97 | 1375 | 7.59% | 1464 | 100% | 2006-01-09 | 2009-07-09 | 2009-10-14 | 2010-01-12 | 2010-08-16 | 0 | Tax Credit | 0 | 23814529 | 1556413.89 | 25370942.89 | 6.536% | 25198434.68 | 0 | 25198434.68 | 99.32% | 6.1 | 100% | 0 | Project Closed | Final Acceptance
5127 | Arecibo | La Meseta | Pedro Vega | Cost Control Company, Inc. | URS Caribe | Enrique Ruiz & Asoc. | Venegas Construction | 300 | 300 | 0 | 300 | 0 | 1098 | 871 | 1969 | 79.33% | 1947 | 100% | 2005-05-31 | 2008-06-01 | 2010-10-20 | 2010-09-29 | 2011-01-24 | 0 | Tax Credit | 0 | 24161000 | 1903823.57 | 26064823.57 | 7.88% | 26064823.57 | 0 | 26064823.57 | 100% | 6.49 | 100% | 0 | Project Closed. | Final Acceptance
3099 | Arecibo | Antonio Márquez Arbona | Frank Nieves | American Management | Klassik Builders | Enrique Ruiz & Asoc. | Karimar Construction, Inc. | 104 | 104 | 0 | 104 | 0 | 730 | 183 | 913 | 25.07% | 912 | 100% | 2010-03-25 | 2012-03-23 | 2012-09-22 | 2012-09-22 | 2013-04-01 | 0 | ARRA/CFP | 0 | 9085636 | 263361.39 | 9348997.39 | 2.899% | 9223663.18 | 0 | 9223663.18 | 98.66% | 8.7692 | 100% | 0 | In Closing Process. | Final Acceptance
3021 | Arroyo | Isidro Cora | Rubén Cotto | MJ Consulting | MD | GMG Eng. Consultants | Venegas Construction | 150 | 150 | 0 | 150 | 0 | 1095 | 302 | 1397 | 27.58% | 1396 | 100% | 1999-09-27 | 2002-09-25 | 2003-07-24 | 2003-07-24 | 2004-09-30 | 0 | 0 | 0 | 10247000 | 437000 | 10684000 | 4.265% | 10654500 | 0 | 10654500 | 99.72% | 9.3067 | 100% | 0 | The close out documents are under correction process by the Program Manager and General Contractor. | Final Acceptance
3036 | Barceloneta | Antonio Dávila Freytes | José Negrón | MAS Corporation | LMC | Andrés Hernández & Asoc. | Caribe Tecno | 100 | 100 | 0 | 100 | 0 | 904 | 413 | 1317 | 45.69% | 1316 | 100% | 1999-10-15 | 2002-04-05 | 2003-05-23 | 2003-05-23 | 2003-06-30 | 0 | 0 | 0 | 6970000 | 1305876.67 | 8275876.67 | 18.74% | 8275877 | 0 | 8275877 | 100% | 13.16 | 100% | 0 | Project Closed | Final Acceptance
3037 | Barranquitas | Villa Universitaria | Jorge Mercado | MJ Consulting | AVP | GMG Eng. Consultants | Royal & Sun Alliance | 100 | 100 | 0 | 100 | 0 | 540 | 913 | 1453 | 169.1% | 1678 | 100% | 1997-11-25 | 1999-05-18 | 2001-11-16 | 2002-06-30 | 2002-11-12 | 0 | 0 | 0 | 5299000 | 804839 | 6103839 | 15.19% | 6103839 | 0 | 6103839 | 100% | 16.78 | 100% | 0 | Project Closed | Final Acceptance
5093 | Bayamón | Brisas de Bayamón | Arturo Acevedo | Cost Control Company, Inc. | URS Caribe | Edison Avilés Deliz | Omega Engineering | 300 | 300 | 0 | 300 | 0 | 1400 | 1372 | 2772 | 98% | 2518 | 100% | 2002-01-09 | 2005-11-08 | 2009-08-11 | 2008-12-01 | 2010-03-22 | 0 | Tax Credit | 0 | 23965851 | 5030471 | 28996322 | 20.99% | 27007484 | 0 | 27007484 | 93.14% | 8.3933 | 100% | 0 | Project Closed | Final Acceptance
5151 | Bayamón | Sierra Linda | Arturo Acevedo | Martinal Property | URS | Gautier & De Torres | JR Builders | 200 | 200 | 0 | 200 | 0 | 1015 | 1071 | 2086 | 105.5% | 2136 | 100% | 2002-04-15 | 2005-01-23 | 2007-12-30 | 2008-02-19 | 2008-08-08 | 0 | CFP-02 | 0 | 13395440 | 1036113 | 14431553 | 7.735% | 14344606 | 0 | 14344606 | 99.4% | 10.68 | 100% | 0 | Project Closed | Final Acceptance
5096 | Bayamón | La Alhambra | Luis Rodríguez | Cost Control Company, Inc. | LMC | Jorge del Río Arquitectos | Del Valle Group | 96 | 96 | 0 | 96 | 0 | 730 | 236 | 966 | 32.33% | 793 | 100% | 2009-07-28 | 2011-07-27 | 2012-03-19 | 2011-09-29 | 2012-05-17 | 0 | ARRA-CFP | 0 | 9555000 | 752914.59 | 10307914.59 | 7.88% | 10307914.59 | 0 | 10307914.59 | 100% | 8.2604 | 100% | 0 | Project Closed | Final Acceptance
5094 | Bayamón | Las Gardenias | Jorge Mercado | Housing Promoters | AVP/Prann | Gautier & Benítez | Del Valle Group | 164 | 164 | 0 | 164 | 0 | 671 | 302 | 973 | 45.01% | 1033 | 100% | 1997-05-29 | 1999-03-30 | 2000-01-26 | 2000-03-27 | 2000-06-08 | 0 | 0 | 0 | 7117000 | 152286.5 | 7269286.5 | 2.14% | 7234564.4 | 0 | 7234564.4 | 99.52% | 6.2988 | 100% | 0 | Project Closed | Final Acceptance
5138 | Caguas | Villa del Rey (With Take Over Agreement) | Fco. Palacios | MJ Consulting | AVP / Vivonis & Villegas | Guillermety, Ortiz & Asoc. | American Intl. | 100 | 100 | 0 | 100 | 0 | 620 | 165 | 785 | 26.61% | 903 | 100% | 2000-08-04 | 2002-04-15 | 2002-09-27 | 2003-01-24 | 2003-01-24 | 0 | 0 | 0 | 2110081 | 192030 | 2302111 | 9.101% | 2302111 | 0 | 2302111 | 100% | 9.03 | 100% | 0 | Project Closed | Final Acceptance
5066 | Caguas | Turabo Heights | Luis Rodríguez | MJ Consulting | LMC | Andrés Hernández & Asoc. | Del Valle Group | 254 | 254 | 0 | 254 | 0 | 1300 | 471 | 1771 | 36.23% | 1641 | 100% | 2006-01-16 | 2009-08-07 | 2010-11-21 | 2010-07-15 | 2010-09-30 | 0 | Tax Credit | 0 | 25534940 | 2776195 | 28311135 | 10.87% | 28311135.04 | 0 | 28311135.04 | 100% | 6.4606 | 100% | 0 | Project Closed | Final Acceptance
3038 | Camuy | M. Román Adames | Arturo Acevedo | NFC | CMS | Gutierez & Gutierrez | Pintores Metropolitanos | 64 | 64 | 0 | 64 | 0 | 396 | 491 | 887 | 124% | 1101 | 100% | 1997-05-19 | 1998-06-18 | 1999-10-22 | 2000-05-24 | 2001-03-19 | 0 | 0 | 0 | 3600000 | 403566 | 4003566 | 11.21% | 4003566 | 0 | 4003566 | 100% | 17.2031 | 100% | 0 | Project Closed | Final Acceptance
3053 | Canóvanas | Jesús T. Piñero | Katherine Vázquez | Peregrine Group Inc. | Klassik Builders | Ray Engineers, PSC | LPC&D | 124 | 124 | 0 | 124 | 0 | 913 | 237 | 1150 | 25.96% | 1149 | 100% | 2009-07-15 | 2012-01-13 | 2012-09-06 | 2012-09-06 | 2013-06-30 | 0 | ARRA/CFP | 0 | 16575250 | 2355453 | 18930703 | 14.21% | 18827830.65 | 0 | 18827830.65 | 99.46% | 9.2661 | 100% | 0 | The following items are pending: comments from payroll non-compliance issues, to submit certification # 38. | Final Acceptance
5082 | Carolina | Alturas de Country Club | José González | PROMMA | URS | Jorge del Rio | North Construction | 72 | 72 | 0 | 72 | 0 | 548 | 373 | 921 | 68.07% | 893 | 100% | 2004-09-27 | 2006-03-28 | 2007-04-05 | 2007-03-09 | 2009-04-24 | 0 | CFP | 0 | 5977756.15 | 1066756.51 | 7044512.66 | 17.85% | 7044512.67 | 0 | 7044512.67 | 100% | 12.4028 | 100% | 0 | Project Closed | Final Acceptance
5057 | Carolina | Los Mirtos | José González | Cost Control | CCC-JV | Hernández - Bauzá | Del Valle group | 144 | 144 | 0 | 144 | 0 | 545 | 121 | 666 | 22.2% | 690 | 100% | 2010-11-08 | 2012-05-05 | 2012-09-03 | 2012-09-28 | 2013-07-17 | 0 | Tax Credit | 0 | 14841000 | 272983 | 15113983 | 1.839% | 14923649 | 0 | 14923649 | 98.74% | 4.7917 | 100% | 0 | Project Closed | Final Acceptance
5076 | Carolina | Catañito Gardens | Luis Rodríguez | Inn Capital Housing Division Joint Venture | MD | URS Caribe | RBC Construction | 124 | 124 | 0 | 124 | 0 | 730 | 937 | 1667 | 128.4% | 0 | 100% | 2006-02-08 | 2008-02-07 | 2010-09-01 | 2006-02-08 | 2011-03-28 | 0 | Tax Credit 908-2008 | 0 | 13938100 | 819027.62 | 14757127.62 | 5.876% | 14757127.62 | 0 | 14757127.62 | 100% | 0 | 100% | 0 | Project Closed | Final Acceptance
5102 | Carolina | El Coral | José A. González | Cost Control Company, Inc. | URS Caribe | Francinetti Arquitectos | Orion Contractors | 100 | 100 | 0 | 100 | 0 | 913 | 1268 | 2181 | 138.9% | 2180 | 100% | 2006-01-09 | 2008-07-09 | 2011-12-29 | 2011-12-29 | 2012-06-29 | 0 | Tax Credit | 0 | 9718830 | 1196730.19 | 10915560.19 | 12.31% | 10915560.19 | 0 | 10915560.19 | 100% | 21.8 | 100% | 0 | Project Closed | Final Acceptance
5101 | Carolina | La Esmeralda | Luis Rodríguez | Inn Capital Housing Division Joint Venture | BMA | Carlos E. Betancourt | Construction Zone Corp. | 84 | 84 | 0 | 84 | 0 | 549 | 65 | 614 | 11.84% | 612 | 100% | 2008-12-22 | 2010-06-23 | 2010-08-27 | 2010-08-26 | 2010-12-10 | 0 | Tax Credit | 0 | 4462898 | 32305.97 | 4495203.97 | 0.7239% | 4495203.77 | 0 | 4495203.77 | 100% | 7.2857 | 100% | 0 | Project Closed | Final Acceptance
5075 | Carolina | Lagos de Blasina | José A. González | Cost Control Company, Inc. | CMS | Guillermety, Ortiz & Asoc. (DG3A Design Group, PSC is actually supervising the works) | Mejia Construction | 240 | 240 | 0 | 240 | 0 | 800 | 289 | 1089 | 36.12% | 1077 | 100% | 2009-06-08 | 2011-08-16 | 2012-05-31 | 2012-05-20 | 2012-09-20 | 0 | Tax Credit | 0 | 15411000 | 809595.16 | 16220595.16 | 5.253% | 16220595.16 | 0 | 16220595.16 | 100% | 4.4875 | 100% | 0 | Project Closed | Final Acceptance
5212 | Carolina | Roberto Clemente | Luz Acevedo | SEG | CMS | Jorge del Río | North Connstruction | 126 | 126 | 0 | 126 | 0 | 730 | 242 | 972 | 33.15% | 1038 | 100% | 2004-08-09 | 2006-08-08 | 2007-04-07 | 2007-06-13 | 2008-02-22 | 0 | 0 | 0 | 11135000 | 586931 | 11721931 | 5.271% | 11610417 | 0 | 11610417 | 99.05% | 8.2381 | 100% | 0 | Project Closed | Final Acceptance
3102 | Cataño | Juana Matos I (Fase I) | Luz Acevedo | A & M | AVP / Erwin Rodriguez | Roca & Associates | Quintero Const. | 212 | 212 | 0 | 212 | 0 | 892 | 744 | 1636 | 83.41% | 1628 | 100% | 1997-05-29 | 1999-11-06 | 2001-11-19 | 2001-11-12 | 2002-07-22 | 0 | 0 | 0 | 11640000 | 424857 | 12064857 | 3.65% | 11679790.2 | 0 | 11679790.2 | 96.81% | 7.6792 | 100% | 0 | Project Closed | Final Acceptance
3102 | Cataño | Juana Matos I (Fase II) | Pedro Vega | A & M | BMA | Roca & Associates | Rodríguez & del Valle | 188 | 188 | 0 | 188 | 0 | 1150 | 141 | 1291 | 12.26% | 1179 | 100% | 2002-09-30 | 2005-11-22 | 2006-04-12 | 2005-12-22 | 2006-01-12 | 0 | 0 | 0 | 14243000 | 831198 | 15074198 | 5.836% | 15074198 | 0 | 15074198 | 100% | 6.2713 | 100% | 0 | Project Closed | Final Acceptance
5037 | Cataño | Jardines de Cataño | Pedro Vega | Martinal Property | CMS | Interplan | Francisco Levy Hijo Inc. | 180 | 180 | 0 | 180 | 0 | 810 | 369 | 1179 | 45.56% | 1175 | 100% | 2004-03-22 | 2006-06-09 | 2007-06-13 | 2007-06-10 | 2007-06-14 | 0 | CFP | 0 | 14181600 | 1145235.46 | 15326835.46 | 8.076% | 15326835.44 | 0 | 15326835.44 | 100% | 6.5278 | 100% | 0 | Project Closed | Final Acceptance
3083 | Cayey | Luis Muñoz Morales | Luz Acevedo | MJ Consulting | AVP | Istra Hernández | I Melendez | 280 | 280 | 0 | 280 | 0 | 913 | 416 | 1329 | 45.56% | 1342 | 100% | 1997-08-01 | 2000-01-30 | 2001-03-21 | 2001-04-04 | 2001-09-19 | 0 | 0 | 0 | 12895800 | 452279 | 13348079 | 3.507% | 13348079 | 0 | 13348079 | 100% | 4.7929 | 100% | 0 | Project Close | Final Acceptance
5127 | Cayey | Jardines de Montellanos | Rubén Cotto | Cost Control | CCC-JV | Hernández - Bauzá | Constructora I. Meléndez | 130 | 130 | 0 | 130 | 0 | 836 | 307 | 1143 | 36.72% | 1142 | 100% | 2009-09-30 | 2012-01-13 | 2012-11-15 | 2012-11-15 | 0 | 0 | Tax Credit | 0 | 17226575.94 | 2771225.7 | 19997801.64 | 16.09% | 19987858.29 | 0 | 19987858.29 | 99.95% | 8.7846 | 100% | 0 | Project Closed | Final Acceptance
5157 | Cayey | Brisas de Cayey | Rubén Cotto | MJ Consulting | MD | Ray Engineers PSC | Three O. Construction | 210 | 210 | 0 | 210 | 0 | 1491 | 1200 | 2691 | 80.48% | 1887 | 100% | 2005-01-12 | 2009-02-10 | 2012-05-25 | 2010-03-14 | 2010-04-06 | 0 | Tax Credit | 0 | 24696653 | 5611698 | 30308351 | 22.72% | 30308351 | 0 | 30308351 | 100% | 8.9857 | 100% | 0 | Project Closed | Final Acceptance
3040 | Ciales | Fernando Sierra Berdecía | José Negrón | MAS Corporation | LMC | Luis Flores & Asociados | Constructores Gilmar | 100 | 100 | 0 | 100 | 0 | 780 | 165 | 945 | 21.15% | 983 | 100% | 2001-08-21 | 2003-10-09 | 2004-03-22 | 2004-04-30 | 2006-05-16 | 0 | 0 | 0 | 9285527 | 414901 | 9700428 | 4.468% | 9700428 | 0 | 9700428 | 100% | 9.83 | 100% | 0 | Project Closed | Final Acceptance
3041 | Cidra | Práxedes Santiago | Rubén Cotto | MJ Consulting | URS | Carlos E. Betancourt | DGM Engineering | 124 | 124 | 0 | 124 | 0 | 912 | 901 | 1813 | 98.79% | 2235 | 100% | 2005-04-28 | 2007-10-26 | 2010-04-14 | 2011-06-11 | 2012-03-09 | 0 | Tax Credit | 0 | 11616773 | 3604885 | 15221658 | 31.03% | 14100168 | 0 | 14100168 | 92.63% | 18.0242 | 100% | 0 | Project Closed | Final Acceptance
3043 | Dorado | El Dorado | Frank Nieves | Cost Control Company, Inc. | BMA | Guillermety, Ortiz & Asoc. | Torres & Colón, Inc | 37 | 37 | 0 | 37 | 0 | 430 | 180 | 610 | 41.86% | 666 | 100% | 2007-06-04 | 2008-08-06 | 2009-02-02 | 2009-03-31 | 2009-04-14 | 0 | Tax Credit | 0 | 3991977 | 753900 | 4745877 | 18.89% | 4745877 | 0 | 4745877 | 100% | 18 | 100% | 0 | Project Closed | Final Acceptance
3095 | Fajardo | Pedro Rosario Nieves | José M. Paris Escalera | Inn Capital Housing Division Joint Venture | CMS | Carlos E. Betancourt | Nogama Construction | 168 | 168 | 0 | 168 | 0 | 915 | 27.5 | 942.5 | 3.005% | 904 | 100% | 2008-12-22 | 2011-06-24 | 2011-07-21 12:00 | 2011-06-14 | 2011-09-06 | 0 | Tax Credit | 0 | 16474000 | -148386.07 | 16325613.93 | -0.9007% | 16325613.93 | 0 | 16325613.93 | 100% | 5.381 | 100% | 0 | Project Closed | Final Acceptance
5021 | Fajardo | Puerto Real | Germán Acevedo | A & M | URS | René Vélez Marichal | Quality Const. | 100 | 100 | 0 | 100 | 0 | 945 | 282 | 1227 | 29.84% | 1124 | 100% | 2001-01-22 | 2003-08-24 | 2004-06-01 | 2004-02-20 | 2004-04-20 | 0 | 0 | 0 | 8220000 | 910990 | 9130990 | 11.08% | 9130990 | 0 | 9130990 | 100% | 11.24 | 100% | 0 | Project Closed | Final Acceptance
5204 | Fajardo | Valle Puerto Real | Germán Acevedo | A & M | URS | Enrique Ruiz & Assoc. | Quality Const. | 75 | 75 | 0 | 75 | 0 | 945 | 181 | 1126 | 19.15% | 1129 | 100% | 2001-01-02 | 2003-08-04 | 2004-02-01 | 2004-02-05 | 2004-05-14 | 0 | 0 | 0 | 6316000 | 725553 | 7041553 | 11.49% | 7041553 | 0 | 7041553 | 100% | 15.0533 | 100% | 0 | Project Closed | Final Acceptance
5176 | Fajardo | Santiago Veve Calzada | Robert H. Cole | A & M | BMA | Ramón W. Costacamps | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 730 | 214 | 944 | 29.32% | 906 | 100% | 2004-06-21 | 2006-06-20 | 2007-01-20 | 2006-12-14 | 2007-01-18 | 0 | 0 | 0 | 8559000 | 558385.32 | 9117385.32 | 6.524% | 9117385.32 | 0 | 9117385.32 | 100% | 9.06 | 100% | 0 | Project Closed | Final Acceptance
5183 | Guánica | Jardines de Guánica | Noefebdo Ramírez | JA Machuca | CCC-JV | Donato Design Development | RAMA Construction | 70 | 70 | 0 | 70 | 0 | 732 | 89 | 821 | 12.16% | 794 | 100% | 2009-11-23 | 2011-11-24 | 2012-02-21 | 2012-01-26 | 2012-01-31 | 0 | ARRA/CFP | 0 | 5499000 | 487497.62 | 5986497.62 | 8.865% | 5986498 | 0 | 5986498 | 100% | 11.3429 | 100% | 0 | Project Closed | Final Acceptance
3084 | Guánica | Luis Muñoz Rivera | Noefebdo Ramírez | Cost Control Company, Inc. | CCC-JV | Behar & Ybarra Associates, PSC | F & R Construction Group, Inc. | 124 | 124 | 0 | 124 | 0 | 485 | 423 | 908 | 87.22% | 970 | 100% | 2009-12-14 | 2011-04-12 | 2012-06-08 | 2012-08-10 | 2013-04-18 | 0 | Tax Credit | 0 | 9009000 | 589263.71 | 9598263.71 | 6.541% | 9590758.22 | 0 | 9590758.22 | 99.92% | 7.8226 | 100% | 0 | Project Closed | Final Acceptance
3085 | Guayama | Luis Palés Matos | Rubén Cotto | MJ Consulting | MD (Grupo C) | Guillermety, Ortiz & Asoc. | Héctor M. Valera Inc. | 298 | 298 | 0 | 298 | 0 | 1130 | 0 | 1130 | 0% | 1375 | 100% | 2002-03-25 | 2005-04-27 | 2005-04-27 | 2005-12-29 | 2006-01-03 | 0 | 0 | 0 | 22466000 | 0 | 22466000 | 0% | 22466000 | 0 | 22466000 | 100% | 4.6141 | 100% | 0 | Project Closed | Final Acceptance
5048 | Guayama | San Antonio Carioca | Jorge Mercado | MJ Consulting | MD (Grupo C) | DDHK | Constructora I. Melendez | 200 | 200 | 0 | 200 | 0 | 900 | 568 | 1468 | 63.11% | 1537 | 100% | 2004-03-15 | 2006-08-31 | 2008-03-21 | 2008-05-30 | 2008-07-30 | 0 | Tax Credit | 0 | 18456662 | 1765148 | 20221810 | 9.564% | 20221810 | 0 | 20221810 | 100% | 7.685 | 100% | 0 | Project Closed | Final Acceptance
5131 | Humacao | Jardines de Oriente | José A. González | Cost Control | CCC-JV | GMG Engineering Conslutants PSC | Ossam Construction | 88 | 88 | 0 | 88 | 0 | 365 | 242 | 607 | 66.3% | 937 | 100% | 2010-05-31 | 2011-05-30 | 2012-01-27 | 2012-12-23 | 2012-07-20 | 0 | Tax Credit | 0 | 5939925 | 394882.55 | 6334807.55 | 6.648% | 6334807.55 | 0 | 6334807.55 | 100% | 10.6477 | 100% | 0 | Project Closed | Final Acceptance
5020 | Humacao | Pedro J. Palou | Fco. Palacios | MJ Consulting | URS | R & del Valle | R & del Valle | 150 | 150 | 0 | 150 | 0 | 1095 | 180 | 1275 | 16.44% | 1145 | 100% | 1999-09-27 | 2002-09-25 | 2003-03-24 | 2002-11-15 | 2002-12-20 | 0 | 0 | 0 | 10968000 | 86049 | 11054049 | 0.7845% | 11054049 | 0 | 11054049 | 100% | 7.6333 | 100% | 0 | Project closed. | Final Acceptance
3094 | Humacao | Padre Rivera (Fase I) | Germán Acevedo | MJ Consulting | BMA | Yañez, Mayol & Asoc. | J R Builders | 128 | 128 | 0 | 128 | 0 | 840 | 731 | 1571 | 87.02% | 1548 | 100% | 1997-10-20 | 2000-02-06 | 2002-02-06 | 2002-01-15 | 2002-02-01 | 0 | 0 | 0 | 6625000 | 386337.2 | 7011337.2 | 5.832% | 7011337 | 0 | 7011337 | 100% | 12.0938 | 100% | 0 | Project Closed | Final Acceptance
3094 | Humacao | Padre Rivera (Fase II) | Jorge Mercado | MJ Consulting | BMA | Yañez & Mayol | Jafer Construction | 132 | 132 | 0 | 132 | 0 | 790 | 299 | 1089 | 37.85% | 861 | 100% | 2004-11-10 | 2007-01-08 | 2007-11-03 | 2007-03-21 | 2008-03-12 | 0 | 0 | 0 | 10199820 | 1471265 | 11671085 | 14.42% | 11237717 | 0 | 11237717 | 96.29% | 6.5227 | 100% | 0 | Project Closed | Final Acceptance
3048 | Jayuya | La Montaña | Pedro Vega | MAS Corporation | URS | OPQ-Pablo Quiñonez | Orama Const. | 100 | 100 | 0 | 100 | 0 | 780 | 128 | 908 | 16.41% | 1026 | 100% | 2000-10-23 | 2002-12-11 | 2003-04-18 | 2003-08-15 | 2004-04-26 | 0 | 0 | 0 | 8790000 | 208826 | 8998826 | 2.376% | 8998826 | 0 | 8998826 | 100% | 10.26 | 100% | 0 | Project Closed | Final Acceptance
5064 | Juncos | Colinas de Magnolia | Iván Blanco | MJ Consulting | BMA | Edison Avilés Deliz | Quality Construction | 148 | 148 | 0 | 148 | 0 | 840 | 614 | 1454 | 73.1% | 1201 | 100% | 2004-11-08 | 2007-02-25 | 2008-10-31 | 2008-02-22 | 2008-04-04 | 0 | CFP | 0 | 13860000 | 854562 | 14714562 | 6.166% | 14438155 | 0 | 14438155 | 98.12% | 8.1149 | 100% | 0 | Project Closed | Final Acceptance
3093 | Juncos | Narciso Varona I | Rubén Cotto | MJ Consulting | ISS | DG3A | Torres & Colón, Inc | 88 | 88 | 0 | 88 | 0 | 600 | 199 | 799 | 33.17% | 798 | 100% | 2009-05-29 | 2011-01-18 | 2011-08-05 | 2011-08-05 | 0 | 0 | ARRA/CFP | 0 | 9879114 | 196304 | 10075418 | 1.987% | 10058405.83 | 0 | 10058405.83 | 99.83% | 9.0682 | 100% | 0 | Project Closed | Final Acceptance
5226 | Las Marías | Jardines de las Marías | Arturo Acevedo | NFC | CMS | José L. Irizarry & Assoc. | Lebrón & Assoc. | 55 | 55 | 0 | 55 | 0 | 730 | 32 | 762 | 4.384% | 766 | 100% | 2001-02-27 | 2003-02-26 | 2003-03-30 | 2003-04-04 | 2003-10-03 | 0 | 0 | 0 | 4156000 | 71269 | 4227269 | 1.715% | 4227269 | 0 | 4227269 | 100% | 13.9273 | 100% | 0 | Project Closed | Final Acceptance
5090 | Las Piedras | Jardines de Judely | Iván Blanco | MJ Consulting | URS | René Acosta Ingenieros | Gilmar Roofing & Painting | 32 | 32 | 0 | 32 | 0 | 365 | 118 | 483 | 32.33% | 555 | 100% | 2005-04-04 | 2006-04-03 | 2006-07-30 | 2006-10-11 | 2006-11-02 | 0 | Tax Credit | 0 | 3481720 | 109596.22 | 3591316.22 | 3.148% | 3573356 | 0 | 3573356 | 99.5% | 17.3438 | 100% | 0 | Project Closed | Final Acceptance
5132 | Loíza | Yuquiyú | Luz Acevedo | A & M | BMA | Roca, González Villamil | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 945 | 60 | 1005 | 6.349% | 754 | 100% | 2001-01-22 | 2003-08-24 | 2003-10-23 | 2003-02-15 | 2003-03-21 | 0 | 0 | 0 | 8644000 | 611853 | 9255853 | 7.078% | 9255853.0708 | 0 | 9255853.0708 | 100% | 7.54 | 100% | 0 | Project Closed | Final Acceptance
5186 | Luquillo | Yuquiyú II | Luz Acevedo | Inn Capital Housing Division Joint Venture | BMA | Enrique Ruiz & Asoc. | Unique Builders | 70 | 70 | 0 | 70 | 0 | 730 | 299 | 1029 | 40.96% | 1092 | 100% | 2006-02-15 | 2008-02-14 | 2008-12-09 | 2009-02-11 | 2009-06-09 | 0 | Tax Credit | 0 | 6964727 | 157419 | 7122146 | 2.26% | 6424134.91 | 0 | 6424134.91 | 90.2% | 15.6 | 100% | 0 | Project Closed | Final Acceptance
3056 | Maricao | Juan Ferrer | Noefebdo Ramírez | J. A. Machuca | NFC | René Batista & Assoc. | Comas & Comas | 30 | 30 | 0 | 30 | 0 | 420 | 251 | 671 | 59.76% | 610 | 100% | 2000-08-02 | 2001-09-25 | 2002-06-03 | 2002-04-04 | 2002-04-30 | 0 | 0 | 0 | 2210000 | 178940 | 2388940 | 8.097% | 2388940 | 0 | 2388940 | 100% | 20.3333 | 100% | 0 | Project Closed | Final Acceptance
3057 | Maunabo | Carmen Vda. Martorell (take over agreement) | Rubén Cotto | AVP | AVP | Rene Batista | American Intl. | 50 | 50 | 0 | 50 | 0 | 375 | 327 | 702 | 87.2% | 703 | 100% | 2000-08-18 | 2001-08-27 | 2002-07-20 | 2002-07-22 | 2005-06-02 | 0 | 0 | 0 | 1308221 | 116706 | 1424927 | 8.921% | 1424927 | 0 | 1424927 | 100% | 14.06 | 100% | 0 | Project Closed | Final Acceptance
5126 | Maunabo | Villa Navarro | Rubén Cotto | MJ Consulting | MD | José L. Irizarry & Assoc. | Inversiones OLPERI | 101 | 101 | 0 | 101 | 0 | 907 | 335 | 1242 | 36.93% | 1241 | 100% | 2000-01-24 | 2002-07-18 | 2003-06-18 | 2003-06-18 | 2003-06-18 | 0 | 0 | 0 | 6745000 | 238239 | 6983239 | 3.532% | 6983239 | 0 | 6983239 | 100% | 12.2871 | 100% | 0 | Project Closed | Final Acceptance
5012 | Mayagüez | Ext. Sábalos Gardens | Noefebdo Ramírez | Inn Capital Housing Division Joint Venture | URS Caribe / AVP | Joint Venture | Venegas Construction | 300 | 300 | 0 | 300 | 0 | 1281 | 690 | 1971 | 53.86% | 1963 | 100% | 2005-05-16 | 2008-11-16 | 2010-10-07 | 2010-09-30 | 2011-04-29 | 0 | Tax Credit 908-2008 | 0 | 28259000 | 14189.7 | 28273189.7 | 0.05021% | 29677970 | 0 | 29677970 | 105% | 6.5433 | 100% | 0 | Project Closed | Final Acceptance
4004 | Mayagüez | Sábalos Gdns. | Arturo Acevedo | Zeta | CMS | Héctor Rodríguez Amezquita | Caribe Tecno | 140 | 140 | 0 | 140 | 0 | 881 | 24 | 905 | 2.724% | 900 | 100% | 1999-11-15 | 2002-04-13 | 2002-05-07 | 2002-05-03 | 2002-11-06 | 0 | 0 | 0 | 11790000 | -294361.74 | 11495638.26 | -2.497% | 11495638 | 0 | 11495638 | 100% | 6.4286 | 100% | 0 | Project Closed | Final Acceptance
4006 | Mayagüez | Cuesta las Piedras | Arturo Acevedo | Zeta | CMS | García Cabot | RC Enginering | 142 | 142 | 0 | 142 | 0 | 1093 | 0 | 1093 | 0% | 907 | 100% | 2000-02-10 | 2003-02-06 | 2003-02-06 | 2002-08-05 | 2002-11-21 | 0 | 0 | 0 | 10673000 | 158657 | 10831657 | 1.487% | 10831657 | 0 | 10831657 | 100% | 6.3873 | 100% | 0 | Se aprobó el "close out". Contratista no cobró el total del contrato debido a ajustes deductivos recomendados por el "Program Manager"C.M. Services. | Final Acceptance
4008 | Mayagüez | Yagüez | Arturo Acevedo | ZETA | CMS | GDA Ing. Consultores | NLL Construction | 200 | 200 | 0 | 200 | 0 | 1399 | 0 | 1399 | 0% | 1177 | 100% | 2000-05-22 | 2004-03-20 | 2004-03-20 | 2003-08-12 | 2003-10-06 | 0 | 0 | 0 | 16799671 | -872594 | 15927077 | -5.194% | 15927077 | 0 | 15927077 | 100% | 5.885 | 100% | 0 | Project Closed | Final Acceptance
4005 | Mayagüez | Marini Farm | Frank Nieves | Zeta | BMA | CSA Architects | Empresas Toledo | 100 | 100 | 0 | 100 | 0 | 218 | 50 | 268 | 22.94% | 247 | 100% | 2004-05-12 | 2004-12-15 | 2005-02-03 | 2005-01-14 | 2005-09-07 | 0 | 0 | 0 | 845900 | 30508 | 876408 | 3.607% | 876408 | 0 | 876408 | 100% | 2.47 | 100% | 0 | Project Closed | Final Acceptance
5005 | Mayagüez | Mar y Sol | Noefebdo Ramírez | Zeta | CMS | Arq. Amadeo Pino | RC Enginering | 124 | 124 | 0 | 124 | 0 | 1055 | 14 | 1069 | 1.327% | 1068 | 100% | 2001-01-22 | 2003-12-12 | 2003-12-26 | 2003-12-26 | 2004-05-26 | 0 | 0 | 0 | 10513000 | 269417 | 10782417 | 2.563% | 10782417 | 0 | 10782417 | 100% | 8.6129 | 100% | 0 | Project Closed | Final Acceptance
5133 | Naguabo | Villas del Río | Félix Ortiz | MJ Consulting | MD | N/A | DGM Engineering | 100 | 100 | 0 | 100 | 0 | 730 | 906 | 1636 | 124.1% | 1640 | 100% | 2006-02-15 | 2008-02-14 | 2010-08-08 | 2010-08-13 | 2011-06-27 | 0 | Tax Credit | 0 | 11008930 | 1560851 | 12569781 | 14.18% | 12120952 | 0 | 12120952 | 96.43% | 16.4 | 100% | 0 | Project Closed | Final Acceptance
3063 | Peñuela | Los Flamboyanes | Noefebdo Ramírez | J.A. Machuca | MD | Fuertes, La Font & Asoc. | St. Paul Surety | 24 | 24 | 0 | 24 | 0 | 345 | 502 | 847 | 145.5% | 845 | 100% | 2003-04-15 | 2004-03-24 | 2005-08-08 | 2005-08-07 | 2005-09-26 | 0 | 0 | 0 | 1235996 | 568973 | 1804969 | 46.03% | 1804969 | 0 | 1804969 | 100% | 35.2083 | 100% | 0 | Project Closed | Final Acceptance
1014 | Ponce | Aristides Chavier | Noefebdo Ramírez | MJ Consulting | CCC Joint Venture | Unipro | Del Valle Group | 480 | 480 | 0 | 480 | 0 | 1464 | 552 | 2016 | 37.7% | 2003 | 100% | 2005-08-01 | 2009-08-03 | 2011-02-06 | 2011-01-25 | 2011-08-16 | 0 | Tax Credit 908-2008 | 0 | 43792000 | 2045988.7 | 45837988.7 | 4.672% | 45837989 | 0 | 45837989 | 100% | 4.1729 | 100% | 0 | Project Closed | Final Acceptance
5088 | Ponce | Lirios del Sur | Arturo Acevedo | J.A. Machuca | CMS | CSA Architects | Omega Engineering | 238 | 238 | 0 | 238 | 0 | 730 | 340 | 1070 | 46.58% | 1083 | 100% | 2003-02-12 | 2005-02-10 | 2006-01-16 | 2006-01-30 | 2006-04-12 | 0 | 0 | 0 | 18140000 | 570661 | 18710661 | 3.146% | 18710661 | 0 | 18710661 | 100% | 4.5504 | 100% | 0 | Project Closed | Final Acceptance
1001 | Ponce | Ponce de León ( Take Over Agreement) Fase I | José González | J. A. Machuca | MD | Interplan | American Intl. | 168 | 168 | 0 | 168 | 0 | 732 | 171 | 903 | 23.36% | 862 | 100% | 2000-08-28 | 2002-08-29 | 2003-02-16 | 2003-01-07 | 2003-01-30 | 0 | 0 | 0 | 10990000 | 512271 | 11502271 | 4.661% | 11447321.14 | 0 | 11447321.14 | 99.52% | 5.131 | 100% | 0 | Project Closed | Final Acceptance
1001 | Ponce | Ponce de León (Fase II) | Noefebdo Ramírez | MJ Consulting | BMA | Interplan | Constructora I. Meléndez | 132 | 132 | 0 | 132 | 0 | 730 | 748 | 1478 | 102.5% | 1442 | 100% | 2005-01-10 | 2007-01-09 | 2009-01-26 | 2008-12-22 | 2009-03-31 | 0 | Tax Credit 908-2008 | 0 | 13680284 | 787807 | 14468091 | 5.759% | 14448030 | 0 | 14448030 | 99.86% | 10.9242 | 100% | 0 | Project Closed | Final Acceptance
1002 | Ponce | Santiago Iglesias (Fase I) | Noefebdo Ramírez | Zeta | CMS | CSA | Ferrovial & Agroman | 160 | 160 | 0 | 160 | 0 | 487 | 505 | 992 | 103.7% | 1791 | 100% | 1997-10-28 | 1999-02-26 | 2000-07-15 | 2002-09-23 | 2002-11-02 | 0 | 0 | 0 | 9445984 | 580020 | 10026004 | 6.14% | 9993950 | 0 | 9993950 | 99.68% | 11.1937 | 100% | 0 | Project Closed | Final Acceptance
1016 | Ponce | Rafael López Nussa | Noefebdo Ramírez | MJ Consulting | BMA | URS Caribe | Del Valle Group | 404 | 404 | 0 | 404 | 0 | 1464 | 369 | 1833 | 25.2% | 1832 | 100% | 2004-10-25 | 2008-10-27 | 2009-10-31 | 2009-10-31 | 2010-06-16 | 0 | Tax Credit 908-2008 | 0 | 38744000 | 738951.13 | 39482951.13 | 1.907% | 39482951.13 | 0 | 39482951.13 | 100% | 4.5347 | 100% | 0 | Project Closed | Final Acceptance
1003 | Ponce | Caribe | Rubén Cotto | J.A. Machuca | MD | Lombardo Pérez | Caribe General Constructors | 116 | 116 | 0 | 116 | 0 | 720 | 358.4 | 1078.4 | 49.78% | 1192 | 100% | 2002-12-01 | 2004-11-19 | 2005-11-12 09:36 | 2006-03-07 | 2006-06-07 | 0 | 0 | 0 | 11468000 | 1539402.23 | 13007402.23 | 13.42% | 13007402 | 0 | 13007402 | 100% | 10.2759 | 100% | 0 | Project Closed | Final Acceptance
5022 | Ponce | La Ceiba | Rubén Cotto | MJ Consulting | BMA | Ray Engineers PSC | Jafer Construction | 300 | 300 | 0 | 300 | 0 | 1281 | 283 | 1564 | 22.09% | 1514 | 100% | 2004-10-11 | 2008-04-13 | 2009-01-21 | 2008-12-03 | 2009-01-30 | 0 | Tax Credit | 0 | 29600820 | 1001464.91 | 30602284.91 | 3.383% | 30602284.91 | 0 | 30602284.91 | 100% | 5.0467 | 100% | 0 | Project Closed | Final Acceptance
5095 | Ponce | Las Terrazas | Rubén Cotto | AVP | ISS Corp. | Méndez, Brunner, Badillo & Associates | Homeca Recycling Center Co., Inc. | 100 | 100 | 0 | 100 | 0 | 365 | 0 | 365 | 0% | 344 | 100% | 2009-07-28 | 2010-07-27 | 2010-07-27 | 2010-07-07 | 2010-07-27 | 0 | Mixed Fund | 0 | 1085000 | 0 | 1085000 | 0% | 918124.83 | 0 | 918124.83 | 84.62% | 3.44 | 100% | 0 | Se entregaron los documentos de cierre, pero aun le falta por cobrar al contratista la Cert # 8 - Parcial (10/Agosto/10) $ 36,954.06 y Cert.#10 - Retenido Final (22/Oct/10) $108,500.00, para un Totasl de $145,454.06, mas reclamacion de intereses por pago tardio. Alega el contratista que le han informado de finanzas que los fondos estan congelados, pero no le han explicado razon. | Final Acceptance
1002 | Ponce | Santiago Iglesias (Fase II) | Noefebdo Ramírez | Individual Management | Klassik Builders | CSA | Jafer Construction | 120 | 120 | 0 | 120 | 0 | 790 | 66 | 856 | 8.354% | 855 | 100% | 2009-06-15 | 2011-08-13 | 2011-10-18 | 2011-10-18 | 2012-01-26 | 0 | ARRA | 0 | 14498820 | 637269.47 | 15136089.47 | 4.395% | 15136089.47 | 0 | 15136089.47 | 100% | 7.125 | 100% | 0 | Project Closed | Final Acceptance
3066 | Río Grande | José H. Ramírez | Luz Acevedo | A & M | AVP / ORAM | Raúl Feliciano & Asoc. | J R Builders | 80 | 80 | 0 | 80 | 0 | 540 | 317 | 857 | 58.7% | 853 | 100% | 2000-03-29 | 2001-09-19 | 2002-08-02 | 2002-07-30 | 2002-11-15 | 0 | 0 | 0 | 3404949 | 226802 | 3631751 | 6.661% | 3631751 | 0 | 3631751 | 100% | 10.6625 | 100% | 0 | Project Closed | Final Acceptance
5145 | San Germán | Manuel F. Rossy | Frank Nieves | Municipio de San Germán | MD | Unipro | Cap Con Inc. | 101 | 101 | 0 | 101 | 0 | 732 | 84 | 816 | 11.48% | 815 | 100% | 2009-06-22 | 2011-06-23 | 2011-09-15 | 2011-09-15 | 2011-12-31 | 0 | CFP/ARRA | 0 | 10316000 | 610969.8 | 10926969.8 | 5.923% | 10908277 | 0 | 10908277 | 99.83% | 8.0693 | 100% | 0 | Project Closed | Final Acceptance
5035 | San Juan | Villa Esperanza | Luz Acevedo | 0 | LMC | Guillermety, Ortiz & Asoc. | Del Valle Group | 300 | 300 | 0 | 300 | 0 | 1130 | 233 | 1363 | 20.62% | 1323 | 100% | 2003-06-18 | 2006-07-21 | 2007-03-11 | 2007-01-31 | 2007-03-30 | 0 | CFP | 0 | 19819000 | 1078350.46 | 20897350.46 | 5.441% | 20897350.46 | 0 | 20897350.46 | 100% | 4.41 | 100% | 0 | Project Closed | Final Acceptance
5077 | San Juan | La Rosa | Jorge Mercado | AUTO ADM. | LMC | García Joglar & Arq. | DGM Engineers | 52 | 52 | 0 | 52 | 0 | 730 | 270 | 1000 | 36.99% | 984 | 100% | 2000-10-02 | 2002-10-01 | 2003-06-28 | 2003-06-13 | 2004-07-19 | 0 | 0 | 0 | 4491000 | 510039 | 5001039 | 11.36% | 5001039 | 0 | 5001039 | 100% | 18.9231 | 100% | 0 | Project Closed | Final Acceptance
5026 | San Juan | Los Lirios | Frank Nieves | A & M | CCC Joint Venture | DG3A | Builders Associates, LLC | 150 | 150 | 0 | 150 | 0 | 854 | 275 | 1129 | 32.2% | 1142 | 100% | 2009-11-12 | 2012-03-14 | 2012-12-14 | 2012-12-28 | 2013-04-19 | 0 | ARRA/CFP | 0 | 15075000 | 523404.07 | 15598404.07 | 3.472% | 15598404.07 | 0 | 15598404.07 | 100% | 7.6133 | 100% | 0 | The Contractor submitted a claim for extended overhead by amount of $989,402.32 | Final Acceptance
5099 | San Juan | El Prado | José González | Cost Control | BMA | Ray Architects | Del Valle Group | 220 | 220 | 0 | 220 | 0 | 1260 | 78 | 1338 | 6.19% | 1202 | 100% | 2000-09-15 | 2004-02-26 | 2004-05-14 | 2003-12-31 | 2004-01-28 | 0 | CFP | 0 | 15715000 | 1037001 | 16752001 | 6.599% | 16752001 | 0 | 16752001 | 100% | 5.4636 | 100% | 0 | Project Closed | Final Acceptance
5192 | San Juan | Antigua Via | José González | MAS Corporation | BMA | Rodríguez & del Valle (Design & Build) | Rodríguez & del Valle | 200 | 200 | 0 | 200 | 0 | 882 | 147 | 1029 | 16.67% | 1338 | 100% | 2000-01-10 | 2002-06-09 | 2002-11-03 | 2003-09-09 | 2003-09-09 | 0 | CFP | 0 | 13397000 | 211211 | 13608211 | 1.577% | 13608211 | 0 | 13608211 | 100% | 6.69 | 100% | 0 | Project Closed | Final Acceptance
2010 | San Juan | Vista Hermosa II (Fase II) | José Negrón | MAS Corporation | AVP / Jorge L. Robert | Guillermety, Ortiz & Asoc. | Urban Builders | 476 | 476 | 0 | 476 | 0 | 1216 | 590 | 1806 | 48.52% | 1442 | 100% | 1997-04-07 | 2000-08-04 | 2002-03-17 | 2001-03-19 | 2001-12-13 | 0 | 0 | 0 | 17900000 | 1037096.5 | 18937096.5 | 5.794% | 18371767.14 | 0 | 18371767.14 | 97.01% | 3.0294 | 100% | 0 | Project Closed | Final Acceptance
5031 | San Juan | Jardines de Campo Rico | José Negrón | Cost Control | CMS | DG3A | North Connstruction | 196 | 196 | 0 | 196 | 0 | 750 | 263 | 1013 | 35.07% | 1012 | 100% | 2006-01-30 | 2008-02-18 | 2008-11-07 | 2008-11-07 | 2008-12-04 | 0 | Tax Credit | 0 | 19483000 | 17564 | 19500564 | 0.09015% | 19500564 | 0 | 19500564 | 100% | 5.1633 | 100% | 0 | Project Closed | Final Acceptance
5143 | San Juan | Monte Park | José Negrón | Housing Promoters | AVP / SAGA | Molinary | Fernández & Gutiérrez | 224 | 224 | 0 | 224 | 0 | 874 | 345 | 1219 | 39.47% | 1517 | 100% | 1996-11-01 | 1999-03-24 | 2000-03-03 | 2000-12-27 | 2001-03-09 | 0 | 0 | 0 | 10585212 | 350973 | 10936185 | 3.316% | 10936185 | 0 | 10936185 | 100% | 6.7723 | 100% | 0 | Project Closed | Final Acceptance
5017 | San Juan | San Martín | Luis Rodríguez | Housing Promoters | LMC | Enrique Ruiz & Assoc. | Del Valle Group | 300 | 300 | 0 | 300 | 0 | 1095 | 353 | 1448 | 32.24% | 1631 | 100% | 2003-05-14 | 2006-05-12 | 2007-04-30 | 2007-10-31 | 2008-01-30 | 0 | 0 | 0 | 19703000 | 845652.15 | 20548652.15 | 4.292% | 20180652.15 | 0 | 20180652.15 | 98.21% | 5.4367 | 100% | 0 | Project Closed | Final Acceptance
5023 | San Juan | San Fernando | Luis Rodríguez | Cost Control Company, Inc. | LMC | DDHK | Del Valle Group | 334 | 334 | 0 | 334 | 0 | 1190 | 807 | 1997 | 67.82% | 1965 | 100% | 2004-12-10 | 2008-03-13 | 2010-05-29 | 2010-04-28 | 2010-10-15 | 0 | Tax Credit | 0 | 32133000 | 1051432.05 | 33184432.05 | 3.272% | 33163350.99 | 0 | 33163350.99 | 99.94% | 5.8832 | 100% | 0 | Project Closed | Final Acceptance
5135 | San Juan | Las Dalias | Luis Rodríguez | Housing Promoters | CMS | CSA Architects | Del Valle Group | 240 | 240 | 0 | 240 | 0 | 1195 | 271 | 1466 | 22.68% | 1458 | 100% | 2004-02-25 | 2007-06-03 | 2008-02-29 | 2008-02-22 | 2008-04-22 | 0 | Tax Credit 908-2008 | 0 | 22437872.18 | 818872.18 | 23256744.36 | 3.65% | 23256744.36 | 0 | 23256744.36 | 100% | 6.075 | 100% | 0 | Project Closed | Final Acceptance
5161 | San Juan | El Manatial | Luis Rodríguez | MAS Corporation | CMS | Behar-Ybarra | Del Valle Group | 200 | 200 | 0 | 200 | 0 | 890 | 345 | 1235 | 38.76% | 1234 | 100% | 2004-01-26 | 2006-07-03 | 2007-06-13 | 2007-06-13 | 2008-05-19 | 0 | 0 | 0 | 12929000 | 1024355.41 | 13953355.41 | 7.923% | 13953355.41 | 0 | 13953355.41 | 100% | 6.17 | 100% | 0 | Project Closed | Final Acceptance
5080 | San Juan | Jardines de Cupey | Félix Ortiz | Cost Control Company, Inc. | URS Caribe | Gautier & de Torres | Ferrovial Agroman | 308 | 308 | 0 | 308 | 0 | 1095 | 628 | 1723 | 57.35% | 1660 | 100% | 2006-02-15 | 2009-02-13 | 2010-11-03 | 2010-09-02 | 2011-08-22 | 0 | Tax Credit | 0 | 33630461 | 1042731.4 | 34673192.4 | 3.101% | 34673192.4 | 0 | 34673192.4 | 100% | 5.3896 | 100% | 0 | Project Closed | Final Acceptance
5040 | San Juan | Jardines de Sellés Fase I (Take over agreement) | Luz Acevedo | 0 | BMA | URS Dames & Moore | Urban Builders (St. Paul Surety) | 184 | 184 | 0 | 184 | 0 | 90 | 0 | 90 | 0% | 114 | 100% | 2003-08-20 | 2003-11-17 | 2003-11-17 | 2003-12-12 | 2004-02-17 | 0 | CFP | 0 | 9975000 | 231719 | 10206719 | 2.323% | 10206719 | 0 | 10206719 | 100% | 0.61957 | 100% | 0 | Project Closed | Final Acceptance
5040 | San Juan | Jardines de Sellés (Fase II) | Luz Acevedo | Housing Promoters | BMA | URS Caribe | Rodríguez & del Valle | 216 | 216 | 0 | 216 | 0 | 1095 | 320 | 1415 | 29.22% | 1415 | 100% | 2002-06-17 | 2005-06-15 | 2006-05-01 | 2006-05-02 | 2007-05-27 | 0 | 0 | 0 | 15268000 | 968748 | 16236748 | 6.345% | 16236748 | 0 | 16236748 | 100% | 6.5509 | 100% | 0 | Project Closed | Final Acceptance
5015-5140 | San Juan | Las Gladiolas I & II | Félix Ortiz | MAS Corp. | CCC-JV | Méndez-Brunner | Del Valle Group | 676 | 676 | 0 | 676 | 0 | 365 | 77 | 442 | 21.1% | 449 | 100% | 2011-04-11 | 2012-04-09 | 2012-06-25 | 2012-07-03 | 2013-02-08 | 0 | CFP | 0 | 2932000 | 129200.55 | 3061200.55 | 4.407% | 3061200.55 | 0 | 3061200.55 | 100% | 0.6642 | 100% | 0 | Pending Close Out | Final Acceptance
2003 | San Juan | Puerta de Tierra | Pedro Vega | Cost Control Company, Inc. | LMC | Guillermety, Ortiz & Asoc. | Homeca Recycling 2007-0498A | 148 | 148 | 0 | 148 | 0 | 150 | 300 | 450 | 200% | 543 | 100% | 2007-03-22 | 2007-08-18 | 2008-06-13 | 2008-09-15 | 0 | 0 | CFP | 0 | 678000 | 152491.82 | 830491.82 | 22.49% | 830492 | 0 | 830492 | 100% | 3.6689 | 100% | 0 | Project Closed | Final Acceptance
2003 | San Juan | New Puerta de Tierra | Pedro Vega | Cost Control Company, Inc. | LMC | Guillermety, Ortiz & Asoc. | Cué & López Construction, Inc | 85 | 85 | 0 | 85 | 0 | 900 | 20 | 920 | 2.222% | 823 | 100% | 2008-11-10 | 2011-04-28 | 2011-05-18 | 2011-02-11 | 2011-05-17 | 0 | CFP/Línea de Crédito | 0 | 16770000 | 813871.99 | 17583871.99 | 4.853% | 17583871.99 | 0 | 17583871.99 | 100% | 9.6824 | 100% | 0 | Project Closed | Final Acceptance
2004 | San Juan | San Agustín | José M. Paris Escalera | AM Contractors | Klassik Builders | Ray Engineers PSC | Cuè & López Construction, Inc | 84 | 84 | 0 | 84 | 0 | 570 | 304 | 874 | 53.33% | 869 | 100% | 2009-12-14 | 2011-07-06 | 2012-05-05 | 2012-05-01 | 2012-07-18 | 0 | ARRA | 0 | 3746000 | 1029880.39 | 4775880.39 | 27.49% | 4775880.39 | 0 | 4775880.39 | 100% | 10.3452 | 100% | 0 | Project Closed | Final Acceptance
2012 | San Juan | Villa España | Pedro Vega | Cost Control Company | LMC | Ray Engineers, PSC | Rodríguez & del Valle | 500 | 500 | 0 | 500 | 0 | 1280 | 929 | 2209 | 72.58% | 2208 | 100% | 2003-09-29 | 2007-03-31 | 2009-10-15 | 2009-10-15 | 2010-10-21 | 0 | Tax Credit | 0 | 33768000 | 1862123 | 35630123 | 5.514% | 35630123 | 0 | 35630123 | 100% | 4.416 | 100% | 0 | Project Closed | Final Acceptance
3090 | Salinas | Bella Vista | Félix Ortiz | MJ Consulting | Klassik Builders | INTEGRA | LPC&D | 100 | 100 | 0 | 100 | 0 | 730 | 160 | 890 | 21.92% | 889 | 100% | 2009-09-08 | 2011-09-07 | 2012-02-14 | 2012-02-14 | 2012-07-16 | 0 | ARRA | 0 | 10500000 | 749675.93 | 11249675.93 | 7.14% | 11249675.93 | 0 | 11249675.93 | 100% | 8.89 | 100% | 0 | 0 | Final Acceptance
5092 | San Lorenzo | La Lorenzana | Iván Blanco | MJ Consulting | URS | René Acosta Ingenieros | CD Builders | 100 | 100 | 0 | 100 | 0 | 730 | 351 | 1081 | 48.08% | 1147 | 100% | 2005-09-14 | 2007-09-13 | 2008-08-29 | 2008-11-04 | 2009-09-17 | 0 | Tax Credit | 0 | 10310000 | 828444.55 | 11138444.55 | 8.035% | 11138444.55 | 0 | 11138444.55 | 100% | 11.47 | 100% | 0 | Project Closed | Final Acceptance
3087 | San Sebastian | Andrés Méndez Liceaga | Arturo Acevedo | Inn Capital Housing Division Joint Venture | CMS | Interplan | RC Engineering | 150 | 150 | 0 | 150 | 0 | 960 | 729 | 1689 | 75.94% | 1688 | 100% | 2004-05-24 | 2007-01-08 | 2009-01-06 | 2009-01-06 | 2009-02-16 | 0 | Tax Credit | 0 | 13130000 | 401586.86 | 13531586.86 | 3.059% | 13531587 | 0 | 13531587 | 100% | 11.2533 | 100% | 0 | Project Closed | Final Acceptance
5144 | Santa Isabel | Rincón Taíno | Rubén Cotto | J. A. Machuca | BMA | Hernández - Bauzá | Constructora I. Meléndez | 100 | 100 | 0 | 100 | 0 | 810 | 499 | 1309 | 61.6% | 1087 | 100% | 2003-07-28 | 2005-10-14 | 2007-02-25 | 2006-07-19 | 2006-09-30 | 0 | 0 | 0 | 7231087 | 175900 | 7406987 | 2.433% | 6372476 | 0 | 6372476 | 86.03% | 10.87 | 100% | 0 | Las OC # 7 y 8 fueron sometidas por el CM, pero le fueron devueltas para aclaracion o correccion, ya que el NGC no esta de acuerdo con el tiempo de extension otorgado y los "supporting documents". Posteriormente el CM las entrego fuera del termino de vigencia y las mismas no se pudieron procesar. El contratista sometio demanda y se efectuo reunion entre ambas representaciones legales. Se llego a un acuerdo: AVP de pagar lo que se le adeudaba por concepto de daños liquidos y retenido, Contratista: No reclamar "extended overhead" ni la OC #8. Esto hace varios meses y AVP tiene pendiente procesar los pagos correspondientes. | Final Acceptance
5198 | Toa Alta | Jardines de San Fernando | Luis Rodríguez | Housing Promoters | MD | URS Caribe, LLP | Orion Contractors | 51 | 51 | 0 | 51 | 0 | 800 | 1627 | 2427 | 203.4% | 2502 | 100% | 2006-01-09 | 2008-03-18 | 2012-08-31 | 2012-11-15 | 2013-10-15 | 0 | BFP-2003 | 0 | 7227000 | -982226.89 | 6244773.11 | -13.59% | 6244773.11 | 0 | 6244773.11 | 100% | 49.0588 | 100% | 0 | The PRPHA and the Contractor signed a Termination by Convinience (TBC), where the contractor grants a creditfor the amount of $2,182,368.61 for the remaining work phase IV,V and VIII. The PRPHA extends the contract by 744 calendar days providing a substantial termination effective at the August 31, 2012. The contractor walves its claim for extended overhead. | Final Acceptance
3069 | Toa Baja | El Toa | Jorge Mercado | MJ Consulting | AVP | Soler Cloquel & Asoc. | Royal Ins. | 80 | 80 | 0 | 80 | 0 | 669 | 458 | 1127 | 68.46% | 1205 | 100% | 1997-06-30 | 1999-04-29 | 2000-07-30 | 2000-10-17 | 2001-05-18 | 0 | 0 | 0 | 4045086 | 299127 | 4344213 | 7.395% | 4344213 | 0 | 4344213 | 100% | 15.0625 | 100% | 0 | Project Closed | Final Acceptance
5193 | Trujillo Alto | Los Rosales | José M. Paris Escalera | Peregrine Group Inc. | Klassik Builders | URS Caribe, LLP | Cidra Excavation, SE | 74 | 74 | 0 | 74 | 0 | 730 | 138 | 868 | 18.9% | 821 | 100% | 2009-11-16 | 2011-11-15 | 2012-04-01 | 2012-02-15 | 2012-08-14 | 0 | ARRA | 0 | 7947800 | 1458351.48 | 9406151.48 | 18.35% | 9406151.48 | 0 | 9406151.48 | 100% | 11.0946 | 100% | 0 | Project Closed | Final Acceptance
3071 | Vega Alta | Fco. Vega Sánchez | José Negrón | MJ Consulting | LMC | Hernández - Bauzá | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 782 | 109 | 891 | 13.94% | 890 | 100% | 2000-10-02 | 2002-11-22 | 2003-03-11 | 2003-03-11 | 2003-04-11 | 0 | 0 | 0 | 9309000 | 70614.85 | 9379614.85 | 0.7586% | 9379616 | 0 | 9379616 | 100% | 8.9 | 100% | 0 | Project Closed | Final Acceptance
5105 | Vega Alta | Las Violetas | Luis Rodríguez | Cost Control Company, Inc. | ISS | URS Dames & Moore | Del Valle Group | 88 | 88 | 0 | 88 | 0 | 730 | 150 | 880 | 20.55% | 1000 | 100% | 2006-02-01 | 2008-01-31 | 2008-06-29 | 2008-10-28 | 2009-09-30 | 0 | Tax Credit | 0 | 9203600 | 46081.53 | 9249681.53 | 0.5007% | 9007681.53 | 0 | 9007681.53 | 97.38% | 11.3636 | 100% | 0 | Project Closed | Final Acceptance
3073 | Villalba | Efraín Suárez Negrón | Arturo Acevedo | J.A. Machuca | CMS | Yañez & Mayol | Ravaro Construction | 60 | 60 | 0 | 60 | 0 | 660 | 295 | 955 | 44.7% | 1240 | 100% | 2002-04-15 | 2004-02-03 | 2004-11-24 | 2005-09-06 | 2005-09-06 | 0 | 0 | 0 | 4033500 | 93123 | 4126623 | 2.309% | 4126623 | 0 | 4126623 | 100% | 20.6667 | 100% | 0 | Project Closed | Final Acceptance
5164 | Villalba | Maximino Miranda Jiménez | Félix Ortiz | Municipio de Villalba | Klassik Builders | LPA Group, Arq. | Constructora I. Meléndez | 100 | 100 | 0 | 100 | 0 | 732 | 180 | 912 | 24.59% | 911 | 100% | 2009-05-20 | 2011-05-21 | 2011-11-17 | 2011-11-17 | 2012-01-19 | 0 | CFP/ARRA | 0 | 12392438 | 408291.81 | 12800729.81 | 3.295% | 12800729.81 | 0 | 12800729.81 | 100% | 9.11 | 100% | 0 | Project Closed | Final Acceptance
5067 | Yauco | Ext. Santa Catalina | Rubén Cotto | Inn Capital Housing Division Joint Venture | URS | René Acosta Ingenieros | A. Rivera & Asociados | 24 | 24 | 0 | 24 | 0 | 548 | 319 | 867 | 58.21% | 814 | 100% | 2006-01-16 | 2007-07-17 | 2008-05-31 | 2008-04-09 | 2008-08-26 | 0 | CFP-2003 | 0 | 1972404 | 50556.96 | 2022960.96 | 2.563% | 2022961 | 0 | 2022961 | 100% | 33.9167 | 100% | 0 | Project Closed | Final Acceptance
| 7 | Active | [5 empty] | 1656 | 1626 | 0 | 1626 | 0 | [14 empty] | 0 | 0 | 90126409.88 |  | 0 | 0 | 86089768.12 |  |  |  | 0 |  | Active
| 2 | Stoped | [5 empty] | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | Stoped
| 10 | Substantial | [5 empty] | 1656 | 1626 | 0 | 1626 | 0 | [14 empty] | 79925735 | 10200674.88 | 90126409.88 |  | 86089768.12 | 0 | 86089768.12 |  | 13.542 |  | 0 |  | Substantial Completion
| 110 | Final Acceptance | [5 empty] | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 9.8658 |  |  |  | Final Acceptance
Total | 129 | [6 empty] | 20299 | 19627 | 78 | 19705 | 60 | [14 empty] | 1493538072.27 | 97622150.87 | 1681286633.02 |  | 1558880043.8708 | 1271462.02 | 1646241274.0108 |  | 10.1721 |  | 0 |  | Total
| Revised by: |  |  |  | Approved by: | [19 empty] | Approved by:
|  | Luz M. Acevedo Pellot, PE |  |  |  |  | Germán Acevedo Marín, PE | [18 empty] | Arturo A. Garcia de la Noceda Castro, PE
|  | Project Coordinator |  |  |  |  | Director | [18 empty] | Deputy Administrator
|  | Construction Management Bureau |  |  |  |  | Construction Management Bureau | [18 empty] | Development and Construction Area
Report Date: |  |  | 2014-04-30
Report Last Revision Date: |  |  | 2014-05-10
Notes/Notas:
CMB Monthly Report is prepared for the use of Construction and Development Area. The Associate Administrator will approve any use of this report outside this area and must have his signature to be valid.
Informe preparado para uso del Área de Desarrollo y Construcción de Proyectos. El Administrador Asociado aprobará cualquier uso de este Informe fuera del Área y debe tener su firma para ser válido.
Information is provided by PRPHA Project Monitors, and is subject to change.
La Información es suministrada con los datos que proveen los Monitores de Proyectos, por lo que está sujeta a cambios.
Final Acceptance Report contains all Projects. This report is not worked by fiscal or natural year, it is a report that contains cumulative information and not all projects present monthly changes.
El Informe de "Final Acceptance" contiene todos los Proyectos. No se trabaja por Año Natural o Año Fiscal; es un reporte que contiene información acumulativa y no en todos los Proyectos se presentan cambios mensuales.
NOTIFICACIÓN DE CONFIDENCIALIDAD: Este Informe y cualquier archivo transmitido en ella pueden contener información confidencial, privilegiada y/o privada bajo las leyes aplicables. Se utiliza solamente para el uso o entidad a que se dirige. Si usted no es el destinatario intencional, se le notifica que cualquier uso, diseminación o copia de esta Informe se prohíbe estrictamente. Si usted recibe esta Informe por error, notificar al remitente inmediatamente y destruir el material en su totalidad.
CONFIDENTIALITY NOTICE: This report and any files transmitted with it may contain information that is confidential, privileged and exempt from disclosure under applicable law. It is intended solely for the use of the individual or entity to which it is addressed. If you are not the intended recipient, you are hereby notify that any use, dissemination or copying of this report is strictly prohibited. If you have received this communication by error, immediately contact the sender and destroy the material in its entirety, whether in electronic of hard copy format.
Note on AC15: lvlynn: Discrepancia: $98,932 Inf. Monitor
Note on H48: lvlynn: Contratista Default Target Engineering
Note on W77: lvlynn: 9-junio-09 Final
Note on W81: lvlynn:
Note on AC96: OC 1 @ 13
Note on Z97: lvlynn: CFP-Línea de Crédito

## ACCEPTANCE PROJECTS MONTLY REPO
A | B | C | D | E | F | G | H | I | J | K | L=J+K | M | N | O | P=N+O | Q=O/N | R=DATE-T | S=R/P | T | U=T+N-1 | V=T+P-1 | W | X | Y | Z | AA | AB | AC | AD=AB+AC | AE=AC/AB | AF | AG | AH=AF+AG | AI=AH/AD | AJ=(W-T)/I | AK |  | AK | AL
RQ | Municipality | Name of the Project | PHAPR Monitor | Management Agent | Construction Manager/PM | Designer (A/E) | Contractor | Units |  |  |  |  | Times | [5 empty] | Dates | [5 empty] | Funds | [9 empty] | Certified Days/Unit | % Progress | Monthly Employment | Executive Summary | Status
[8 empty] | Total Dwelling Units | Previous Completed Dwelling Units | Completed Dwelling Units for this Period | Total Completed Dwelling Units | Dwelling Units Forecast for next Month | Contruction Period (Cal. Days) | Time Extension (Cal. Days) | Revised Construction Period (Cal. Days) | % Extended Time | Elapsed Time (Cal. Days) | Elapsed Time (%) | Construction Start Date | Original Completion Date | Revised Construction Completion Date | Substantial Completion Date | Final Acceptance Date | Registered at Controller Contract Termination Date | Funds Proceeds | Funds Obligation Date | Original Construction Contract Amount | Approved Change Orders Amount ($) | Revised Construction Contract Amount | % Of Change Orders | Previous Certified Amount | Certified this Period | Total Certified Amount | Certified Amount (%)
3025 | Carolina | Felipe Sánchez Osorio (Demolition) | Luis Rodríguez | N/A | Municipio de Carolina | State Engineering | Municipio de Carolina | 32 | 26 | 0 | 26 | 0 | 120 | 0 | 120 | 0% | 259 | 215.8% | 2013-08-14 | 2013-12-11 | 2013-12-11 | 0 | 0 | 0 | 0 | 0 | 336510 | 0 | 336510 | 0% | 27516.72 | 122054.24 | 149570.96 | 44.45% |  | 0% | 0 | ♦ Project Situation according to the CPM Uptaded: Phase I was completed on November 27, 2013. ♦ Reasons of the Delay (if applies) N/A ♦ Change Order in PRPHA pending for approval: N/A ♦ Extraordinary Situations with Relocation (if applies)- N/A ♦ Situations with Governmental Agencies (if applies): N/A ♦ Others situations that are affecting the project (if Applies): N/A | Active
5127 | Arecibo | La Meseta | Pedro Vega | Housing Promoters, Inc. | AVP | ERA | Maglez Engineering & Contractors, Corp. | 0 | 0 | 0 | 0 | 0 | 365 | 0 | 365 | 0% | 394 | 107.9% | 2013-04-01 | 2014-03-31 | 2014-03-31 | 0 | 0 | 2014-03-31 | CFP | 0 | 1602797 | 0 | 1602797 | 0% | 979943.16 | 71165.27 | 1051108.43 | 65.58% |  | 0% | 0 | • Project Situation: Some submmittal requirement from designer are delaying the Contractor's time to make purchase orders or solve construction problems as design error for primary system upgrade. • Project Status: Last CPM Updated february 28,2014, refected a reduction of project delay from 49 days behind schedule. There is a CO #1 with 14 calendars days pending for PRPHA approval. New letter of intents are in negotiation that can reflect additional extension claim. • Change Orders: CO #1 $41,193.88 where send to PRPHA. • Last Certification: #11 february 28, 2014 • Relocation issues: There is not Relocation issues. • Goverment Agencies issues: AEE are requiring change to approved design that represent additional cost to project. • Other Situation issues: There is not AAA endorsement. this month the designer submmit the endorsement amedment. | Active
4011 | Mayaguez | Rafael Hernandez (El Kennedy) | Noefebdo Ramírez | JA Machuca | Klassik Builders | Hernán Jr. Machado Ingenieros Consultores | F & R Construction | 190 | 26 | 0 | 26 | 24 | 1094 | 153 | 1247 | 13.99% | 926 | 74.26% | 2011-10-17 | 2014-10-14 | 2015-03-16 | 0 | 0 | 2016-02-07 | CFP | 0 | 21797000 | 446287.81 | 22243287.81 | 2.047% | 13868385.06 | 204312.21 | 14072697.27 | 63.27% |  | 0% | 0 | • Project situation according to the CPM updated: According to the last CPM updated, the project finish date is September 3, 2015. The contract revisedconstruction completion date is March 16,2015. That represent 171 days of delay. When thechange order # 9 be approvedthe completion date move to May 30, 2015. the Change Order # 10 included 10 aditional days for weather conditions. Then represent 58 days of delay. • Reasons of the Delay: One reasons is the delay for termination and delivery of modernized units by the Contractors. The lead and asbestos abatement started on February 3,2014 to enclosure the building # 4. The buildingcome to be ready to start the works on March 21,2014, No contruction works can't do it into the buildings. Those impact the crithical path which is total responsability of the contractor. In special the building # 18, which in the next building in the modernization sequence and are stopped for 108 days. • Change Order in PRPHA pending for approval:. The CO # 9 (193,914.32 and include 75 calendar days extension) and change order # 10 (of $562,564.73 and include 10 calendar days extension) • Payments Certifications Status: The Contractor has pending to submit to PRPHA the Certifications for partial payment of # 30 (February 2014 period) and # 31 (March 2014 period) • Extraordinary Situations with Relocation - N/A • Situations with Governmental Agencies: The tapping conection for the potable water services, under the PR #2 state road was not do it in this period. This tapping is a change order in a process of negotiation. The AAA final endosement depend of finish this connection works. The Puerto Rico Power Authority present a new request to install other facilities for existingsanitary pump station. That works were not contemplted in the design. • Others situations that are affecting the project: The installationof the restrainers in the 36 inches ductile iron forced line was not completed in this period. A 70% of the total pipe line need to be reinstalling. A wprkplan was by KBI to the Contractor to define this work to be done during summer school vacation as requested. | Active
3105 | San Juan | Ext. Manuel A. Pérez | Arturo Acevedo | MAS Corp. | Klassik Builders | DDHK | LPC&D | 324 | 188 | 12 | 200 | 12 | 1098 | 433 | 1531 | 39.44% | 1385 | 90.46% | 2010-07-15 | 2013-07-16 | 2014-09-22 | 0 | 0 | 2015-08-06 | HOPE IV | 0 | 24800000 | 1110120.04 | 25910120.04 | 4.476% | 19847694.84 | 161086 | 20008780.84 | 77.22% |  | 0% | 0 | • Project situation according to the CPM updated • Reasons of the Delay (if applies) • Payments Certifications Status- Lastcertification rendered for payment is certification # 42, for the period of January 2014. • Change Orders: • Extraordinary Situations with Relocation (if applies)-N/A • Situations with Governmental Agencies (if applies)-N/A • Others situations that are affecting the project (if applies)-N/A • Withheld: | Active
5034 | San Juan | Alturas de Cupey | José M. Paris | SP Management Corp. | Klassik Builders | CSA | F&R Construction | 96 | 48 | 16 | 64 | 0 | 732 | 256 | 988 | 34.97% | 1057 | 107% | 2011-06-08 | 2013-06-08 | 2014-02-19 | 0 | 0 | 2015-06-20 | CFP | 0 | 7936000 | 1003018.78 | 8939018.78 | 12.64% | 7832237.98 | 470242.15 | 8302480.13 | 92.88% |  | 0% | 0 | • Project situation according to the CPM updated: According to the last CPM updated on June 2013, the project is 72 calendar days ahead schedule with a possible termination date on December 19, 2013. • Reasons of the Delay (if applies) • Bad execution by the Contractor (if applies)- N/A • Change Orders pending for approval - N/A • Others (if applies) - a) Weather and site conditions (Soil Moisture) • Change Order in PRPHA pending for approval: N/A • Latest Certification: The last certification for payment submitted by the Contractor correspond to the period of July 26, 2013 thru August 25, 2013 (Certification #27 for the amount of $470,242.15 • Extraordinary Situations with Relocation (if applies) - N/A • Situations with Governmental Agencies (if applies) - N/A • Others situations that are affecting the project (if applies) - N/A | Active
5068 | San Juan | Las Amapolas (Demolition) | Noefebdo Ramírez | SP Management Corp. | AVP | Integra | Anibal Díaz Construction, Inc. | 204 | 138 | 50 | 188 | 16 | 365 | 0 | 365 | 0% | 176 | 48.22% | 2013-11-05 | 2014-11-04 | 2014-11-04 | 0 | 0 | 2015-10-30 | CFP | 0 | 948000 | 0 | 948000 | 0% | 231193.27 | 0 | 231193.27 | 24.39% |  | 0% | 0 | • Project situation according to CPM (updated): According to the CPM, the project is on schedule. • Reasons of Delay: none • Change Orders in PRPHA pending for Approval: none • Payments CertificationS Status: The contractor has pending to submit to PRPHA the certificactions for the partial Payments # 3 (February 2014) and #4 (March 2014 period) • Extraordinary situations with Relocation: N/A • Situations with Governmental Agencies: none • Other situations that are affecting the project: No report in this moment. | Active
5028 | Yauco | Ana Catalina Rodríguez Vélez (Santa Catalina) | Arturo Acevedo | JA Machuca | AVP | URS Caribe LLC | La Mar Construction Corporation | 200 | 154 | 0 | 154 | 8 | 1098 | 339 | 1437 | 30.87% | 1525 | 106.1% | 2010-02-25 | 2013-02-26 | 2014-01-31 | 0 | 0 | 2014-11-26 | ARRA/Mixed | 0 | 17447000 | 1678841 | 19125841 | 9.623% | 17208971.22 | 242602.15 | 17451573.37 | 91.25% |  | 0% | 0 | • Project situation according to CPM (updated): • Reasons of Delay: • Change Orders in PRPHA pending for Approval: • latest Certification: Last certification rendered for payment is certification # 49 (February 2014) • Extraordinary situations with Relocation: N/A • Situations with Governmental Agencies: N/A • Other situations that are affecting the project: N/A | Active
5011 | San Juan | Jardines del Paraíso | José Negrón | Cost Control Company, Inc. | BMA | Andrés Hernández & Asoc. | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 41759 | #DIV/0! | 0 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | 0% | 0 | Proyecto en Re-Subasta. Subasta declarada Desierta. No se ha Comenzado el proyecto. | Stoped
3049 | Lajas | Las Américas | Noefebdo Ramírez | Inn Capital Housing Division Joint Venture | none | URS Caribe, LLP | none | 80 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | #DIV/0! | 41759 | #DIV/0! | 0 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | 0% | 0 | Design completed. Pending for will be assigned construction funds by PHA. | Stoped
3100 | Aguadilla | Agustín Stahl I | Arturo Acevedo | American Management Corp. | CCC-JV | René Acosta Arquitectos | Karimar Construction, Inc. | 180 | 180 | 0 | 180 | 0 | 915 | 192 | 1107 | 20.98% | 1100 | 100% | 2010-03-23 | 2012-09-22 | 2013-04-02 | 2013-03-27 | 0 | 0 | ARRA/CFP | 0 | 13875675 | 597322.95 | 14472997.95 | 4.305% | 13367679 | 0 | 13367679 | 92.36% | 6.1111 | 0% | 0 | Project started on march 23, 2010. substantial completion was awarded on March 27 2013 Last certification rendered for payment is certification # 38, for the period of March 1 to 30, 2013. | Substantial Completion
5201 | Cayey | Alturas de Montellano | Jorge Mercado | Municipio | LMC | Arq. José Luzunaris | RC Group S.E. | 80 | 50 | 0 | 50 | 0 | 730 | 846 | 1576 | 115.9% | 1970 | 100% | 2001-09-04 | 2003-09-03 | 2005-12-27 | 2007-01-26 | 0 | 0 | CFP | 2001-11-21 | 4790000 | 2327268.37 | 7117268.37 | 48.59% | 7036300.8 | 0 | 7036300.8 | 98.86% | 24.625 | 0% | 0 | Nunca se aprobaron las ordenes de cambio #17 y #18 porque el contratista no sometió los documentos solicitados por el Área de Adquisición y Contratación. Nunca se le otorgó el "Final Acceptance". El caso esta siendo atendido en la División Legal de la Admnisitración de Vivienda Pública. Queda un balance de $80,967.57 en espera se resuelva la controversia. | Substantial Completion
3089 | Juana Díaz | Villa del Parque (Take over agreement) | Rubén Cotto | J.A. Machuca | MD | GMG Eng. Consultants | (USF & G) | 100 | 100 | 0 | 100 | 0 | 547 | 746 | 1293 | 136.4% | 552 | 100% | 2000-12-18 | 2002-06-17 | 2004-07-02 | 2002-06-23 | 0 | 0 | CFP | 2000-09-30 | 3105100 | 239005.38 | 3344105.38 | 7.697% | 3171314 | 0 | 3171314 | 94.83% | 5.52 | 0% | 0 | El "final acceptance" le fue entregado a la Administracion del proyecto , JA Machuca, no obstante los mismos no lo han firmado ya que la Aseguradora no ha sometido aun los documentos de garantía de techo. Se le indicó vervalmente al Ing. Carrasquillo, representante de la Aseguradora. | Substantial Completion
3093 | Juncos | Narciso Varona Fase II | José González | MJ Consulting | AVP | DG3A Design Group, PSC | F & R Construction Group, Inc. | 172 | 172 | 0 | 172 | 0 | 1220 | 235 | 1455 | 19.26% | 1385 | 100% | 2010-02-24 | 2013-06-27 | 2014-02-17 | 2013-12-10 | 0 | 0 | Arra/Mixed | 0 | 13189000 | 822958.39 | 14011958.39 | 6.24% | 13762592.18 | 0 | 13762592.18 | 98.22% | 8.0523 | 0% | 0 | Project is almost completed. | Substantial Completion
5053 | Mayagüez | Ramírez de Arellano | Pedro Vega | JA Machuca | LMC | GMG Engineering | Comas & Comas Contractors, Corp | 80 | 80 | 0 | 80 | 0 | 720 | 661 | 1381 | 91.81% | 1375 | 100% | 2009-07-13 | 2011-07-02 | 2013-04-23 | 2013-04-18 | 0 | 0 | ARRA/CFP | 0 | 4040000 | 2215708.24 | 6255708.24 | 54.84% | 6011262.53 | 0 | 6011262.53 | 96.09% | 17.1875 | 0% | 0 | Final Completion and Close Out era specting for: 1) PRPHA approval CO#9 and CO#10; 2)Contractor correction of payroll defiecience | Substantial Completion
3058 | Moca | José N. Gándara | Noefebdo Ramírez | NFC | CMS | Ray Engineers PSC | Moss Construction | 74 | 74 | 0 | 74 | 0 | 896 | 73 | 969 | 8.147% | 940 | 100% | 1999-11-08 | 2002-04-21 | 2002-07-03 | 2002-06-05 | 0 | 0 | CFP-02 | 2000-01-13 | 4671000 | 238289 | 4909289 | 5.101% | 4805897.22 | 0 | 4805897.22 | 97.89% | 12.7027 | 0% | 0 | The close out was not completed because the Contractor not submit to PRPHA the final documents required by the Construction and Management Bureau and the Legal Division of the PRPHA. The solution of this case was referred to Legal Division of the PRPHA. | Substantial Completion
5088 | Ponce | Lirios del Sur | Arturo Acevedo | MJ Consulting | CMS | CSA | Caribe General Constructors | 400 | 400 | 0 | 400 | 0 | 791 | 487 | 1278 | 61.57% | 1267 | 100% | 2009-03-02 | 2011-05-01 | 2012-08-30 | 2012-08-20 | 0 | 0 | CFP | 0 | 16598000 | 2352431.7 | 18950431.7 | 14.17% | 17140589.22 | 0 | 17140589.22 | 90.45% | 3.1675 | 0% | 0 | Project started in march 2009, The contrator finished the instalation of the luminaries on the fence of the west side of the project. Last certification rendered for payment is certification # 35, which is the 50% of retainage. | Substantial Completion
5056 | Guaynabo | Loa Alamos | José González | Municipio de Guaynabo | Klassik | Hernández-Bauzá | Homeca Recycling | 376 | 376 | 0 | 376 | 0 | 549 | 0 | 549 | 0% | 547 | 100% | 2012-09-17 | 2014-03-19 | 2014-03-19 | 2014-03-18 | 0 | 0 | CFP | 0 | 2339000 | -40565.21 | 2298434.79 | -1.734% | 2149223.01 | 0 | 2149223.01 | 93.51% | 1.4548 | 0% | 0 | Project is almost completed. | Substantial Completion
5166 | San Juan | Brisas de Cupey | José M. Paris | SP Management Corp. | CCC-JV | Fracinetti Arquitectos | Pitirre Copnstruction | 184 | 184 | 0 | 184 | 0 | 993 | 127 | 1120 | 12.79% | 1251 | 100% | 2010-02-26 | 2012-11-14 | 2013-03-21 | 2013-07-31 | 0 | 0 | ARRA/CFP | 0 | 15326960 | 1013140.06 | 16340100.06 | 6.61% | 16340100.06 | 0 | 16340100.06 | 100% | 6.7989 | 0% | 0 | The Program Manager is preparing the change order # 10, this CO has time extension by wheater condition and delay in the delivery of the building # 12 to the Contractor. The six building completed and we are waiting for legal RW documents, | Substantial Completion
3070 | Trujillo Alto | Pedro Regalado Díaz | José González | Inn Capital Housing Division Joint Venture | MD | Ray Engineers PSC | José L. Colón | 10 | 10 | 0 | 10 | 0 | 273 | 226 | 499 | 82.78% | 498 | 100% | 2008-04-14 | 2009-01-11 | 2009-08-25 | 2009-08-25 | 0 | 0 | CFP | 0 | 1991000 | 435116 | 2426116 | 21.85% | 2304810.1 | 0 | 2304810.1 | 95% | 49.8 | 0% | 0 | ♦ Repair of Units and Administration Building - The Management Agent has prepared a report about the scope of work and cost to repair units that will be delivered to the residents. Extraordinary Maintenance Office (PHAPR) is working with this item. ♦ Existing post removal - This work will be performed once the AEE connects the project and the Cable TV Company removes its wiring. ♦ Claim of the Contractor Jose Luis Colon - it was assigned to PGES to work with it. | Substantial Completion
3030 | Adjuntas | Villa Valle Verde | Pedro Vega | J.A. Machuca | URS | Jorge L. Roberts, PSC | Venegas Construction | 150 | 150 | 0 | 150 | 0 | 913 | 144 | 1057 | 15.77% | 1743 | 100% | 2001-01-15 | 2003-07-16 | 2003-12-07 | 2005-10-24 | 2007-02-06 | 0 | 0 | 0 | 11829000 | 337235 | 12166235 | 2.851% | 12103923 | 0 | 12103923 | 99.49% | 11.62 | 100% | 0 | These Close out is in process by PGES. | Final Acceptance
3034 | Aguada | Francisco Egipciaco | Noefebdo Ramírez | NFC | CMS | Arq. José Luzunaris | NLL Construction | 100 | 100 | 0 | 100 | 0 | 887 | 0 | 887 | 0% | 819 | 100% | 2000-03-23 | 2002-08-26 | 2002-08-26 | 2002-06-20 | 2002-10-04 | 0 | 0 | 0 | 8107810 | 207539 | 8315349 | 2.56% | 8315349 | 0 | 8315349 | 100% | 8.19 | 100% | 0 | Project Closed | Final Acceptance
5252 | Aguada | Los Robles | Noefebdo Ramírez | NFC | CMS | Joglar & Architects | 422 Corporation | 62 | 62 | 0 | 62 | 0 | 669 | 0 | 669 | 0% | 692 | 100% | 2001-01-18 | 2002-11-17 | 2002-11-17 | 2002-12-11 | 2003-10-02 | 0 | 0 | 0 | 2640000 | -11465 | 2628535 | -0.4343% | 2628535 | 0 | 2628535 | 100% | 11.1613 | 100% | 0 | Project Closed | Final Acceptance
5158 | Aguadilla | La Montaña | Frank Nieves | American Management | URS | Unipro | Caribe Tecno Habitat | 220 | 220 | 0 | 220 | 0 | 895 | 458 | 1353 | 51.17% | 1341 | 100% | 2003-07-28 | 2006-01-07 | 2007-04-10 | 2007-03-30 | 2007-03-30 | 0 | CFP | 0 | 16148000 | 1232941.34 | 17380941.34 | 7.635% | 16890921 | 0 | 16890921 | 97.18% | 6.0955 | 100% | 0 | Project Closed | Final Acceptance
3035 | Aguas Buenas | Vista Alegre | Rubén Cotto | MJ Consulting | URS Caribe | Carlos E. Betancourt | Constructores Gilmar | 74 | 74 | 0 | 74 | 0 | 912 | 752 | 1664 | 82.46% | 1645 | 100% | 2005-06-06 | 2007-12-04 | 2009-12-25 | 2009-12-07 | 2010-09-10 | 0 | Tax Credit 908-2008 | 0 | 6690000 | 2657915 | 9347915 | 39.73% | 8143277.42 | 0 | 8143277.42 | 87.11% | 22.2297 | 100% | 0 | Project Closed | Final Acceptance
3082 | Arecibo | Ramón Marín Solá (Fase II) | Arturo Acevedo | MAS Corporation | CMS | Andrés Hernández | Nogama Construction | 96 | 96 | 0 | 96 | 0 | 612 | 44 | 656 | 7.19% | 626 | 100% | 2000-05-15 | 2002-01-16 | 2002-03-01 | 2002-01-31 | 2002-03-15 | 0 | 0 | 0 | 7837000 | 0 | 7837000 | 0% | 7837000 | 0 | 7837000 | 100% | 6.5208 | 100% | 0 | Project Closed | Final Acceptance
3097 | Arecibo | Trina Padilla de Sanz | Frank Nieves | Cost Control Company, Inc. | ISS Corp | Ray Engineers PSC | Nogama Construction | 240 | 240 | 0 | 240 | 0 | 1278 | 97 | 1375 | 7.59% | 1464 | 100% | 2006-01-09 | 2009-07-09 | 2009-10-14 | 2010-01-12 | 2010-08-16 | 0 | Tax Credit | 0 | 23814529 | 1556413.89 | 25370942.89 | 6.536% | 25198434.68 | 0 | 25198434.68 | 99.32% | 6.1 | 100% | 0 | Project Closed | Final Acceptance
5127 | Arecibo | La Meseta | Pedro Vega | Cost Control Company, Inc. | URS Caribe | Enrique Ruiz & Asoc. | Venegas Construction | 300 | 300 | 0 | 300 | 0 | 1098 | 871 | 1969 | 79.33% | 1947 | 100% | 2005-05-31 | 2008-06-01 | 2010-10-20 | 2010-09-29 | 2011-01-24 | 0 | Tax Credit | 0 | 24161000 | 1903823.57 | 26064823.57 | 7.88% | 26064823.57 | 0 | 26064823.57 | 100% | 6.49 | 100% | 0 | Project Closed. | Final Acceptance
3099 | Arecibo | Antonio Márquez Arbona | Frank Nieves | American Management | Klassik Builders | Enrique Ruiz & Asoc. | Karimar Construction, Inc. | 104 | 104 | 0 | 104 | 0 | 730 | 183 | 913 | 25.07% | 912 | 100% | 2010-03-25 | 2012-03-23 | 2012-09-22 | 2012-09-22 | 2013-04-01 | 0 | ARRA/CFP | 0 | 9085636 | 263361.39 | 9348997.39 | 2.899% | 9223663.18 | 0 | 9223663.18 | 98.66% | 8.7692 | 100% | 0 | In Closing Process. | Final Acceptance
3021 | Arroyo | Isidro Cora | Rubén Cotto | MJ Consulting | MD | GMG Eng. Consultants | Venegas Construction | 150 | 150 | 0 | 150 | 0 | 1095 | 302 | 1397 | 27.58% | 1396 | 100% | 1999-09-27 | 2002-09-25 | 2003-07-24 | 2003-07-24 | 2004-09-30 | 0 | 0 | 0 | 10247000 | 437000 | 10684000 | 4.265% | 10654500 | 0 | 10654500 | 99.72% | 9.3067 | 100% | 0 | The close out documents are under correction process by the Program Manager and General Contractor. | Final Acceptance
3036 | Barceloneta | Antonio Dávila Freytes | José Negrón | MAS Corporation | LMC | Andrés Hernández & Asoc. | Caribe Tecno | 100 | 100 | 0 | 100 | 0 | 904 | 413 | 1317 | 45.69% | 1316 | 100% | 1999-10-15 | 2002-04-05 | 2003-05-23 | 2003-05-23 | 2003-06-30 | 0 | 0 | 0 | 6970000 | 1305876.67 | 8275876.67 | 18.74% | 8275877 | 0 | 8275877 | 100% | 13.16 | 100% | 0 | Project Closed | Final Acceptance
3037 | Barranquitas | Villa Universitaria | Jorge Mercado | MJ Consulting | AVP | GMG Eng. Consultants | Royal & Sun Alliance | 100 | 100 | 0 | 100 | 0 | 540 | 913 | 1453 | 169.1% | 1678 | 100% | 1997-11-25 | 1999-05-18 | 2001-11-16 | 2002-06-30 | 2002-11-12 | 0 | 0 | 0 | 5299000 | 804839 | 6103839 | 15.19% | 6103839 | 0 | 6103839 | 100% | 16.78 | 100% | 0 | Project Closed | Final Acceptance
5093 | Bayamón | Brisas de Bayamón | Arturo Acevedo | Cost Control Company, Inc. | URS Caribe | Edison Avilés Deliz | Omega Engineering | 300 | 300 | 0 | 300 | 0 | 1400 | 1372 | 2772 | 98% | 2518 | 100% | 2002-01-09 | 2005-11-08 | 2009-08-11 | 2008-12-01 | 2010-03-22 | 0 | Tax Credit | 0 | 23965851 | 5030471 | 28996322 | 20.99% | 27007484 | 0 | 27007484 | 93.14% | 8.3933 | 100% | 0 | Project Closed | Final Acceptance
5151 | Bayamón | Sierra Linda | Arturo Acevedo | Martinal Property | URS | Gautier & De Torres | JR Builders | 200 | 200 | 0 | 200 | 0 | 1015 | 1071 | 2086 | 105.5% | 2136 | 100% | 2002-04-15 | 2005-01-23 | 2007-12-30 | 2008-02-19 | 2008-08-08 | 0 | CFP-02 | 0 | 13395440 | 1036113 | 14431553 | 7.735% | 14344606 | 0 | 14344606 | 99.4% | 10.68 | 100% | 0 | Project Closed | Final Acceptance
5096 | Bayamón | La Alhambra | Luis Rodríguez | Cost Control Company, Inc. | LMC | Jorge del Río Arquitectos | Del Valle Group | 96 | 96 | 0 | 96 | 0 | 730 | 236 | 966 | 32.33% | 793 | 100% | 2009-07-28 | 2011-07-27 | 2012-03-19 | 2011-09-29 | 2012-05-17 | 0 | ARRA-CFP | 0 | 9555000 | 752914.59 | 10307914.59 | 7.88% | 10307914.59 | 0 | 10307914.59 | 100% | 8.2604 | 100% | 0 | Project Closed | Final Acceptance
5094 | Bayamón | Las Gardenias | Jorge Mercado | Housing Promoters | AVP/Prann | Gautier & Benítez | Del Valle Group | 164 | 164 | 0 | 164 | 0 | 671 | 302 | 973 | 45.01% | 1033 | 100% | 1997-05-29 | 1999-03-30 | 2000-01-26 | 2000-03-27 | 2000-06-08 | 0 | 0 | 0 | 7117000 | 152286.5 | 7269286.5 | 2.14% | 7234564.4 | 0 | 7234564.4 | 99.52% | 6.2988 | 100% | 0 | Project Closed | Final Acceptance
5138 | Caguas | Villa del Rey (With Take Over Agreement) | Fco. Palacios | MJ Consulting | AVP / Vivonis & Villegas | Guillermety, Ortiz & Asoc. | American Intl. | 100 | 100 | 0 | 100 | 0 | 620 | 165 | 785 | 26.61% | 903 | 100% | 2000-08-04 | 2002-04-15 | 2002-09-27 | 2003-01-24 | 2003-01-24 | 0 | 0 | 0 | 2110081 | 192030 | 2302111 | 9.101% | 2302111 | 0 | 2302111 | 100% | 9.03 | 100% | 0 | Project Closed | Final Acceptance
5066 | Caguas | Turabo Heights | Luis Rodríguez | MJ Consulting | LMC | Andrés Hernández & Asoc. | Del Valle Group | 254 | 254 | 0 | 254 | 0 | 1300 | 471 | 1771 | 36.23% | 1641 | 100% | 2006-01-16 | 2009-08-07 | 2010-11-21 | 2010-07-15 | 2010-09-30 | 0 | Tax Credit | 0 | 25534940 | 2776195 | 28311135 | 10.87% | 28311135.04 | 0 | 28311135.04 | 100% | 6.4606 | 100% | 0 | Project Closed | Final Acceptance
3038 | Camuy | M. Román Adames | Arturo Acevedo | NFC | CMS | Gutierez & Gutierrez | Pintores Metropolitanos | 64 | 64 | 0 | 64 | 0 | 396 | 491 | 887 | 124% | 1101 | 100% | 1997-05-19 | 1998-06-18 | 1999-10-22 | 2000-05-24 | 2001-03-19 | 0 | 0 | 0 | 3600000 | 403566 | 4003566 | 11.21% | 4003566 | 0 | 4003566 | 100% | 17.2031 | 100% | 0 | Project Closed | Final Acceptance
3053 | Canóvanas | Jesús T. Piñero | Katherine Vázquez | Peregrine Group Inc. | Klassik Builders | Ray Engineers, PSC | LPC&D | 124 | 124 | 0 | 124 | 0 | 913 | 237 | 1150 | 25.96% | 1149 | 100% | 2009-07-15 | 2012-01-13 | 2012-09-06 | 2012-09-06 | 2013-06-30 | 0 | ARRA/CFP | 0 | 16575250 | 2355453 | 18930703 | 14.21% | 18827830.65 | 0 | 18827830.65 | 99.46% | 9.2661 | 100% | 0 | The following items are pending: comments from payroll non-compliance issues, to submit certification # 38. | Final Acceptance
5082 | Carolina | Alturas de Country Club | José González | PROMMA | URS | Jorge del Rio | North Construction | 72 | 72 | 0 | 72 | 0 | 548 | 373 | 921 | 68.07% | 893 | 100% | 2004-09-27 | 2006-03-28 | 2007-04-05 | 2007-03-09 | 2009-04-24 | 0 | CFP | 0 | 5977756.15 | 1066756.51 | 7044512.66 | 17.85% | 7044512.67 | 0 | 7044512.67 | 100% | 12.4028 | 100% | 0 | Project Closed | Final Acceptance
5057 | Carolina | Los Mirtos | José González | Cost Control | CCC-JV | Hernández - Bauzá | Del Valle group | 144 | 144 | 0 | 144 | 0 | 545 | 121 | 666 | 22.2% | 690 | 100% | 2010-11-08 | 2012-05-05 | 2012-09-03 | 2012-09-28 | 2013-07-17 | 0 | Tax Credit | 0 | 14841000 | 272983 | 15113983 | 1.839% | 14923649 | 0 | 14923649 | 98.74% | 4.7917 | 100% | 0 | Project Closed | Final Acceptance
5076 | Carolina | Catañito Gardens | Luis Rodríguez | Inn Capital Housing Division Joint Venture | MD | URS Caribe | RBC Construction | 124 | 124 | 0 | 124 | 0 | 730 | 937 | 1667 | 128.4% | 0 | 100% | 2006-02-08 | 2008-02-07 | 2010-09-01 | 2006-02-08 | 2011-03-28 | 0 | Tax Credit 908-2008 | 0 | 13938100 | 819027.62 | 14757127.62 | 5.876% | 14757127.62 | 0 | 14757127.62 | 100% | 0 | 100% | 0 | Project Closed | Final Acceptance
5102 | Carolina | El Coral | José A. González | Cost Control Company, Inc. | URS Caribe | Francinetti Arquitectos | Orion Contractors | 100 | 100 | 0 | 100 | 0 | 913 | 1268 | 2181 | 138.9% | 2180 | 100% | 2006-01-09 | 2008-07-09 | 2011-12-29 | 2011-12-29 | 2012-06-29 | 0 | Tax Credit | 0 | 9718830 | 1196730.19 | 10915560.19 | 12.31% | 10915560.19 | 0 | 10915560.19 | 100% | 21.8 | 100% | 0 | Project Closed | Final Acceptance
5101 | Carolina | La Esmeralda | Luis Rodríguez | Inn Capital Housing Division Joint Venture | BMA | Carlos E. Betancourt | Construction Zone Corp. | 84 | 84 | 0 | 84 | 0 | 549 | 65 | 614 | 11.84% | 612 | 100% | 2008-12-22 | 2010-06-23 | 2010-08-27 | 2010-08-26 | 2010-12-10 | 0 | Tax Credit | 0 | 4462898 | 32305.97 | 4495203.97 | 0.7239% | 4495203.77 | 0 | 4495203.77 | 100% | 7.2857 | 100% | 0 | Project Closed | Final Acceptance
5075 | Carolina | Lagos de Blasina | José A. González | Cost Control Company, Inc. | CMS | Guillermety, Ortiz & Asoc. (DG3A Design Group, PSC is actually supervising the works) | Mejia Construction | 240 | 240 | 0 | 240 | 0 | 800 | 289 | 1089 | 36.12% | 1077 | 100% | 2009-06-08 | 2011-08-16 | 2012-05-31 | 2012-05-20 | 2012-09-20 | 0 | Tax Credit | 0 | 15411000 | 809595.16 | 16220595.16 | 5.253% | 16220595.16 | 0 | 16220595.16 | 100% | 4.4875 | 100% | 0 | Project Closed | Final Acceptance
5212 | Carolina | Roberto Clemente | Luz Acevedo | SEG | CMS | Jorge del Río | North Connstruction | 126 | 126 | 0 | 126 | 0 | 730 | 242 | 972 | 33.15% | 1038 | 100% | 2004-08-09 | 2006-08-08 | 2007-04-07 | 2007-06-13 | 2008-02-22 | 0 | 0 | 0 | 11135000 | 586931 | 11721931 | 5.271% | 11610417 | 0 | 11610417 | 99.05% | 8.2381 | 100% | 0 | Project Closed | Final Acceptance
3102 | Cataño | Juana Matos I (Fase I) | Luz Acevedo | A & M | AVP / Erwin Rodriguez | Roca & Associates | Quintero Const. | 212 | 212 | 0 | 212 | 0 | 892 | 744 | 1636 | 83.41% | 1628 | 100% | 1997-05-29 | 1999-11-06 | 2001-11-19 | 2001-11-12 | 2002-07-22 | 0 | 0 | 0 | 11640000 | 424857 | 12064857 | 3.65% | 11679790.2 | 0 | 11679790.2 | 96.81% | 7.6792 | 100% | 0 | Project Closed | Final Acceptance
3102 | Cataño | Juana Matos I (Fase II) | Pedro Vega | A & M | BMA | Roca & Associates | Rodríguez & del Valle | 188 | 188 | 0 | 188 | 0 | 1150 | 141 | 1291 | 12.26% | 1179 | 100% | 2002-09-30 | 2005-11-22 | 2006-04-12 | 2005-12-22 | 2006-01-12 | 0 | 0 | 0 | 14243000 | 831198 | 15074198 | 5.836% | 15074198 | 0 | 15074198 | 100% | 6.2713 | 100% | 0 | Project Closed | Final Acceptance
5037 | Cataño | Jardines de Cataño | Pedro Vega | Martinal Property | CMS | Interplan | Francisco Levy Hijo Inc. | 180 | 180 | 0 | 180 | 0 | 810 | 369 | 1179 | 45.56% | 1175 | 100% | 2004-03-22 | 2006-06-09 | 2007-06-13 | 2007-06-10 | 2007-06-14 | 0 | CFP | 0 | 14181600 | 1145235.46 | 15326835.46 | 8.076% | 15326835.44 | 0 | 15326835.44 | 100% | 6.5278 | 100% | 0 | Project Closed | Final Acceptance
3083 | Cayey | Luis Muñoz Morales | Luz Acevedo | MJ Consulting | AVP | Istra Hernández | I Melendez | 280 | 280 | 0 | 280 | 0 | 913 | 416 | 1329 | 45.56% | 1342 | 100% | 1997-08-01 | 2000-01-30 | 2001-03-21 | 2001-04-04 | 2001-09-19 | 0 | 0 | 0 | 12895800 | 452279 | 13348079 | 3.507% | 13348079 | 0 | 13348079 | 100% | 4.7929 | 100% | 0 | Project Close | Final Acceptance
5127 | Cayey | Jardines de Montellanos | Rubén Cotto | Cost Control | CCC-JV | Hernández - Bauzá | Constructora I. Meléndez | 130 | 130 | 0 | 130 | 0 | 836 | 307 | 1143 | 36.72% | 1142 | 100% | 2009-09-30 | 2012-01-13 | 2012-11-15 | 2012-11-15 | 0 | 0 | Tax Credit | 0 | 17226575.94 | 2771225.7 | 19997801.64 | 16.09% | 19987858.29 | 0 | 19987858.29 | 99.95% | 8.7846 | 100% | 0 | Project Closed | Final Acceptance
5157 | Cayey | Brisas de Cayey | Rubén Cotto | MJ Consulting | MD | Ray Engineers PSC | Three O. Construction | 210 | 210 | 0 | 210 | 0 | 1491 | 1200 | 2691 | 80.48% | 1887 | 100% | 2005-01-12 | 2009-02-10 | 2012-05-25 | 2010-03-14 | 2010-04-06 | 0 | Tax Credit | 0 | 24696653 | 5611698 | 30308351 | 22.72% | 30308351 | 0 | 30308351 | 100% | 8.9857 | 100% | 0 | Project Closed | Final Acceptance
3040 | Ciales | Fernando Sierra Berdecía | José Negrón | MAS Corporation | LMC | Luis Flores & Asociados | Constructores Gilmar | 100 | 100 | 0 | 100 | 0 | 780 | 165 | 945 | 21.15% | 983 | 100% | 2001-08-21 | 2003-10-09 | 2004-03-22 | 2004-04-30 | 2006-05-16 | 0 | 0 | 0 | 9285527 | 414901 | 9700428 | 4.468% | 9700428 | 0 | 9700428 | 100% | 9.83 | 100% | 0 | Project Closed | Final Acceptance
3041 | Cidra | Práxedes Santiago | Rubén Cotto | MJ Consulting | URS | Carlos E. Betancourt | DGM Engineering | 124 | 124 | 0 | 124 | 0 | 912 | 901 | 1813 | 98.79% | 2235 | 100% | 2005-04-28 | 2007-10-26 | 2010-04-14 | 2011-06-11 | 2012-03-09 | 0 | Tax Credit | 0 | 11616773 | 3604885 | 15221658 | 31.03% | 14100168 | 0 | 14100168 | 92.63% | 18.0242 | 100% | 0 | Project Closed | Final Acceptance
3043 | Dorado | El Dorado | Frank Nieves | Cost Control Company, Inc. | BMA | Guillermety, Ortiz & Asoc. | Torres & Colón, Inc | 37 | 37 | 0 | 37 | 0 | 430 | 180 | 610 | 41.86% | 666 | 100% | 2007-06-04 | 2008-08-06 | 2009-02-02 | 2009-03-31 | 2009-04-14 | 0 | Tax Credit | 0 | 3991977 | 753900 | 4745877 | 18.89% | 4745877 | 0 | 4745877 | 100% | 18 | 100% | 0 | Project Closed | Final Acceptance
3095 | Fajardo | Pedro Rosario Nieves | José M. Paris Escalera | Inn Capital Housing Division Joint Venture | CMS | Carlos E. Betancourt | Nogama Construction | 168 | 168 | 0 | 168 | 0 | 915 | 27.5 | 942.5 | 3.005% | 904 | 100% | 2008-12-22 | 2011-06-24 | 2011-07-21 12:00 | 2011-06-14 | 2011-09-06 | 0 | Tax Credit | 0 | 16474000 | -148386.07 | 16325613.93 | -0.9007% | 16325613.93 | 0 | 16325613.93 | 100% | 5.381 | 100% | 0 | Project Closed | Final Acceptance
5021 | Fajardo | Puerto Real | Germán Acevedo | A & M | URS | René Vélez Marichal | Quality Const. | 100 | 100 | 0 | 100 | 0 | 945 | 282 | 1227 | 29.84% | 1124 | 100% | 2001-01-22 | 2003-08-24 | 2004-06-01 | 2004-02-20 | 2004-04-20 | 0 | 0 | 0 | 8220000 | 910990 | 9130990 | 11.08% | 9130990 | 0 | 9130990 | 100% | 11.24 | 100% | 0 | Project Closed | Final Acceptance
5204 | Fajardo | Valle Puerto Real | Germán Acevedo | A & M | URS | Enrique Ruiz & Assoc. | Quality Const. | 75 | 75 | 0 | 75 | 0 | 945 | 181 | 1126 | 19.15% | 1129 | 100% | 2001-01-02 | 2003-08-04 | 2004-02-01 | 2004-02-05 | 2004-05-14 | 0 | 0 | 0 | 6316000 | 725553 | 7041553 | 11.49% | 7041553 | 0 | 7041553 | 100% | 15.0533 | 100% | 0 | Project Closed | Final Acceptance
5176 | Fajardo | Santiago Veve Calzada | Robert H. Cole | A & M | BMA | Ramón W. Costacamps | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 730 | 214 | 944 | 29.32% | 906 | 100% | 2004-06-21 | 2006-06-20 | 2007-01-20 | 2006-12-14 | 2007-01-18 | 0 | 0 | 0 | 8559000 | 558385.32 | 9117385.32 | 6.524% | 9117385.32 | 0 | 9117385.32 | 100% | 9.06 | 100% | 0 | Project Closed | Final Acceptance
5183 | Guánica | Jardines de Guánica | Noefebdo Ramírez | JA Machuca | CCC-JV | Donato Design Development | RAMA Construction | 70 | 70 | 0 | 70 | 0 | 732 | 89 | 821 | 12.16% | 794 | 100% | 2009-11-23 | 2011-11-24 | 2012-02-21 | 2012-01-26 | 2012-01-31 | 0 | ARRA/CFP | 0 | 5499000 | 487497.62 | 5986497.62 | 8.865% | 5986498 | 0 | 5986498 | 100% | 11.3429 | 100% | 0 | Project Closed | Final Acceptance
3084 | Guánica | Luis Muñoz Rivera | Noefebdo Ramírez | Cost Control Company, Inc. | CCC-JV | Behar & Ybarra Associates, PSC | F & R Construction Group, Inc. | 124 | 124 | 0 | 124 | 0 | 485 | 423 | 908 | 87.22% | 970 | 100% | 2009-12-14 | 2011-04-12 | 2012-06-08 | 2012-08-10 | 2013-04-18 | 0 | Tax Credit | 0 | 9009000 | 589263.71 | 9598263.71 | 6.541% | 9590758.22 | 0 | 9590758.22 | 99.92% | 7.8226 | 100% | 0 | Project Closed | Final Acceptance
3085 | Guayama | Luis Palés Matos | Rubén Cotto | MJ Consulting | MD (Grupo C) | Guillermety, Ortiz & Asoc. | Héctor M. Valera Inc. | 298 | 298 | 0 | 298 | 0 | 1130 | 0 | 1130 | 0% | 1375 | 100% | 2002-03-25 | 2005-04-27 | 2005-04-27 | 2005-12-29 | 2006-01-03 | 0 | 0 | 0 | 22466000 | 0 | 22466000 | 0% | 22466000 | 0 | 22466000 | 100% | 4.6141 | 100% | 0 | Project Closed | Final Acceptance
5048 | Guayama | San Antonio Carioca | Jorge Mercado | MJ Consulting | MD (Grupo C) | DDHK | Constructora I. Melendez | 200 | 200 | 0 | 200 | 0 | 900 | 568 | 1468 | 63.11% | 1537 | 100% | 2004-03-15 | 2006-08-31 | 2008-03-21 | 2008-05-30 | 2008-07-30 | 0 | Tax Credit | 0 | 18456662 | 1765148 | 20221810 | 9.564% | 20221810 | 0 | 20221810 | 100% | 7.685 | 100% | 0 | Project Closed | Final Acceptance
5131 | Humacao | Jardines de Oriente | José A. González | Cost Control | CCC-JV | GMG Engineering Conslutants PSC | Ossam Construction | 88 | 88 | 0 | 88 | 0 | 365 | 242 | 607 | 66.3% | 937 | 100% | 2010-05-31 | 2011-05-30 | 2012-01-27 | 2012-12-23 | 2012-07-20 | 0 | Tax Credit | 0 | 5939925 | 394882.55 | 6334807.55 | 6.648% | 6334807.55 | 0 | 6334807.55 | 100% | 10.6477 | 100% | 0 | Project Closed | Final Acceptance
5020 | Humacao | Pedro J. Palou | Fco. Palacios | MJ Consulting | URS | R & del Valle | R & del Valle | 150 | 150 | 0 | 150 | 0 | 1095 | 180 | 1275 | 16.44% | 1145 | 100% | 1999-09-27 | 2002-09-25 | 2003-03-24 | 2002-11-15 | 2002-12-20 | 0 | 0 | 0 | 10968000 | 86049 | 11054049 | 0.7845% | 11054049 | 0 | 11054049 | 100% | 7.6333 | 100% | 0 | Project closed. | Final Acceptance
3094 | Humacao | Padre Rivera (Fase I) | Germán Acevedo | MJ Consulting | BMA | Yañez, Mayol & Asoc. | J R Builders | 128 | 128 | 0 | 128 | 0 | 840 | 731 | 1571 | 87.02% | 1548 | 100% | 1997-10-20 | 2000-02-06 | 2002-02-06 | 2002-01-15 | 2002-02-01 | 0 | 0 | 0 | 6625000 | 386337.2 | 7011337.2 | 5.832% | 7011337 | 0 | 7011337 | 100% | 12.0938 | 100% | 0 | Project Closed | Final Acceptance
3094 | Humacao | Padre Rivera (Fase II) | Jorge Mercado | MJ Consulting | BMA | Yañez & Mayol | Jafer Construction | 132 | 132 | 0 | 132 | 0 | 790 | 299 | 1089 | 37.85% | 861 | 100% | 2004-11-10 | 2007-01-08 | 2007-11-03 | 2007-03-21 | 2008-03-12 | 0 | 0 | 0 | 10199820 | 1471265 | 11671085 | 14.42% | 11237717 | 0 | 11237717 | 96.29% | 6.5227 | 100% | 0 | Project Closed | Final Acceptance
3048 | Jayuya | La Montaña | Pedro Vega | MAS Corporation | URS | OPQ-Pablo Quiñonez | Orama Const. | 100 | 100 | 0 | 100 | 0 | 780 | 128 | 908 | 16.41% | 1026 | 100% | 2000-10-23 | 2002-12-11 | 2003-04-18 | 2003-08-15 | 2004-04-26 | 0 | 0 | 0 | 8790000 | 208826 | 8998826 | 2.376% | 8998826 | 0 | 8998826 | 100% | 10.26 | 100% | 0 | Project Closed | Final Acceptance
5064 | Juncos | Colinas de Magnolia | Iván Blanco | MJ Consulting | BMA | Edison Avilés Deliz | Quality Construction | 148 | 148 | 0 | 148 | 0 | 840 | 614 | 1454 | 73.1% | 1201 | 100% | 2004-11-08 | 2007-02-25 | 2008-10-31 | 2008-02-22 | 2008-04-04 | 0 | CFP | 0 | 13860000 | 854562 | 14714562 | 6.166% | 14438155 | 0 | 14438155 | 98.12% | 8.1149 | 100% | 0 | Project Closed | Final Acceptance
3093 | Juncos | Narciso Varona I | Rubén Cotto | MJ Consulting | ISS | DG3A | Torres & Colón, Inc | 88 | 88 | 0 | 88 | 0 | 600 | 199 | 799 | 33.17% | 798 | 100% | 2009-05-29 | 2011-01-18 | 2011-08-05 | 2011-08-05 | 0 | 0 | ARRA/CFP | 0 | 9879114 | 196304 | 10075418 | 1.987% | 10058405.83 | 0 | 10058405.83 | 99.83% | 9.0682 | 100% | 0 | Project Closed | Final Acceptance
5226 | Las Marías | Jardines de las Marías | Arturo Acevedo | NFC | CMS | José L. Irizarry & Assoc. | Lebrón & Assoc. | 55 | 55 | 0 | 55 | 0 | 730 | 32 | 762 | 4.384% | 766 | 100% | 2001-02-27 | 2003-02-26 | 2003-03-30 | 2003-04-04 | 2003-10-03 | 0 | 0 | 0 | 4156000 | 71269 | 4227269 | 1.715% | 4227269 | 0 | 4227269 | 100% | 13.9273 | 100% | 0 | Project Closed | Final Acceptance
5090 | Las Piedras | Jardines de Judely | Iván Blanco | MJ Consulting | URS | René Acosta Ingenieros | Gilmar Roofing & Painting | 32 | 32 | 0 | 32 | 0 | 365 | 118 | 483 | 32.33% | 555 | 100% | 2005-04-04 | 2006-04-03 | 2006-07-30 | 2006-10-11 | 2006-11-02 | 0 | Tax Credit | 0 | 3481720 | 109596.22 | 3591316.22 | 3.148% | 3573356 | 0 | 3573356 | 99.5% | 17.3438 | 100% | 0 | Project Closed | Final Acceptance
5132 | Loíza | Yuquiyú | Luz Acevedo | A & M | BMA | Roca, González Villamil | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 945 | 60 | 1005 | 6.349% | 754 | 100% | 2001-01-22 | 2003-08-24 | 2003-10-23 | 2003-02-15 | 2003-03-21 | 0 | 0 | 0 | 8644000 | 611853 | 9255853 | 7.078% | 9255853.0708 | 0 | 9255853.0708 | 100% | 7.54 | 100% | 0 | Project Closed | Final Acceptance
5186 | Luquillo | Yuquiyú II | Luz Acevedo | Inn Capital Housing Division Joint Venture | BMA | Enrique Ruiz & Asoc. | Unique Builders | 70 | 70 | 0 | 70 | 0 | 730 | 299 | 1029 | 40.96% | 1092 | 100% | 2006-02-15 | 2008-02-14 | 2008-12-09 | 2009-02-11 | 2009-06-09 | 0 | Tax Credit | 0 | 6964727 | 157419 | 7122146 | 2.26% | 6424134.91 | 0 | 6424134.91 | 90.2% | 15.6 | 100% | 0 | Project Closed | Final Acceptance
3056 | Maricao | Juan Ferrer | Noefebdo Ramírez | J. A. Machuca | NFC | René Batista & Assoc. | Comas & Comas | 30 | 30 | 0 | 30 | 0 | 420 | 251 | 671 | 59.76% | 610 | 100% | 2000-08-02 | 2001-09-25 | 2002-06-03 | 2002-04-04 | 2002-04-30 | 0 | 0 | 0 | 2210000 | 178940 | 2388940 | 8.097% | 2388940 | 0 | 2388940 | 100% | 20.3333 | 100% | 0 | Project Closed | Final Acceptance
3057 | Maunabo | Carmen Vda. Martorell (take over agreement) | Rubén Cotto | AVP | AVP | Rene Batista | American Intl. | 50 | 50 | 0 | 50 | 0 | 375 | 327 | 702 | 87.2% | 703 | 100% | 2000-08-18 | 2001-08-27 | 2002-07-20 | 2002-07-22 | 2005-06-02 | 0 | 0 | 0 | 1308221 | 116706 | 1424927 | 8.921% | 1424927 | 0 | 1424927 | 100% | 14.06 | 100% | 0 | Project Closed | Final Acceptance
5126 | Maunabo | Villa Navarro | Rubén Cotto | MJ Consulting | MD | José L. Irizarry & Assoc. | Inversiones OLPERI | 101 | 101 | 0 | 101 | 0 | 907 | 335 | 1242 | 36.93% | 1241 | 100% | 2000-01-24 | 2002-07-18 | 2003-06-18 | 2003-06-18 | 2003-06-18 | 0 | 0 | 0 | 6745000 | 238239 | 6983239 | 3.532% | 6983239 | 0 | 6983239 | 100% | 12.2871 | 100% | 0 | Project Closed | Final Acceptance
5012 | Mayagüez | Ext. Sábalos Gardens | Noefebdo Ramírez | Inn Capital Housing Division Joint Venture | URS Caribe / AVP | Joint Venture | Venegas Construction | 300 | 300 | 0 | 300 | 0 | 1281 | 690 | 1971 | 53.86% | 1963 | 100% | 2005-05-16 | 2008-11-16 | 2010-10-07 | 2010-09-30 | 2011-04-29 | 0 | Tax Credit 908-2008 | 0 | 28259000 | 14189.7 | 28273189.7 | 0.05021% | 29677970 | 0 | 29677970 | 105% | 6.5433 | 100% | 0 | Project Closed | Final Acceptance
4004 | Mayagüez | Sábalos Gdns. | Arturo Acevedo | Zeta | CMS | Héctor Rodríguez Amezquita | Caribe Tecno | 140 | 140 | 0 | 140 | 0 | 881 | 24 | 905 | 2.724% | 900 | 100% | 1999-11-15 | 2002-04-13 | 2002-05-07 | 2002-05-03 | 2002-11-06 | 0 | 0 | 0 | 11790000 | -294361.74 | 11495638.26 | -2.497% | 11495638 | 0 | 11495638 | 100% | 6.4286 | 100% | 0 | Project Closed | Final Acceptance
4006 | Mayagüez | Cuesta las Piedras | Arturo Acevedo | Zeta | CMS | García Cabot | RC Enginering | 142 | 142 | 0 | 142 | 0 | 1093 | 0 | 1093 | 0% | 907 | 100% | 2000-02-10 | 2003-02-06 | 2003-02-06 | 2002-08-05 | 2002-11-21 | 0 | 0 | 0 | 10673000 | 158657 | 10831657 | 1.487% | 10831657 | 0 | 10831657 | 100% | 6.3873 | 100% | 0 | Se aprobó el "close out". Contratista no cobró el total del contrato debido a ajustes deductivos recomendados por el "Program Manager"C.M. Services. | Final Acceptance
4008 | Mayagüez | Yagüez | Arturo Acevedo | ZETA | CMS | GDA Ing. Consultores | NLL Construction | 200 | 200 | 0 | 200 | 0 | 1399 | 0 | 1399 | 0% | 1177 | 100% | 2000-05-22 | 2004-03-20 | 2004-03-20 | 2003-08-12 | 2003-10-06 | 0 | 0 | 0 | 16799671 | -872594 | 15927077 | -5.194% | 15927077 | 0 | 15927077 | 100% | 5.885 | 100% | 0 | Project Closed | Final Acceptance
4005 | Mayagüez | Marini Farm | Frank Nieves | Zeta | BMA | CSA Architects | Empresas Toledo | 100 | 100 | 0 | 100 | 0 | 218 | 50 | 268 | 22.94% | 247 | 100% | 2004-05-12 | 2004-12-15 | 2005-02-03 | 2005-01-14 | 2005-09-07 | 0 | 0 | 0 | 845900 | 30508 | 876408 | 3.607% | 876408 | 0 | 876408 | 100% | 2.47 | 100% | 0 | Project Closed | Final Acceptance
5005 | Mayagüez | Mar y Sol | Noefebdo Ramírez | Zeta | CMS | Arq. Amadeo Pino | RC Enginering | 124 | 124 | 0 | 124 | 0 | 1055 | 14 | 1069 | 1.327% | 1068 | 100% | 2001-01-22 | 2003-12-12 | 2003-12-26 | 2003-12-26 | 2004-05-26 | 0 | 0 | 0 | 10513000 | 269417 | 10782417 | 2.563% | 10782417 | 0 | 10782417 | 100% | 8.6129 | 100% | 0 | Project Closed | Final Acceptance
5133 | Naguabo | Villas del Río | Félix Ortiz | MJ Consulting | MD | N/A | DGM Engineering | 100 | 100 | 0 | 100 | 0 | 730 | 906 | 1636 | 124.1% | 1640 | 100% | 2006-02-15 | 2008-02-14 | 2010-08-08 | 2010-08-13 | 2011-06-27 | 0 | Tax Credit | 0 | 11008930 | 1560851 | 12569781 | 14.18% | 12120952 | 0 | 12120952 | 96.43% | 16.4 | 100% | 0 | Project Closed | Final Acceptance
3063 | Peñuela | Los Flamboyanes | Noefebdo Ramírez | J.A. Machuca | MD | Fuertes, La Font & Asoc. | St. Paul Surety | 24 | 24 | 0 | 24 | 0 | 345 | 502 | 847 | 145.5% | 845 | 100% | 2003-04-15 | 2004-03-24 | 2005-08-08 | 2005-08-07 | 2005-09-26 | 0 | 0 | 0 | 1235996 | 568973 | 1804969 | 46.03% | 1804969 | 0 | 1804969 | 100% | 35.2083 | 100% | 0 | Project Closed | Final Acceptance
1014 | Ponce | Aristides Chavier | Noefebdo Ramírez | MJ Consulting | CCC Joint Venture | Unipro | Del Valle Group | 480 | 480 | 0 | 480 | 0 | 1464 | 552 | 2016 | 37.7% | 2003 | 100% | 2005-08-01 | 2009-08-03 | 2011-02-06 | 2011-01-25 | 2011-08-16 | 0 | Tax Credit 908-2008 | 0 | 43792000 | 2045988.7 | 45837988.7 | 4.672% | 45837989 | 0 | 45837989 | 100% | 4.1729 | 100% | 0 | Project Closed | Final Acceptance
5088 | Ponce | Lirios del Sur | Arturo Acevedo | J.A. Machuca | CMS | CSA Architects | Omega Engineering | 238 | 238 | 0 | 238 | 0 | 730 | 340 | 1070 | 46.58% | 1083 | 100% | 2003-02-12 | 2005-02-10 | 2006-01-16 | 2006-01-30 | 2006-04-12 | 0 | 0 | 0 | 18140000 | 570661 | 18710661 | 3.146% | 18710661 | 0 | 18710661 | 100% | 4.5504 | 100% | 0 | Project Closed | Final Acceptance
1001 | Ponce | Ponce de León ( Take Over Agreement) Fase I | José González | J. A. Machuca | MD | Interplan | American Intl. | 168 | 168 | 0 | 168 | 0 | 732 | 171 | 903 | 23.36% | 862 | 100% | 2000-08-28 | 2002-08-29 | 2003-02-16 | 2003-01-07 | 2003-01-30 | 0 | 0 | 0 | 10990000 | 512271 | 11502271 | 4.661% | 11447321.14 | 0 | 11447321.14 | 99.52% | 5.131 | 100% | 0 | Project Closed | Final Acceptance
1001 | Ponce | Ponce de León (Fase II) | Noefebdo Ramírez | MJ Consulting | BMA | Interplan | Constructora I. Meléndez | 132 | 132 | 0 | 132 | 0 | 730 | 748 | 1478 | 102.5% | 1442 | 100% | 2005-01-10 | 2007-01-09 | 2009-01-26 | 2008-12-22 | 2009-03-31 | 0 | Tax Credit 908-2008 | 0 | 13680284 | 787807 | 14468091 | 5.759% | 14448030 | 0 | 14448030 | 99.86% | 10.9242 | 100% | 0 | Project Closed | Final Acceptance
1002 | Ponce | Santiago Iglesias (Fase I) | Noefebdo Ramírez | Zeta | CMS | CSA | Ferrovial & Agroman | 160 | 160 | 0 | 160 | 0 | 487 | 505 | 992 | 103.7% | 1791 | 100% | 1997-10-28 | 1999-02-26 | 2000-07-15 | 2002-09-23 | 2002-11-02 | 0 | 0 | 0 | 9445984 | 580020 | 10026004 | 6.14% | 9993950 | 0 | 9993950 | 99.68% | 11.1937 | 100% | 0 | Project Closed | Final Acceptance
1016 | Ponce | Rafael López Nussa | Noefebdo Ramírez | MJ Consulting | BMA | URS Caribe | Del Valle Group | 404 | 404 | 0 | 404 | 0 | 1464 | 369 | 1833 | 25.2% | 1832 | 100% | 2004-10-25 | 2008-10-27 | 2009-10-31 | 2009-10-31 | 2010-06-16 | 0 | Tax Credit 908-2008 | 0 | 38744000 | 738951.13 | 39482951.13 | 1.907% | 39482951.13 | 0 | 39482951.13 | 100% | 4.5347 | 100% | 0 | Project Closed | Final Acceptance
1003 | Ponce | Caribe | Rubén Cotto | J.A. Machuca | MD | Lombardo Pérez | Caribe General Constructors | 116 | 116 | 0 | 116 | 0 | 720 | 358.4 | 1078.4 | 49.78% | 1192 | 100% | 2002-12-01 | 2004-11-19 | 2005-11-12 09:36 | 2006-03-07 | 2006-06-07 | 0 | 0 | 0 | 11468000 | 1539402.23 | 13007402.23 | 13.42% | 13007402 | 0 | 13007402 | 100% | 10.2759 | 100% | 0 | Project Closed | Final Acceptance
5022 | Ponce | La Ceiba | Rubén Cotto | MJ Consulting | BMA | Ray Engineers PSC | Jafer Construction | 300 | 300 | 0 | 300 | 0 | 1281 | 283 | 1564 | 22.09% | 1514 | 100% | 2004-10-11 | 2008-04-13 | 2009-01-21 | 2008-12-03 | 2009-01-30 | 0 | Tax Credit | 0 | 29600820 | 1001464.91 | 30602284.91 | 3.383% | 30602284.91 | 0 | 30602284.91 | 100% | 5.0467 | 100% | 0 | Project Closed | Final Acceptance
5095 | Ponce | Las Terrazas | Rubén Cotto | AVP | ISS Corp. | Méndez, Brunner, Badillo & Associates | Homeca Recycling Center Co., Inc. | 100 | 100 | 0 | 100 | 0 | 365 | 0 | 365 | 0% | 344 | 100% | 2009-07-28 | 2010-07-27 | 2010-07-27 | 2010-07-07 | 2010-07-27 | 0 | Mixed Fund | 0 | 1085000 | 0 | 1085000 | 0% | 918124.83 | 0 | 918124.83 | 84.62% | 3.44 | 100% | 0 | Se entregaron los documentos de cierre, pero aun le falta por cobrar al contratista la Cert # 8 - Parcial (10/Agosto/10) $ 36,954.06 y Cert.#10 - Retenido Final (22/Oct/10) $108,500.00, para un Totasl de $145,454.06, mas reclamacion de intereses por pago tardio. Alega el contratista que le han informado de finanzas que los fondos estan congelados, pero no le han explicado razon. | Final Acceptance
1002 | Ponce | Santiago Iglesias (Fase II) | Noefebdo Ramírez | Individual Management | Klassik Builders | CSA | Jafer Construction | 120 | 120 | 0 | 120 | 0 | 790 | 66 | 856 | 8.354% | 855 | 100% | 2009-06-15 | 2011-08-13 | 2011-10-18 | 2011-10-18 | 2012-01-26 | 0 | ARRA | 0 | 14498820 | 637269.47 | 15136089.47 | 4.395% | 15136089.47 | 0 | 15136089.47 | 100% | 7.125 | 100% | 0 | Project Closed | Final Acceptance
3066 | Río Grande | José H. Ramírez | Luz Acevedo | A & M | AVP / ORAM | Raúl Feliciano & Asoc. | J R Builders | 80 | 80 | 0 | 80 | 0 | 540 | 317 | 857 | 58.7% | 853 | 100% | 2000-03-29 | 2001-09-19 | 2002-08-02 | 2002-07-30 | 2002-11-15 | 0 | 0 | 0 | 3404949 | 226802 | 3631751 | 6.661% | 3631751 | 0 | 3631751 | 100% | 10.6625 | 100% | 0 | Project Closed | Final Acceptance
5145 | San Germán | Manuel F. Rossy | Frank Nieves | Municipio de San Germán | MD | Unipro | Cap Con Inc. | 101 | 101 | 0 | 101 | 0 | 732 | 84 | 816 | 11.48% | 815 | 100% | 2009-06-22 | 2011-06-23 | 2011-09-15 | 2011-09-15 | 2011-12-31 | 0 | CFP/ARRA | 0 | 10316000 | 610969.8 | 10926969.8 | 5.923% | 10908277 | 0 | 10908277 | 99.83% | 8.0693 | 100% | 0 | Project Closed | Final Acceptance
5035 | San Juan | Villa Esperanza | Luz Acevedo | 0 | LMC | Guillermety, Ortiz & Asoc. | Del Valle Group | 300 | 300 | 0 | 300 | 0 | 1130 | 233 | 1363 | 20.62% | 1323 | 100% | 2003-06-18 | 2006-07-21 | 2007-03-11 | 2007-01-31 | 2007-03-30 | 0 | CFP | 0 | 19819000 | 1078350.46 | 20897350.46 | 5.441% | 20897350.46 | 0 | 20897350.46 | 100% | 4.41 | 100% | 0 | Project Closed | Final Acceptance
5077 | San Juan | La Rosa | Jorge Mercado | AUTO ADM. | LMC | García Joglar & Arq. | DGM Engineers | 52 | 52 | 0 | 52 | 0 | 730 | 270 | 1000 | 36.99% | 984 | 100% | 2000-10-02 | 2002-10-01 | 2003-06-28 | 2003-06-13 | 2004-07-19 | 0 | 0 | 0 | 4491000 | 510039 | 5001039 | 11.36% | 5001039 | 0 | 5001039 | 100% | 18.9231 | 100% | 0 | Project Closed | Final Acceptance
5026 | San Juan | Los Lirios | Frank Nieves | A & M | CCC Joint Venture | DG3A | Builders Associates, LLC | 150 | 150 | 0 | 150 | 0 | 854 | 275 | 1129 | 32.2% | 1142 | 100% | 2009-11-12 | 2012-03-14 | 2012-12-14 | 2012-12-28 | 2013-04-19 | 0 | ARRA/CFP | 0 | 15075000 | 523404.07 | 15598404.07 | 3.472% | 15598404.07 | 0 | 15598404.07 | 100% | 7.6133 | 100% | 0 | The Contractor submitted a claim for extended overhead by amount of $989,402.32 | Final Acceptance
5099 | San Juan | El Prado | José González | Cost Control | BMA | Ray Architects | Del Valle Group | 220 | 220 | 0 | 220 | 0 | 1260 | 78 | 1338 | 6.19% | 1202 | 100% | 2000-09-15 | 2004-02-26 | 2004-05-14 | 2003-12-31 | 2004-01-28 | 0 | CFP | 0 | 15715000 | 1037001 | 16752001 | 6.599% | 16752001 | 0 | 16752001 | 100% | 5.4636 | 100% | 0 | Project Closed | Final Acceptance
5192 | San Juan | Antigua Via | José González | MAS Corporation | BMA | Rodríguez & del Valle (Design & Build) | Rodríguez & del Valle | 200 | 200 | 0 | 200 | 0 | 882 | 147 | 1029 | 16.67% | 1338 | 100% | 2000-01-10 | 2002-06-09 | 2002-11-03 | 2003-09-09 | 2003-09-09 | 0 | CFP | 0 | 13397000 | 211211 | 13608211 | 1.577% | 13608211 | 0 | 13608211 | 100% | 6.69 | 100% | 0 | Project Closed | Final Acceptance
2010 | San Juan | Vista Hermosa II (Fase II) | José Negrón | MAS Corporation | AVP / Jorge L. Robert | Guillermety, Ortiz & Asoc. | Urban Builders | 476 | 476 | 0 | 476 | 0 | 1216 | 590 | 1806 | 48.52% | 1442 | 100% | 1997-04-07 | 2000-08-04 | 2002-03-17 | 2001-03-19 | 2001-12-13 | 0 | 0 | 0 | 17900000 | 1037096.5 | 18937096.5 | 5.794% | 18371767.14 | 0 | 18371767.14 | 97.01% | 3.0294 | 100% | 0 | Project Closed | Final Acceptance
5031 | San Juan | Jardines de Campo Rico | José Negrón | Cost Control | CMS | DG3A | North Connstruction | 196 | 196 | 0 | 196 | 0 | 750 | 263 | 1013 | 35.07% | 1012 | 100% | 2006-01-30 | 2008-02-18 | 2008-11-07 | 2008-11-07 | 2008-12-04 | 0 | Tax Credit | 0 | 19483000 | 17564 | 19500564 | 0.09015% | 19500564 | 0 | 19500564 | 100% | 5.1633 | 100% | 0 | Project Closed | Final Acceptance
5143 | San Juan | Monte Park | José Negrón | Housing Promoters | AVP / SAGA | Molinary | Fernández & Gutiérrez | 224 | 224 | 0 | 224 | 0 | 874 | 345 | 1219 | 39.47% | 1517 | 100% | 1996-11-01 | 1999-03-24 | 2000-03-03 | 2000-12-27 | 2001-03-09 | 0 | 0 | 0 | 10585212 | 350973 | 10936185 | 3.316% | 10936185 | 0 | 10936185 | 100% | 6.7723 | 100% | 0 | Project Closed | Final Acceptance
5017 | San Juan | San Martín | Luis Rodríguez | Housing Promoters | LMC | Enrique Ruiz & Assoc. | Del Valle Group | 300 | 300 | 0 | 300 | 0 | 1095 | 353 | 1448 | 32.24% | 1631 | 100% | 2003-05-14 | 2006-05-12 | 2007-04-30 | 2007-10-31 | 2008-01-30 | 0 | 0 | 0 | 19703000 | 845652.15 | 20548652.15 | 4.292% | 20180652.15 | 0 | 20180652.15 | 98.21% | 5.4367 | 100% | 0 | Project Closed | Final Acceptance
5023 | San Juan | San Fernando | Luis Rodríguez | Cost Control Company, Inc. | LMC | DDHK | Del Valle Group | 334 | 334 | 0 | 334 | 0 | 1190 | 807 | 1997 | 67.82% | 1965 | 100% | 2004-12-10 | 2008-03-13 | 2010-05-29 | 2010-04-28 | 2010-10-15 | 0 | Tax Credit | 0 | 32133000 | 1051432.05 | 33184432.05 | 3.272% | 33163350.99 | 0 | 33163350.99 | 99.94% | 5.8832 | 100% | 0 | Project Closed | Final Acceptance
5135 | San Juan | Las Dalias | Luis Rodríguez | Housing Promoters | CMS | CSA Architects | Del Valle Group | 240 | 240 | 0 | 240 | 0 | 1195 | 271 | 1466 | 22.68% | 1458 | 100% | 2004-02-25 | 2007-06-03 | 2008-02-29 | 2008-02-22 | 2008-04-22 | 0 | Tax Credit 908-2008 | 0 | 22437872.18 | 818872.18 | 23256744.36 | 3.65% | 23256744.36 | 0 | 23256744.36 | 100% | 6.075 | 100% | 0 | Project Closed | Final Acceptance
5161 | San Juan | El Manatial | Luis Rodríguez | MAS Corporation | CMS | Behar-Ybarra | Del Valle Group | 200 | 200 | 0 | 200 | 0 | 890 | 345 | 1235 | 38.76% | 1234 | 100% | 2004-01-26 | 2006-07-03 | 2007-06-13 | 2007-06-13 | 2008-05-19 | 0 | 0 | 0 | 12929000 | 1024355.41 | 13953355.41 | 7.923% | 13953355.41 | 0 | 13953355.41 | 100% | 6.17 | 100% | 0 | Project Closed | Final Acceptance
5080 | San Juan | Jardines de Cupey | Félix Ortiz | Cost Control Company, Inc. | URS Caribe | Gautier & de Torres | Ferrovial Agroman | 308 | 308 | 0 | 308 | 0 | 1095 | 628 | 1723 | 57.35% | 1660 | 100% | 2006-02-15 | 2009-02-13 | 2010-11-03 | 2010-09-02 | 2011-08-22 | 0 | Tax Credit | 0 | 33630461 | 1042731.4 | 34673192.4 | 3.101% | 34673192.4 | 0 | 34673192.4 | 100% | 5.3896 | 100% | 0 | Project Closed | Final Acceptance
5040 | San Juan | Jardines de Sellés Fase I (Take over agreement) | Luz Acevedo | 0 | BMA | URS Dames & Moore | Urban Builders (St. Paul Surety) | 184 | 184 | 0 | 184 | 0 | 90 | 0 | 90 | 0% | 114 | 100% | 2003-08-20 | 2003-11-17 | 2003-11-17 | 2003-12-12 | 2004-02-17 | 0 | CFP | 0 | 9975000 | 231719 | 10206719 | 2.323% | 10206719 | 0 | 10206719 | 100% | 0.61957 | 100% | 0 | Project Closed | Final Acceptance
5040 | San Juan | Jardines de Sellés (Fase II) | Luz Acevedo | Housing Promoters | BMA | URS Caribe | Rodríguez & del Valle | 216 | 216 | 0 | 216 | 0 | 1095 | 320 | 1415 | 29.22% | 1415 | 100% | 2002-06-17 | 2005-06-15 | 2006-05-01 | 2006-05-02 | 2007-05-27 | 0 | 0 | 0 | 15268000 | 968748 | 16236748 | 6.345% | 16236748 | 0 | 16236748 | 100% | 6.5509 | 100% | 0 | Project Closed | Final Acceptance
5015-5140 | San Juan | Las Gladiolas I & II | Félix Ortiz | MAS Corp. | CCC-JV | Méndez-Brunner | Del Valle Group | 676 | 676 | 0 | 676 | 0 | 365 | 77 | 442 | 21.1% | 449 | 100% | 2011-04-11 | 2012-04-09 | 2012-06-25 | 2012-07-03 | 2013-02-08 | 0 | CFP | 0 | 2932000 | 129200.55 | 3061200.55 | 4.407% | 3061200.55 | 0 | 3061200.55 | 100% | 0.6642 | 100% | 0 | Pending Close Out | Final Acceptance
2003 | San Juan | Puerta de Tierra | Pedro Vega | Cost Control Company, Inc. | LMC | Guillermety, Ortiz & Asoc. | Homeca Recycling 2007-0498A | 148 | 148 | 0 | 148 | 0 | 150 | 300 | 450 | 200% | 543 | 100% | 2007-03-22 | 2007-08-18 | 2008-06-13 | 2008-09-15 | 0 | 0 | CFP | 0 | 678000 | 152491.82 | 830491.82 | 22.49% | 830492 | 0 | 830492 | 100% | 3.6689 | 100% | 0 | Project Closed | Final Acceptance
2003 | San Juan | New Puerta de Tierra | Pedro Vega | Cost Control Company, Inc. | LMC | Guillermety, Ortiz & Asoc. | Cué & López Construction, Inc | 85 | 85 | 0 | 85 | 0 | 900 | 20 | 920 | 2.222% | 823 | 100% | 2008-11-10 | 2011-04-28 | 2011-05-18 | 2011-02-11 | 2011-05-17 | 0 | CFP/Línea de Crédito | 0 | 16770000 | 813871.99 | 17583871.99 | 4.853% | 17583871.99 | 0 | 17583871.99 | 100% | 9.6824 | 100% | 0 | Project Closed | Final Acceptance
2004 | San Juan | San Agustín | José M. Paris Escalera | AM Contractors | Klassik Builders | Ray Engineers PSC | Cuè & López Construction, Inc | 84 | 84 | 0 | 84 | 0 | 570 | 304 | 874 | 53.33% | 869 | 100% | 2009-12-14 | 2011-07-06 | 2012-05-05 | 2012-05-01 | 2012-07-18 | 0 | ARRA | 0 | 3746000 | 1029880.39 | 4775880.39 | 27.49% | 4775880.39 | 0 | 4775880.39 | 100% | 10.3452 | 100% | 0 | Project Closed | Final Acceptance
2012 | San Juan | Villa España | Pedro Vega | Cost Control Company | LMC | Ray Engineers, PSC | Rodríguez & del Valle | 500 | 500 | 0 | 500 | 0 | 1280 | 929 | 2209 | 72.58% | 2208 | 100% | 2003-09-29 | 2007-03-31 | 2009-10-15 | 2009-10-15 | 2010-10-21 | 0 | Tax Credit | 0 | 33768000 | 1862123 | 35630123 | 5.514% | 35630123 | 0 | 35630123 | 100% | 4.416 | 100% | 0 | Project Closed | Final Acceptance
3090 | Salinas | Bella Vista | Félix Ortiz | MJ Consulting | Klassik Builders | INTEGRA | LPC&D | 100 | 100 | 0 | 100 | 0 | 730 | 160 | 890 | 21.92% | 889 | 100% | 2009-09-08 | 2011-09-07 | 2012-02-14 | 2012-02-14 | 2012-07-16 | 0 | ARRA | 0 | 10500000 | 749675.93 | 11249675.93 | 7.14% | 11249675.93 | 0 | 11249675.93 | 100% | 8.89 | 100% | 0 | 0 | Final Acceptance
5092 | San Lorenzo | La Lorenzana | Iván Blanco | MJ Consulting | URS | René Acosta Ingenieros | CD Builders | 100 | 100 | 0 | 100 | 0 | 730 | 351 | 1081 | 48.08% | 1147 | 100% | 2005-09-14 | 2007-09-13 | 2008-08-29 | 2008-11-04 | 2009-09-17 | 0 | Tax Credit | 0 | 10310000 | 828444.55 | 11138444.55 | 8.035% | 11138444.55 | 0 | 11138444.55 | 100% | 11.47 | 100% | 0 | Project Closed | Final Acceptance
3087 | San Sebastian | Andrés Méndez Liceaga | Arturo Acevedo | Inn Capital Housing Division Joint Venture | CMS | Interplan | RC Engineering | 150 | 150 | 0 | 150 | 0 | 960 | 729 | 1689 | 75.94% | 1688 | 100% | 2004-05-24 | 2007-01-08 | 2009-01-06 | 2009-01-06 | 2009-02-16 | 0 | Tax Credit | 0 | 13130000 | 401586.86 | 13531586.86 | 3.059% | 13531587 | 0 | 13531587 | 100% | 11.2533 | 100% | 0 | Project Closed | Final Acceptance
5144 | Santa Isabel | Rincón Taíno | Rubén Cotto | J. A. Machuca | BMA | Hernández - Bauzá | Constructora I. Meléndez | 100 | 100 | 0 | 100 | 0 | 810 | 499 | 1309 | 61.6% | 1087 | 100% | 2003-07-28 | 2005-10-14 | 2007-02-25 | 2006-07-19 | 2006-09-30 | 0 | 0 | 0 | 7231087 | 175900 | 7406987 | 2.433% | 6372476 | 0 | 6372476 | 86.03% | 10.87 | 100% | 0 | Las OC # 7 y 8 fueron sometidas por el CM, pero le fueron devueltas para aclaracion o correccion, ya que el NGC no esta de acuerdo con el tiempo de extension otorgado y los "supporting documents". Posteriormente el CM las entrego fuera del termino de vigencia y las mismas no se pudieron procesar. El contratista sometio demanda y se efectuo reunion entre ambas representaciones legales. Se llego a un acuerdo: AVP de pagar lo que se le adeudaba por concepto de daños liquidos y retenido, Contratista: No reclamar "extended overhead" ni la OC #8. Esto hace varios meses y AVP tiene pendiente procesar los pagos correspondientes. | Final Acceptance
5198 | Toa Alta | Jardines de San Fernando | Luis Rodríguez | Housing Promoters | MD | URS Caribe, LLP | Orion Contractors | 51 | 51 | 0 | 51 | 0 | 800 | 1627 | 2427 | 203.4% | 2502 | 100% | 2006-01-09 | 2008-03-18 | 2012-08-31 | 2012-11-15 | 2013-10-15 | 0 | BFP-2003 | 0 | 7227000 | -982226.89 | 6244773.11 | -13.59% | 6244773.11 | 0 | 6244773.11 | 100% | 49.0588 | 100% | 0 | The PRPHA and the Contractor signed a Termination by Convinience (TBC), where the contractor grants a creditfor the amount of $2,182,368.61 for the remaining work phase IV,V and VIII. The PRPHA extends the contract by 744 calendar days providing a substantial termination effective at the August 31, 2012. The contractor walves its claim for extended overhead. | Final Acceptance
3069 | Toa Baja | El Toa | Jorge Mercado | MJ Consulting | AVP | Soler Cloquel & Asoc. | Royal Ins. | 80 | 80 | 0 | 80 | 0 | 669 | 458 | 1127 | 68.46% | 1205 | 100% | 1997-06-30 | 1999-04-29 | 2000-07-30 | 2000-10-17 | 2001-05-18 | 0 | 0 | 0 | 4045086 | 299127 | 4344213 | 7.395% | 4344213 | 0 | 4344213 | 100% | 15.0625 | 100% | 0 | Project Closed | Final Acceptance
5193 | Trujillo Alto | Los Rosales | José M. Paris Escalera | Peregrine Group Inc. | Klassik Builders | URS Caribe, LLP | Cidra Excavation, SE | 74 | 74 | 0 | 74 | 0 | 730 | 138 | 868 | 18.9% | 821 | 100% | 2009-11-16 | 2011-11-15 | 2012-04-01 | 2012-02-15 | 2012-08-14 | 0 | ARRA | 0 | 7947800 | 1458351.48 | 9406151.48 | 18.35% | 9406151.48 | 0 | 9406151.48 | 100% | 11.0946 | 100% | 0 | Project Closed | Final Acceptance
3071 | Vega Alta | Fco. Vega Sánchez | José Negrón | MJ Consulting | LMC | Hernández - Bauzá | Del Valle Group | 100 | 100 | 0 | 100 | 0 | 782 | 109 | 891 | 13.94% | 890 | 100% | 2000-10-02 | 2002-11-22 | 2003-03-11 | 2003-03-11 | 2003-04-11 | 0 | 0 | 0 | 9309000 | 70614.85 | 9379614.85 | 0.7586% | 9379616 | 0 | 9379616 | 100% | 8.9 | 100% | 0 | Project Closed | Final Acceptance
5105 | Vega Alta | Las Violetas | Luis Rodríguez | Cost Control Company, Inc. | ISS | URS Dames & Moore | Del Valle Group | 88 | 88 | 0 | 88 | 0 | 730 | 150 | 880 | 20.55% | 1000 | 100% | 2006-02-01 | 2008-01-31 | 2008-06-29 | 2008-10-28 | 2009-09-30 | 0 | Tax Credit | 0 | 9203600 | 46081.53 | 9249681.53 | 0.5007% | 9007681.53 | 0 | 9007681.53 | 97.38% | 11.3636 | 100% | 0 | Project Closed | Final Acceptance
3073 | Villalba | Efraín Suárez Negrón | Arturo Acevedo | J.A. Machuca | CMS | Yañez & Mayol | Ravaro Construction | 60 | 60 | 0 | 60 | 0 | 660 | 295 | 955 | 44.7% | 1240 | 100% | 2002-04-15 | 2004-02-03 | 2004-11-24 | 2005-09-06 | 2005-09-06 | 0 | 0 | 0 | 4033500 | 93123 | 4126623 | 2.309% | 4126623 | 0 | 4126623 | 100% | 20.6667 | 100% | 0 | Project Closed | Final Acceptance
5164 | Villalba | Maximino Miranda Jiménez | Félix Ortiz | Municipio de Villalba | Klassik Builders | LPA Group, Arq. | Constructora I. Meléndez | 100 | 100 | 0 | 100 | 0 | 732 | 180 | 912 | 24.59% | 911 | 100% | 2009-05-20 | 2011-05-21 | 2011-11-17 | 2011-11-17 | 2012-01-19 | 0 | CFP/ARRA | 0 | 12392438 | 408291.81 | 12800729.81 | 3.295% | 12800729.81 | 0 | 12800729.81 | 100% | 9.11 | 100% | 0 | Project Closed | Final Acceptance
5067 | Yauco | Ext. Santa Catalina | Rubén Cotto | Inn Capital Housing Division Joint Venture | URS | René Acosta Ingenieros | A. Rivera & Asociados | 24 | 24 | 0 | 24 | 0 | 548 | 319 | 867 | 58.21% | 814 | 100% | 2006-01-16 | 2007-07-17 | 2008-05-31 | 2008-04-09 | 2008-08-26 | 0 | CFP-2003 | 0 | 1972404 | 50556.96 | 2022960.96 | 2.563% | 2022961 | 0 | 2022961 | 100% | 33.9167 | 100% | 0 | Project Closed | Final Acceptance
| 7 | Active | [5 empty] | 17405 | 17405 | 0 | 17405 | 0 | [14 empty] | 0 | 0 | 1421928238.63 |  | 0 | 0 | 1412794333.5008 |  |  |  | 0 |  | Active
| 2 | Stoped | [5 empty] | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | Stoped
| 10 | Substantial | [5 empty] | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 13.542 |  |  |  | Substantial Completion
| 110 | Final Acceptance | [5 empty] | 17405 | 17405 | 0 | 17405 | 0 | [14 empty] | 1338745030.27 | 83183208.36 | 1421928238.63 |  | 1412794333.5008 | 0 | 1412794333.5008 |  | 9.8658 |  |  |  | Final Acceptance
Total | 129 | [6 empty] | 20299 | 19627 | 78 | 19705 | 60 | [14 empty] | 1493538072.27 | 97622150.87 | 3013088461.77 |  | 1558880043.8708 | 1271462.02 | 2972945839.3916 |  | 10.1721 |  | 0 |  | Total
| Revised by: |  |  |  | Approved by: | [19 empty] | Approved by:
|  | Luz M. Acevedo Pellot, PE |  |  |  |  | Germán Acevedo Marín, PE | [18 empty] | Arturo A. Garcia de la Noceda Castro, PE
|  | Project Coordinator |  |  |  |  | Director | [18 empty] | Deputy Administrator
|  | Construction Management Bureau |  |  |  |  | Construction Management Bureau | [18 empty] | Development and Construction Area
Report Date: |  |  | 2014-04-30
Report Last Revision Date: |  |  | 2014-05-10
Notes/Notas:
CMB Monthly Report is prepared for the use of Construction and Development Area. The Associate Administrator will approve any use of this report outside this area and must have his signature to be valid.
Informe preparado para uso del Área de Desarrollo y Construcción de Proyectos. El Administrador Asociado aprobará cualquier uso de este Informe fuera del Área y debe tener su firma para ser válido.
Information is provided by PRPHA Project Monitors, and is subject to change.
La Información es suministrada con los datos que proveen los Monitores de Proyectos, por lo que está sujeta a cambios.
Final Acceptance Report contains all Projects. This report is not worked by fiscal or natural year, it is a report that contains cumulative information and not all projects present monthly changes.
El Informe de "Final Acceptance" contiene todos los Proyectos. No se trabaja por Año Natural o Año Fiscal; es un reporte que contiene información acumulativa y no en todos los Proyectos se presentan cambios mensuales.
NOTIFICACIÓN DE CONFIDENCIALIDAD: Este Informe y cualquier archivo transmitido en ella pueden contener información confidencial, privilegiada y/o privada bajo las leyes aplicables. Se utiliza solamente para el uso o entidad a que se dirige. Si usted no es el destinatario intencional, se le notifica que cualquier uso, diseminación o copia de esta Informe se prohíbe estrictamente. Si usted recibe esta Informe por error, notificar al remitente inmediatamente y destruir el material en su totalidad.
CONFIDENTIALITY NOTICE: This report and any files transmitted with it may contain information that is confidential, privileged and exempt from disclosure under applicable law. It is intended solely for the use of the individual or entity to which it is addressed. If you are not the intended recipient, you are hereby notify that any use, dissemination or copying of this report is strictly prohibited. If you have received this communication by error, immediately contact the sender and destroy the material in its entirety, whether in electronic of hard copy format.
Note on AC15: lvlynn: Discrepancia: $98,932 Inf. Monitor
Note on H48: lvlynn: Contratista Default Target Engineering
Note on W77: lvlynn: 9-junio-09 Final
Note on W81: lvlynn:
Note on AC96: OC 1 @ 13
Note on Z97: lvlynn: CFP-Línea de Crédito