Designer Cost Estimate Report for Change Order No. __

| Project: | Modernization of ___________________Public Housing _________________, P.R. RQ-_______ |
| --- | --- |
| Date: | __________ |
| Change Order: | __________ |
| General Contractor: | _____________________________________ |
| Contract Number: | __________ |
| Design Firm: | _____________________________________ |
| CM/PM/Inspection Firm: | _____________________________________ |
| Change Order Cost: | __________ |

We submit for consideration this change order’s cost estimates based on an actual cost per unit, representing the construction industry cost.  The following table provides the cost estimate considered.

- Title 1

| LABOR: |  |  |  |  |
| --- | --- | --- | --- | --- |
| CLASSIFICATION |  | HOURS | RATE/HOUR | EXTENSION |
| Operators (3EA) (2 Month) |  | 960 | $ 7.00 | $ 6,720.00 |
| Driver (2 Month) |  | 320 | $ 6.50 | $ 2,080.00 |
| Labors (4 E.A.) |  | 1,280 | $ 5.51 | $ 7,052.80 |
| SUB-TOTAL |  |  |  | $ 15,852.80 |
| BENEFITS (38.25%) |  |  |  | $ 6,063.70 |
| TOTAL LABOR |  |  |  | ( $ 21,916.50) |
| EQUIPMENT |  |  |  |  |
| DESCRIPTION | QTY | UNIT | UNIT COST | TOTAL COST |
| Traxcavator | 2 | Month | $ 6,311.00 | $ 12,622.00 |
| Digger (2 EA) | 4 | Month | $ 2,612.00 | $ 10,448.00 |
| Dump Truck | 2 | Month | $ 6,000.00 | $ 12,000.00 |
| Air Compressor | 2 | Month | $ 1,051.00 | $ 2,102.00 |
| Concrete Saw | 1 | Month | $ 1,446.00 | $ 1,446.00 |
| SUB TOTAL EQUIPMENT |  |  |  | Form AVP-500603 Rev. June 2017 $ 38,618.00 |
| GAS, LUBRICANTS,ETC. (25%) |  |  |  | $ 9,654.50 |
| TOTAL EQUIPMENT |  |  |  | $ 48,272.50 |
| SUB CONTRACT |  |  |  |  |
| DESCRIPTION | QTY | UNIT | UNIT COST | TOTAL COST |
| 6" Crushed Stone | 690 | C.M. | $ 10.00 | $ 6,900.00 |
| 4" Black Base | 1,275 | Ton | $ 40.00 | $ 51,000.00 |
| 2" Asphalt Pavement | 625 | Ton | $ 60.00 | $ 37,500.00 |
| TOTAL MATERIALS |  |  |  | ( $ 95,400.00 ) |
| SUB TOTAL |  |  |  | $ 165,589.00 |
| SUERVISION (0%) |  |  |  |  |
| SUB TOTAL |  |  |  |  |
| INSURANCES (4.7%) |  |  |  | $ 7,782.68 |
| SUB TOTAL |  |  |  | $ 173,371.68 |
| OVERHEAD & PROFIT (0%) |  |  |  |  |
| FINAL TOTAL |  |  |  | ($ 173,371.68 ) |
| II. Title 2 |  |  |  |  |
| LABOR: |  |  |  |  |
| CLASSIFICATION |  | HOURS | RATE/HOUR | EXTENSION |
| Operators |  | 160 | $ 7.00 | $ 1,120.00 |
| Driver |  | 160 | $ 6.50 | $ 1,040.00 |
| Labors |  | 240 | $ 5.51 | $ 1,322.40 |
| Cement Mason (2 E.A.) |  | 120 | $ 5.85 | $ 702.00 |
| Cement Mason Helper (2 E.A.) |  | 120 | $ 5.51 | $ 661.20 |
| SUB-TOTAL |  |  |  | $ 4,845.60 |
| BENEFITS (38.25%) |  |  |  | $ 1,853.44 |
| TOTAL LABOR |  |  |  | $ 6,699.04 |
| EQUIPMENT |  |  |  |  |
| DESCRIPTION | QTY | UNIT | UNIT COST | TOTAL COST |
| Digger | 1 | Month | $ 2,612.00 | $ 2,612.00 |
| Dump Truck | 1 | Month | $ 6,000.00 | $ 6,000.00 |
| Concrete Saw | 1 | Week | $ 490.00 | $ 490.00 |
| Air Compressor | 1 | Month | $ 1,051.00 | $ 1,051.00 |
| SUB TOTAL EQUIPMENT |  |  |  | $ 10,153.00 |
| GAS, LUBRICANTS,ETC. (25%) |  |  |  | $ 2,538.25 |
| TOTAL EQUIPMENT |  |  |  | $ 12,691.25 |
| MATERIALS |  |  |  |  |
| DESCRIPTION | QTY | UNIT | UNIT COST | TOTAL COST |
| Concrete | 170 | C.Y. | $ 68.00 | $ 11,560.00 |
| Wood, Nails, Etc. | 1 | L.S. | $ 500.00 | $ 500.00 |
| TOTAL MATERIALS |  |  |  | $ 12,060.00 |
| SUB CONTRACT |  |  |  |  |
| DESCRIPTION | QTY | UNIT | UNIT COST | TOTAL COST |
| 1-1/2" Asphalt Pavement | 469 | Ton | $ 60.00 | $ 28,140.00 |
| TOTAL MATERIALS |  |  |  | $ 28,140.00 |
| SUB TOTAL |  |  |  | $ 59,590.29 |
| SUPERVISION (5%) |  |  |  | $ 2,979.51 |
| SUB TOTAL |  |  |  | $ 62,569.81 |
| INSURANCES (4.7%) |  |  |  | $ 2,940.78 |
| SUB TOTAL |  |  |  | $ 65,510.59 |
| OVERHEAD & PROFIT (15%) |  |  |  | $ 9,826.59 |
| FINAL TOTAL |  |  |  | $ 75,337.18 |
| III. SUMMARY: |  |  |  |  |
| CLASSIFICATION |  |  |  | EXTENSION |
| DEDUCTIVE COST |  |  |  | ($ 173,371.68) |
| ADDED COST |  |  |  | $ 75,337.18 |
| FINAL TOTAL |  |  |  | ($ 98,034.50) |

I hereby certify that the above detail is correct and we recommend the approval of this contract modification.

| Prepared by: |  |  |
| --- | --- | --- |
| Project Designer By: |  |  |
| Signature Date |  |  |